## Portfolio
project_id | project_name | client_name | industry_sector | delivery_model | project_start_date | baseline_end_date | duration_calendar_days | project_manager_id | project_manager_name | executive_sponsor_id | executive_sponsor_name | current_stage | planned_completion_pct | actual_completion_pct | overall_rag_status | project_objective | classification | synthetic_record
P001 | LuxHealth Data Platform | Synthetic Client A S.A. | Healthcare | Fixed Price | 2026-01-05 | 2026-12-18 | 348 | E011 | Maya Fernandes | E006 | Jean Schmit | UAT and transition | 86 | 84.3 | Green | Deliver a governed health-data platform with metadata, access control and secure exchange capabilities. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002 | Sovereign AI Factory | Synthetic Client B S.A. | Public Sector | Time & Materials | 2026-02-02 | 2026-12-18 | 320 | E011 | Maya Fernandes | E008 | Luca Conti | Production hardening | 92 | 93.5 | Amber | Deploy a local sovereign AI platform with accelerated inference, governed RAG and operational controls. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003 | Core Banking Modernisation | Synthetic Client C S.A. | Financial Services | Time & Materials | 2026-01-05 | 2026-11-30 | 330 | E012 | Julien Bernard | E009 | Amélie Dubois | Closed | 100 | 88.3 | Green | Modernize selected core-banking integration and reporting services. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004 | Smart Mobility Analytics | Synthetic Client D S.A. | Mobility | Fixed Price | 2026-03-02 | 2026-12-18 | 292 | E012 | Julien Bernard | E008 | Luca Conti | Pilot validation | 82 | 79.8 | Amber | Create an analytics foundation for corridor demand, operational mobility insights and forecasting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005 | Cloud Landing Zone | Synthetic Client E S.A. | Utilities | Time & Materials | 2026-01-05 | 2026-08-31 | 239 | E013 | Sara Khan | E009 | Amélie Dubois | Closed | 100 | 93.7 | Green | Implement a secure cloud landing zone, platform guardrails and delivery automation. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006 | AML Data Quality | Synthetic Client F S.A. | Financial Services | Fixed Price | 2026-02-02 | 2026-10-30 | 271 | E013 | Sara Khan | E007 | Claire Muller | Closed | 100 | 88.2 | Green | Improve AML data quality, lineage, exception management and regulatory controls. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007 | Cyber Resilience Programme | Synthetic Client G S.A. | Public Sector | Time & Materials | 2026-01-12 | 2026-12-18 | 341 | E014 | Nicolas Wagner | E006 | Jean Schmit | Resilience testing | 88 | 90.6 | Red | Strengthen cyber resilience, recovery controls, monitoring and evidence collection. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008 | Customer 360 Platform | Synthetic Client H S.A. | Retail | Fixed Price | 2026-04-06 | 2026-12-18 | 257 | E014 | Nicolas Wagner | E009 | Amélie Dubois | Integration and UAT | 78 | 76.3 | Amber | Build a governed customer-360 data product and activation layer. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009 | ERP Integration | Synthetic Client I S.A. | Industry | Time & Materials | 2026-01-05 | 2026-09-30 | 269 | E011 | Maya Fernandes | E009 | Amélie Dubois | Closed | 100 | 89 | Green | Integrate finance, procurement and delivery processes into the client ERP landscape. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010 | GenAI Knowledge Assistant | Synthetic Client J S.A. | Healthcare | Fixed Price | 2026-05-04 | 2026-12-18 | 229 | E014 | Nicolas Wagner | E008 | Luca Conti | Controlled pilot | 74 | 79.6 | Amber | Deliver a generative-AI knowledge assistant using local inference and restricted RAG. | PROJECT_MANAGEMENT_RESTRICTED | TRUE

## Resources
employee_id | employee_name | department | job_title | employment_type | fte | location | standard_hourly_project_cost_rate_eur | target_client_utilization_pct | resource_category | classification | privacy_note | synthetic_record
E001 | Sophie Lambert | Finance | Finance Director | Permanent | 1 | Luxembourg | 97.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E002 | Marc Hoffmann | Finance | Senior Financial Controller | Permanent | 1 | Luxembourg | 80 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E003 | Elena Rossi | Finance | Management Accountant | Permanent | 1 | Luxembourg | 62.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | Permanent | 1 | Luxembourg | 57.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E005 | Nadia Benali | Finance | Financial Analyst | Permanent | 1 | Luxembourg | 55 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E006 | Jean Schmit | Executive | Chief Executive Officer | Permanent | 1 | Luxembourg | 187.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E007 | Claire Muller | Executive | Chief Financial Officer | Permanent | 1 | Luxembourg | 157.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E008 | Luca Conti | Executive | Chief Technology Officer | Permanent | 1 | Luxembourg | 162.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E009 | Amélie Dubois | Executive | Chief Operating Officer | Permanent | 1 | Luxembourg | 150 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E010 | David Martin | Project Management | PMO Director | Permanent | 1 | Luxembourg | 105 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E011 | Maya Fernandes | Project Management | Senior Project Manager | Permanent | 1 | Luxembourg | 85 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E012 | Julien Bernard | Project Management | Senior Project Manager | Permanent | 1 | Luxembourg | 82.5 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E013 | Sara Khan | Project Management | Project Manager | Permanent | 1 | Luxembourg | 67.5 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E014 | Nicolas Wagner | Project Management | Project Manager | Permanent | 1 | Luxembourg | 67.5 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E015 | Inès Petit | Project Management | PMO Analyst | Permanent | 1 | Luxembourg | 55 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E016 | Olivier Lefevre | Project Management | Resource Manager | Permanent | 1 | Luxembourg | 65 | 68 | Project Manager | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E017 | Amina Amar | Data & AI | Principal Data & AI Architect | Permanent | 1 | Luxembourg | 120 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E018 | Gabriel Simon | Data & AI | Senior Data Architect | Permanent | 1 | Luxembourg | 100 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E019 | Eva Moreau | Data & AI | Senior AI Engineer | Permanent | 1 | Luxembourg | 100 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E020 | Antoine Robert | Data & AI | Data Engineer | Permanent | 1 | Luxembourg | 75 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E021 | Lea Nguyen | Data & AI | ML Engineer | Permanent | 1 | Luxembourg | 67.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E022 | Hugo Laurent | Data & AI | Data Scientist | Permanent | 1 | Luxembourg | 67.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E023 | Mila Costa | Cloud & Platform | Cloud Architect | Permanent | 1 | Luxembourg | 102.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | Permanent | 1 | Luxembourg | 77.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E025 | Camille Garcia | Cloud & Platform | Platform Engineer | Permanent | 1 | Luxembourg | 65 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E026 | Noah Durand | Cybersecurity | Security Architect | Permanent | 1 | Luxembourg | 117.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E027 | Emma Lopez | Cybersecurity | Security Engineer | Permanent | 1 | Luxembourg | 82.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E028 | Arthur Mercier | Consulting | Senior Business Consultant | Permanent | 1 | Luxembourg | 95 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E029 | Chloé Diallo | Consulting | Business Consultant | Permanent | 1 | Luxembourg | 60 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E030 | Rayan Fischer | Applications | Senior Software Engineer | Permanent | 1 | Luxembourg | 90 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E031 | Lucie Pereira | Applications | Software Engineer | Permanent | 1 | Luxembourg | 62.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E032 | Maxime Richard | Applications | QA Engineer | Permanent | 1 | Luxembourg | 62.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E033 | Aya Bauer | Sales | Account Director | Permanent | 1 | Luxembourg | 105 | 20 | Commercial | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E034 | Victor Renard | Sales | Account Manager | Permanent | 1 | Luxembourg | 72.5 | 20 | Commercial | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E035 | Alice Meier | HR | HR Business Partner | Permanent | 1 | Luxembourg | 65 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E036 | Nathan Cohen | HR | Talent Acquisition Specialist | Permanent | 1 | Luxembourg | 55 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E037 | Lina Gomes | Operations | Office & Operations Manager | Permanent | 1 | Luxembourg | 67.5 | 10 | Corporate | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | Permanent | 1 | Luxembourg | 120 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E039 | Jade Santos | Data & AI | Senior Data Architect | Permanent | 1 | Luxembourg | 100 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E040 | Adam Klein | Data & AI | Senior AI Engineer | Permanent | 1 | Luxembourg | 90 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E041 | Zoé Marques | Data & AI | Data Engineer | Permanent | 1 | Luxembourg | 67.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E042 | Samuel Jung | Data & AI | ML Engineer | Permanent | 1 | Luxembourg | 75 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E043 | Manon Franco | Data & AI | Data Scientist | Permanent | 1 | Luxembourg | 75 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | Permanent | 1 | Luxembourg | 97.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | Permanent | 1 | Luxembourg | 75 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | Permanent | 1 | Luxembourg | 67.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E047 | Mia Nowak | Cybersecurity | Security Architect | Permanent | 1 | Luxembourg | 115 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E048 | Raphaël Meyer | Cybersecurity | Security Engineer | Permanent | 1 | Luxembourg | 87.5 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E049 | Nora Aydin | Consulting | Senior Business Consultant | Permanent | 1 | Luxembourg | 90 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE
E050 | Mathis Girard | Consulting | Business Consultant | Permanent | 1 | Luxembourg | 60 | 78 | Delivery | PROJECT_MANAGEMENT_RESTRICTED | Project costing rate only; no salary information included. | TRUE

## Allocations
allocation_id | employee_id | employee_name | department | job_title | project_id | project_name | project_role | allocation_start_date | allocation_end_date | planned_allocation_pct | planned_hours_per_week | allocation_type | project_manager_name | standard_cost_rate_eur | classification | synthetic_record
A-E001-P001 | E001 | Sophie Lambert | Finance | Finance Director | P001 | LuxHealth Data Platform | Project Financial Support | 2026-01-05 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Maya Fernandes | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P002 | E001 | Sophie Lambert | Finance | Finance Director | P002 | Sovereign AI Factory | Project Financial Support | 2026-02-02 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Maya Fernandes | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P003 | E001 | Sophie Lambert | Finance | Finance Director | P003 | Core Banking Modernisation | Project Financial Support | 2026-01-05 | 2026-11-30 | 1 | 0.4 | Shared Specialist | Julien Bernard | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P004 | E001 | Sophie Lambert | Finance | Finance Director | P004 | Smart Mobility Analytics | Project Financial Support | 2026-03-02 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Julien Bernard | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P005 | E001 | Sophie Lambert | Finance | Finance Director | P005 | Cloud Landing Zone | Project Financial Support | 2026-01-05 | 2026-08-31 | 1 | 0.4 | Shared Specialist | Sara Khan | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P006 | E001 | Sophie Lambert | Finance | Finance Director | P006 | AML Data Quality | Project Financial Support | 2026-02-02 | 2026-10-30 | 1 | 0.4 | Shared Specialist | Sara Khan | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P007 | E001 | Sophie Lambert | Finance | Finance Director | P007 | Cyber Resilience Programme | Project Financial Support | 2026-01-12 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Nicolas Wagner | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P008 | E001 | Sophie Lambert | Finance | Finance Director | P008 | Customer 360 Platform | Project Financial Support | 2026-04-06 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Nicolas Wagner | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P009 | E001 | Sophie Lambert | Finance | Finance Director | P009 | ERP Integration | Project Financial Support | 2026-01-05 | 2026-09-30 | 1 | 0.4 | Shared Specialist | Maya Fernandes | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E001-P010 | E001 | Sophie Lambert | Finance | Finance Director | P010 | GenAI Knowledge Assistant | Project Financial Support | 2026-05-04 | 2026-12-18 | 1 | 0.4 | Shared Specialist | Nicolas Wagner | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P001 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P001 | LuxHealth Data Platform | Project Financial Support | 2026-01-05 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P002 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P002 | Sovereign AI Factory | Project Financial Support | 2026-02-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P003 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P003 | Core Banking Modernisation | Project Financial Support | 2026-01-05 | 2026-11-30 | 2 | 0.8 | Shared Specialist | Julien Bernard | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P004 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P004 | Smart Mobility Analytics | Project Financial Support | 2026-03-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Julien Bernard | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P005 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P005 | Cloud Landing Zone | Project Financial Support | 2026-01-05 | 2026-08-31 | 2 | 0.8 | Shared Specialist | Sara Khan | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P006 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P006 | AML Data Quality | Project Financial Support | 2026-02-02 | 2026-10-30 | 2 | 0.8 | Shared Specialist | Sara Khan | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P007 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P007 | Cyber Resilience Programme | Project Financial Support | 2026-01-12 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P008 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P008 | Customer 360 Platform | Project Financial Support | 2026-04-06 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P009 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P009 | ERP Integration | Project Financial Support | 2026-01-05 | 2026-09-30 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E002-P010 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | P010 | GenAI Knowledge Assistant | Project Financial Support | 2026-05-04 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 80 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P001 | E003 | Elena Rossi | Finance | Management Accountant | P001 | LuxHealth Data Platform | Project Financial Support | 2026-01-05 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P002 | E003 | Elena Rossi | Finance | Management Accountant | P002 | Sovereign AI Factory | Project Financial Support | 2026-02-02 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P003 | E003 | Elena Rossi | Finance | Management Accountant | P003 | Core Banking Modernisation | Project Financial Support | 2026-01-05 | 2026-11-30 | 3 | 1.2 | Shared Specialist | Julien Bernard | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P004 | E003 | Elena Rossi | Finance | Management Accountant | P004 | Smart Mobility Analytics | Project Financial Support | 2026-03-02 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Julien Bernard | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P005 | E003 | Elena Rossi | Finance | Management Accountant | P005 | Cloud Landing Zone | Project Financial Support | 2026-01-05 | 2026-08-31 | 3 | 1.2 | Shared Specialist | Sara Khan | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P006 | E003 | Elena Rossi | Finance | Management Accountant | P006 | AML Data Quality | Project Financial Support | 2026-02-02 | 2026-10-30 | 3 | 1.2 | Shared Specialist | Sara Khan | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P007 | E003 | Elena Rossi | Finance | Management Accountant | P007 | Cyber Resilience Programme | Project Financial Support | 2026-01-12 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Nicolas Wagner | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P008 | E003 | Elena Rossi | Finance | Management Accountant | P008 | Customer 360 Platform | Project Financial Support | 2026-04-06 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Nicolas Wagner | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P009 | E003 | Elena Rossi | Finance | Management Accountant | P009 | ERP Integration | Project Financial Support | 2026-01-05 | 2026-09-30 | 3 | 1.2 | Shared Specialist | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E003-P010 | E003 | Elena Rossi | Finance | Management Accountant | P010 | GenAI Knowledge Assistant | Project Financial Support | 2026-05-04 | 2026-12-18 | 3 | 1.2 | Shared Specialist | Nicolas Wagner | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P001 | E005 | Nadia Benali | Finance | Financial Analyst | P001 | LuxHealth Data Platform | Project Financial Support | 2026-01-05 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P002 | E005 | Nadia Benali | Finance | Financial Analyst | P002 | Sovereign AI Factory | Project Financial Support | 2026-02-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P003 | E005 | Nadia Benali | Finance | Financial Analyst | P003 | Core Banking Modernisation | Project Financial Support | 2026-01-05 | 2026-11-30 | 2 | 0.8 | Shared Specialist | Julien Bernard | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P004 | E005 | Nadia Benali | Finance | Financial Analyst | P004 | Smart Mobility Analytics | Project Financial Support | 2026-03-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Julien Bernard | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P005 | E005 | Nadia Benali | Finance | Financial Analyst | P005 | Cloud Landing Zone | Project Financial Support | 2026-01-05 | 2026-08-31 | 2 | 0.8 | Shared Specialist | Sara Khan | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P006 | E005 | Nadia Benali | Finance | Financial Analyst | P006 | AML Data Quality | Project Financial Support | 2026-02-02 | 2026-10-30 | 2 | 0.8 | Shared Specialist | Sara Khan | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P007 | E005 | Nadia Benali | Finance | Financial Analyst | P007 | Cyber Resilience Programme | Project Financial Support | 2026-01-12 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P008 | E005 | Nadia Benali | Finance | Financial Analyst | P008 | Customer 360 Platform | Project Financial Support | 2026-04-06 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P009 | E005 | Nadia Benali | Finance | Financial Analyst | P009 | ERP Integration | Project Financial Support | 2026-01-05 | 2026-09-30 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E005-P010 | E005 | Nadia Benali | Finance | Financial Analyst | P010 | GenAI Knowledge Assistant | Project Financial Support | 2026-05-04 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E006-P001 | E006 | Jean Schmit | Executive | Chief Executive Officer | P001 | LuxHealth Data Platform | Executive Sponsor / Steering | 2026-01-05 | 2026-12-18 | 2.5 | 1 | Shared Specialist | Maya Fernandes | 187.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E006-P002 | E006 | Jean Schmit | Executive | Chief Executive Officer | P002 | Sovereign AI Factory | Executive Sponsor / Steering | 2026-02-02 | 2026-12-18 | 2.5 | 1 | Shared Specialist | Maya Fernandes | 187.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E006-P003 | E006 | Jean Schmit | Executive | Chief Executive Officer | P003 | Core Banking Modernisation | Executive Sponsor / Steering | 2026-01-05 | 2026-11-30 | 2.5 | 1 | Shared Specialist | Julien Bernard | 187.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E006-P007 | E006 | Jean Schmit | Executive | Chief Executive Officer | P007 | Cyber Resilience Programme | Executive Sponsor / Steering | 2026-01-12 | 2026-12-18 | 2.5 | 1 | Shared Specialist | Nicolas Wagner | 187.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P001 | E007 | Claire Muller | Executive | Chief Financial Officer | P001 | LuxHealth Data Platform | Executive Sponsor / Steering | 2026-01-05 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P002 | E007 | Claire Muller | Executive | Chief Financial Officer | P002 | Sovereign AI Factory | Executive Sponsor / Steering | 2026-02-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P003 | E007 | Claire Muller | Executive | Chief Financial Officer | P003 | Core Banking Modernisation | Executive Sponsor / Steering | 2026-01-05 | 2026-11-30 | 2 | 0.8 | Shared Specialist | Julien Bernard | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P004 | E007 | Claire Muller | Executive | Chief Financial Officer | P004 | Smart Mobility Analytics | Executive Sponsor / Steering | 2026-03-02 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Julien Bernard | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P005 | E007 | Claire Muller | Executive | Chief Financial Officer | P005 | Cloud Landing Zone | Executive Sponsor / Steering | 2026-01-05 | 2026-08-31 | 2 | 0.8 | Shared Specialist | Sara Khan | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P006 | E007 | Claire Muller | Executive | Chief Financial Officer | P006 | AML Data Quality | Executive Sponsor / Steering | 2026-02-02 | 2026-10-30 | 2 | 0.8 | Shared Specialist | Sara Khan | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P007 | E007 | Claire Muller | Executive | Chief Financial Officer | P007 | Cyber Resilience Programme | Executive Sponsor / Steering | 2026-01-12 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P008 | E007 | Claire Muller | Executive | Chief Financial Officer | P008 | Customer 360 Platform | Executive Sponsor / Steering | 2026-04-06 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P009 | E007 | Claire Muller | Executive | Chief Financial Officer | P009 | ERP Integration | Executive Sponsor / Steering | 2026-01-05 | 2026-09-30 | 2 | 0.8 | Shared Specialist | Maya Fernandes | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E007-P010 | E007 | Claire Muller | Executive | Chief Financial Officer | P010 | GenAI Knowledge Assistant | Executive Sponsor / Steering | 2026-05-04 | 2026-12-18 | 2 | 0.8 | Shared Specialist | Nicolas Wagner | 157.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E008-P001 | E008 | Luca Conti | Executive | Chief Technology Officer | P001 | LuxHealth Data Platform | Executive Sponsor / Steering | 2026-01-05 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 162.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E008-P002 | E008 | Luca Conti | Executive | Chief Technology Officer | P002 | Sovereign AI Factory | Executive Sponsor / Steering | 2026-02-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 162.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E008-P004 | E008 | Luca Conti | Executive | Chief Technology Officer | P004 | Smart Mobility Analytics | Executive Sponsor / Steering | 2026-03-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Julien Bernard | 162.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E008-P007 | E008 | Luca Conti | Executive | Chief Technology Officer | P007 | Cyber Resilience Programme | Executive Sponsor / Steering | 2026-01-12 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 162.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E008-P010 | E008 | Luca Conti | Executive | Chief Technology Officer | P010 | GenAI Knowledge Assistant | Executive Sponsor / Steering | 2026-05-04 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 162.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E009-P003 | E009 | Amélie Dubois | Executive | Chief Operating Officer | P003 | Core Banking Modernisation | Executive Sponsor / Steering | 2026-01-05 | 2026-11-30 | 4 | 1.6 | Shared Specialist | Julien Bernard | 150 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E009-P005 | E009 | Amélie Dubois | Executive | Chief Operating Officer | P005 | Cloud Landing Zone | Executive Sponsor / Steering | 2026-01-05 | 2026-08-31 | 4 | 1.6 | Shared Specialist | Sara Khan | 150 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E009-P006 | E009 | Amélie Dubois | Executive | Chief Operating Officer | P006 | AML Data Quality | Executive Sponsor / Steering | 2026-02-02 | 2026-10-30 | 4 | 1.6 | Shared Specialist | Sara Khan | 150 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E009-P008 | E009 | Amélie Dubois | Executive | Chief Operating Officer | P008 | Customer 360 Platform | Executive Sponsor / Steering | 2026-04-06 | 2026-12-18 | 4 | 1.6 | Shared Specialist | Nicolas Wagner | 150 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E009-P009 | E009 | Amélie Dubois | Executive | Chief Operating Officer | P009 | ERP Integration | Executive Sponsor / Steering | 2026-01-05 | 2026-09-30 | 4 | 1.6 | Shared Specialist | Maya Fernandes | 150 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P001 | E010 | David Martin | Project Management | PMO Director | P001 | LuxHealth Data Platform | PMO Director | 2026-01-05 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P002 | E010 | David Martin | Project Management | PMO Director | P002 | Sovereign AI Factory | PMO Director | 2026-02-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P003 | E010 | David Martin | Project Management | PMO Director | P003 | Core Banking Modernisation | PMO Director | 2026-01-05 | 2026-11-30 | 5 | 2 | Shared Specialist | Julien Bernard | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P004 | E010 | David Martin | Project Management | PMO Director | P004 | Smart Mobility Analytics | PMO Director | 2026-03-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Julien Bernard | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P005 | E010 | David Martin | Project Management | PMO Director | P005 | Cloud Landing Zone | PMO Director | 2026-01-05 | 2026-08-31 | 5 | 2 | Shared Specialist | Sara Khan | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P006 | E010 | David Martin | Project Management | PMO Director | P006 | AML Data Quality | PMO Director | 2026-02-02 | 2026-10-30 | 5 | 2 | Shared Specialist | Sara Khan | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P007 | E010 | David Martin | Project Management | PMO Director | P007 | Cyber Resilience Programme | PMO Director | 2026-01-12 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P008 | E010 | David Martin | Project Management | PMO Director | P008 | Customer 360 Platform | PMO Director | 2026-04-06 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P009 | E010 | David Martin | Project Management | PMO Director | P009 | ERP Integration | PMO Director | 2026-01-05 | 2026-09-30 | 5 | 2 | Shared Specialist | Maya Fernandes | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E010-P010 | E010 | David Martin | Project Management | PMO Director | P010 | GenAI Knowledge Assistant | PMO Director | 2026-05-04 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E011-P001 | E011 | Maya Fernandes | Project Management | Senior Project Manager | P001 | LuxHealth Data Platform | Project Manager | 2026-01-05 | 2026-12-18 | 45 | 18 | Primary Shared | Maya Fernandes | 85 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E011-P002 | E011 | Maya Fernandes | Project Management | Senior Project Manager | P002 | Sovereign AI Factory | Project Manager | 2026-02-02 | 2026-12-18 | 40 | 16 | Primary Shared | Maya Fernandes | 85 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E011-P009 | E011 | Maya Fernandes | Project Management | Senior Project Manager | P009 | ERP Integration | Project Manager | 2026-01-05 | 2026-09-30 | 15 | 6 | Shared Specialist | Maya Fernandes | 85 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E012-P003 | E012 | Julien Bernard | Project Management | Senior Project Manager | P003 | Core Banking Modernisation | Project Manager | 2026-01-05 | 2026-11-30 | 55 | 22 | Primary Shared | Julien Bernard | 82.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E012-P004 | E012 | Julien Bernard | Project Management | Senior Project Manager | P004 | Smart Mobility Analytics | Project Manager | 2026-03-02 | 2026-12-18 | 45 | 18 | Primary Shared | Julien Bernard | 82.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E013-P005 | E013 | Sara Khan | Project Management | Project Manager | P005 | Cloud Landing Zone | Project Manager | 2026-01-05 | 2026-08-31 | 50 | 20 | Primary Shared | Sara Khan | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E013-P006 | E013 | Sara Khan | Project Management | Project Manager | P006 | AML Data Quality | Project Manager | 2026-02-02 | 2026-10-30 | 50 | 20 | Primary Shared | Sara Khan | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E014-P007 | E014 | Nicolas Wagner | Project Management | Project Manager | P007 | Cyber Resilience Programme | Project Manager | 2026-01-12 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E014-P008 | E014 | Nicolas Wagner | Project Management | Project Manager | P008 | Customer 360 Platform | Project Manager | 2026-04-06 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E014-P010 | E014 | Nicolas Wagner | Project Management | Project Manager | P010 | GenAI Knowledge Assistant | Project Manager | 2026-05-04 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P001 | E015 | Inès Petit | Project Management | PMO Analyst | P001 | LuxHealth Data Platform | PMO Analyst | 2026-01-05 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P002 | E015 | Inès Petit | Project Management | PMO Analyst | P002 | Sovereign AI Factory | PMO Analyst | 2026-02-02 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P003 | E015 | Inès Petit | Project Management | PMO Analyst | P003 | Core Banking Modernisation | PMO Analyst | 2026-01-05 | 2026-11-30 | 8 | 3.2 | Shared Specialist | Julien Bernard | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P004 | E015 | Inès Petit | Project Management | PMO Analyst | P004 | Smart Mobility Analytics | PMO Analyst | 2026-03-02 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Julien Bernard | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P005 | E015 | Inès Petit | Project Management | PMO Analyst | P005 | Cloud Landing Zone | PMO Analyst | 2026-01-05 | 2026-08-31 | 8 | 3.2 | Shared Specialist | Sara Khan | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P006 | E015 | Inès Petit | Project Management | PMO Analyst | P006 | AML Data Quality | PMO Analyst | 2026-02-02 | 2026-10-30 | 8 | 3.2 | Shared Specialist | Sara Khan | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P007 | E015 | Inès Petit | Project Management | PMO Analyst | P007 | Cyber Resilience Programme | PMO Analyst | 2026-01-12 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P008 | E015 | Inès Petit | Project Management | PMO Analyst | P008 | Customer 360 Platform | PMO Analyst | 2026-04-06 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P009 | E015 | Inès Petit | Project Management | PMO Analyst | P009 | ERP Integration | PMO Analyst | 2026-01-05 | 2026-09-30 | 8 | 3.2 | Shared Specialist | Maya Fernandes | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E015-P010 | E015 | Inès Petit | Project Management | PMO Analyst | P010 | GenAI Knowledge Assistant | PMO Analyst | 2026-05-04 | 2026-12-18 | 8 | 3.2 | Shared Specialist | Nicolas Wagner | 55 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P001 | E016 | Olivier Lefevre | Project Management | Resource Manager | P001 | LuxHealth Data Platform | Resource Manager | 2026-01-05 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P002 | E016 | Olivier Lefevre | Project Management | Resource Manager | P002 | Sovereign AI Factory | Resource Manager | 2026-02-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Maya Fernandes | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P003 | E016 | Olivier Lefevre | Project Management | Resource Manager | P003 | Core Banking Modernisation | Resource Manager | 2026-01-05 | 2026-11-30 | 5 | 2 | Shared Specialist | Julien Bernard | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P004 | E016 | Olivier Lefevre | Project Management | Resource Manager | P004 | Smart Mobility Analytics | Resource Manager | 2026-03-02 | 2026-12-18 | 5 | 2 | Shared Specialist | Julien Bernard | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P005 | E016 | Olivier Lefevre | Project Management | Resource Manager | P005 | Cloud Landing Zone | Resource Manager | 2026-01-05 | 2026-08-31 | 5 | 2 | Shared Specialist | Sara Khan | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P006 | E016 | Olivier Lefevre | Project Management | Resource Manager | P006 | AML Data Quality | Resource Manager | 2026-02-02 | 2026-10-30 | 5 | 2 | Shared Specialist | Sara Khan | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P007 | E016 | Olivier Lefevre | Project Management | Resource Manager | P007 | Cyber Resilience Programme | Resource Manager | 2026-01-12 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P008 | E016 | Olivier Lefevre | Project Management | Resource Manager | P008 | Customer 360 Platform | Resource Manager | 2026-04-06 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P009 | E016 | Olivier Lefevre | Project Management | Resource Manager | P009 | ERP Integration | Resource Manager | 2026-01-05 | 2026-09-30 | 5 | 2 | Shared Specialist | Maya Fernandes | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E016-P010 | E016 | Olivier Lefevre | Project Management | Resource Manager | P010 | GenAI Knowledge Assistant | Resource Manager | 2026-05-04 | 2026-12-18 | 5 | 2 | Shared Specialist | Nicolas Wagner | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E017-P001 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | P001 | LuxHealth Data Platform | Data & AI Architect | 2026-01-05 | 2026-12-18 | 60 | 24 | Primary Shared | Maya Fernandes | 120 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E017-P002 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | P002 | Sovereign AI Factory | Data & AI Architect | 2026-02-02 | 2026-12-18 | 30 | 12 | Shared Specialist | Maya Fernandes | 120 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E018-P001 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | P001 | LuxHealth Data Platform | Data Architect | 2026-01-05 | 2026-12-18 | 70 | 28 | Dedicated | Maya Fernandes | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E018-P006 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | P006 | AML Data Quality | Data Architect | 2026-02-02 | 2026-10-30 | 20 | 8 | Shared Specialist | Sara Khan | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E019-P002 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | P002 | Sovereign AI Factory | AI Engineer | 2026-02-02 | 2026-12-18 | 80 | 32 | Dedicated | Maya Fernandes | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E019-P010 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | P010 | GenAI Knowledge Assistant | AI Engineer | 2026-05-04 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E020-P001 | E020 | Antoine Robert | Data & AI | Data Engineer | P001 | LuxHealth Data Platform | Data Engineer | 2026-01-05 | 2026-12-18 | 70 | 28 | Dedicated | Maya Fernandes | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E020-P006 | E020 | Antoine Robert | Data & AI | Data Engineer | P006 | AML Data Quality | Data Engineer | 2026-02-02 | 2026-10-30 | 30 | 12 | Shared Specialist | Sara Khan | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E021-P002 | E021 | Lea Nguyen | Data & AI | ML Engineer | P002 | Sovereign AI Factory | ML Engineer | 2026-02-02 | 2026-12-18 | 80 | 32 | Dedicated | Maya Fernandes | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E021-P010 | E021 | Lea Nguyen | Data & AI | ML Engineer | P010 | GenAI Knowledge Assistant | ML Engineer | 2026-05-04 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E022-P004 | E022 | Hugo Laurent | Data & AI | Data Scientist | P004 | Smart Mobility Analytics | Data Scientist | 2026-03-02 | 2026-12-18 | 70 | 28 | Dedicated | Julien Bernard | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E022-P010 | E022 | Hugo Laurent | Data & AI | Data Scientist | P010 | GenAI Knowledge Assistant | Data Scientist | 2026-05-04 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E023-P005 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | P005 | Cloud Landing Zone | Cloud Architect | 2026-01-05 | 2026-08-31 | 80 | 32 | Dedicated | Sara Khan | 102.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E023-P001 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | P001 | LuxHealth Data Platform | Cloud Architect | 2026-01-05 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 102.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E024-P005 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | P005 | Cloud Landing Zone | DevOps Engineer | 2026-01-05 | 2026-08-31 | 80 | 32 | Dedicated | Sara Khan | 77.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E024-P002 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | P002 | Sovereign AI Factory | DevOps Engineer | 2026-02-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 77.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E025-P005 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | P005 | Cloud Landing Zone | Platform Engineer | 2026-01-05 | 2026-08-31 | 70 | 28 | Dedicated | Sara Khan | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E025-P009 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | P009 | ERP Integration | Platform Engineer | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 65 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E026-P003 | E026 | Noah Durand | Cybersecurity | Security Architect | P003 | Core Banking Modernisation | Security Architect | 2026-01-05 | 2026-11-30 | 40 | 16 | Primary Shared | Julien Bernard | 117.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E026-P007 | E026 | Noah Durand | Cybersecurity | Security Architect | P007 | Cyber Resilience Programme | Security Architect | 2026-01-12 | 2026-12-18 | 40 | 16 | Primary Shared | Nicolas Wagner | 117.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E026-P001 | E026 | Noah Durand | Cybersecurity | Security Architect | P001 | LuxHealth Data Platform | Security Architect | 2026-01-05 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 117.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E027-P005 | E027 | Emma Lopez | Cybersecurity | Security Engineer | P005 | Cloud Landing Zone | Security Engineer | 2026-01-05 | 2026-08-31 | 40 | 16 | Primary Shared | Sara Khan | 82.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E027-P007 | E027 | Emma Lopez | Cybersecurity | Security Engineer | P007 | Cyber Resilience Programme | Security Engineer | 2026-01-12 | 2026-12-18 | 40 | 16 | Primary Shared | Nicolas Wagner | 82.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E027-P002 | E027 | Emma Lopez | Cybersecurity | Security Engineer | P002 | Sovereign AI Factory | Security Engineer | 2026-02-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 82.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E028-P001 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | P001 | LuxHealth Data Platform | Senior Business Consultant | 2026-01-05 | 2026-12-18 | 50 | 20 | Primary Shared | Maya Fernandes | 95 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E028-P006 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | P006 | AML Data Quality | Senior Business Consultant | 2026-02-02 | 2026-10-30 | 30 | 12 | Shared Specialist | Sara Khan | 95 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E028-P003 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | P003 | Core Banking Modernisation | Senior Business Consultant | 2026-01-05 | 2026-11-30 | 20 | 8 | Shared Specialist | Julien Bernard | 95 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E029-P004 | E029 | Chloé Diallo | Consulting | Business Consultant | P004 | Smart Mobility Analytics | Business Consultant | 2026-03-02 | 2026-12-18 | 60 | 24 | Primary Shared | Julien Bernard | 60 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E029-P006 | E029 | Chloé Diallo | Consulting | Business Consultant | P006 | AML Data Quality | Business Consultant | 2026-02-02 | 2026-10-30 | 40 | 16 | Primary Shared | Sara Khan | 60 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E030-P003 | E030 | Rayan Fischer | Applications | Senior Software Engineer | P003 | Core Banking Modernisation | Senior Software Engineer | 2026-01-05 | 2026-11-30 | 50 | 20 | Primary Shared | Julien Bernard | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E030-P009 | E030 | Rayan Fischer | Applications | Senior Software Engineer | P009 | ERP Integration | Senior Software Engineer | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E030-P001 | E030 | Rayan Fischer | Applications | Senior Software Engineer | P001 | LuxHealth Data Platform | Senior Software Engineer | 2026-01-05 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E031-P001 | E031 | Lucie Pereira | Applications | Software Engineer | P001 | LuxHealth Data Platform | Software Engineer | 2026-01-05 | 2026-12-18 | 50 | 20 | Primary Shared | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E031-P009 | E031 | Lucie Pereira | Applications | Software Engineer | P009 | ERP Integration | Software Engineer | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E031-P004 | E031 | Lucie Pereira | Applications | Software Engineer | P004 | Smart Mobility Analytics | Software Engineer | 2026-03-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Julien Bernard | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E032-P003 | E032 | Maxime Richard | Applications | QA Engineer | P003 | Core Banking Modernisation | QA Engineer | 2026-01-05 | 2026-11-30 | 40 | 16 | Primary Shared | Julien Bernard | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E032-P009 | E032 | Maxime Richard | Applications | QA Engineer | P009 | ERP Integration | QA Engineer | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E032-P010 | E032 | Maxime Richard | Applications | QA Engineer | P010 | GenAI Knowledge Assistant | QA Engineer | 2026-05-04 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 62.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E033-P002 | E033 | Aya Bauer | Sales | Account Director | P002 | Sovereign AI Factory | Account / Commercial Support | 2026-02-02 | 2026-12-18 | 10 | 4 | Shared Specialist | Maya Fernandes | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E033-P010 | E033 | Aya Bauer | Sales | Account Director | P010 | GenAI Knowledge Assistant | Account / Commercial Support | 2026-05-04 | 2026-12-18 | 10 | 4 | Shared Specialist | Nicolas Wagner | 105 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E034-P001 | E034 | Victor Renard | Sales | Account Manager | P001 | LuxHealth Data Platform | Account / Commercial Support | 2026-01-05 | 2026-12-18 | 10 | 4 | Shared Specialist | Maya Fernandes | 72.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E034-P008 | E034 | Victor Renard | Sales | Account Manager | P008 | Customer 360 Platform | Account / Commercial Support | 2026-04-06 | 2026-12-18 | 10 | 4 | Shared Specialist | Nicolas Wagner | 72.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E038-P003 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | P003 | Core Banking Modernisation | Data & AI Architect | 2026-01-05 | 2026-11-30 | 60 | 24 | Primary Shared | Julien Bernard | 120 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E038-P008 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | P008 | Customer 360 Platform | Data & AI Architect | 2026-04-06 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 120 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E038-P004 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | P004 | Smart Mobility Analytics | Data & AI Architect | 2026-03-02 | 2026-12-18 | 10 | 4 | Shared Specialist | Julien Bernard | 120 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E039-P003 | E039 | Jade Santos | Data & AI | Senior Data Architect | P003 | Core Banking Modernisation | Data Architect | 2026-01-05 | 2026-11-30 | 70 | 28 | Dedicated | Julien Bernard | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E039-P008 | E039 | Jade Santos | Data & AI | Senior Data Architect | P008 | Customer 360 Platform | Data Architect | 2026-04-06 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 100 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E040-P008 | E040 | Adam Klein | Data & AI | Senior AI Engineer | P008 | Customer 360 Platform | AI Engineer | 2026-04-06 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E040-P010 | E040 | Adam Klein | Data & AI | Senior AI Engineer | P010 | GenAI Knowledge Assistant | AI Engineer | 2026-05-04 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E041-P003 | E041 | Zoé Marques | Data & AI | Data Engineer | P003 | Core Banking Modernisation | Data Engineer | 2026-01-05 | 2026-11-30 | 50 | 20 | Primary Shared | Julien Bernard | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E041-P004 | E041 | Zoé Marques | Data & AI | Data Engineer | P004 | Smart Mobility Analytics | Data Engineer | 2026-03-02 | 2026-12-18 | 30 | 12 | Shared Specialist | Julien Bernard | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E041-P008 | E041 | Zoé Marques | Data & AI | Data Engineer | P008 | Customer 360 Platform | Data Engineer | 2026-04-06 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E042-P004 | E042 | Samuel Jung | Data & AI | ML Engineer | P004 | Smart Mobility Analytics | ML Engineer | 2026-03-02 | 2026-12-18 | 50 | 20 | Primary Shared | Julien Bernard | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E042-P010 | E042 | Samuel Jung | Data & AI | ML Engineer | P010 | GenAI Knowledge Assistant | ML Engineer | 2026-05-04 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E043-P004 | E043 | Manon Franco | Data & AI | Data Scientist | P004 | Smart Mobility Analytics | Data Scientist | 2026-03-02 | 2026-12-18 | 60 | 24 | Primary Shared | Julien Bernard | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E043-P008 | E043 | Manon Franco | Data & AI | Data Scientist | P008 | Customer 360 Platform | Data Scientist | 2026-04-06 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E043-P010 | E043 | Manon Franco | Data & AI | Data Scientist | P010 | GenAI Knowledge Assistant | Data Scientist | 2026-05-04 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E044-P007 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | P007 | Cyber Resilience Programme | Cloud Architect | 2026-01-12 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E044-P004 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | P004 | Smart Mobility Analytics | Cloud Architect | 2026-03-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Julien Bernard | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E044-P005 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | P005 | Cloud Landing Zone | Cloud Architect | 2026-01-05 | 2026-08-31 | 30 | 12 | Shared Specialist | Sara Khan | 97.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E045-P007 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | P007 | Cyber Resilience Programme | DevOps Engineer | 2026-01-12 | 2026-12-18 | 80 | 32 | Dedicated | Nicolas Wagner | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E045-P002 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | P002 | Sovereign AI Factory | DevOps Engineer | 2026-02-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 75 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E046-P007 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | P007 | Cyber Resilience Programme | Platform Engineer | 2026-01-12 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E046-P009 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | P009 | ERP Integration | Platform Engineer | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E046-P005 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | P005 | Cloud Landing Zone | Platform Engineer | 2026-01-05 | 2026-08-31 | 20 | 8 | Shared Specialist | Sara Khan | 67.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E047-P007 | E047 | Mia Nowak | Cybersecurity | Security Architect | P007 | Cyber Resilience Programme | Security Architect | 2026-01-12 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 115 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E047-P006 | E047 | Mia Nowak | Cybersecurity | Security Architect | P006 | AML Data Quality | Security Architect | 2026-02-02 | 2026-10-30 | 30 | 12 | Shared Specialist | Sara Khan | 115 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E047-P003 | E047 | Mia Nowak | Cybersecurity | Security Architect | P003 | Core Banking Modernisation | Security Architect | 2026-01-05 | 2026-11-30 | 20 | 8 | Shared Specialist | Julien Bernard | 115 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E048-P007 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | P007 | Cyber Resilience Programme | Security Engineer | 2026-01-12 | 2026-12-18 | 50 | 20 | Primary Shared | Nicolas Wagner | 87.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E048-P006 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | P006 | AML Data Quality | Security Engineer | 2026-02-02 | 2026-10-30 | 30 | 12 | Shared Specialist | Sara Khan | 87.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E048-P002 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | P002 | Sovereign AI Factory | Security Engineer | 2026-02-02 | 2026-12-18 | 20 | 8 | Shared Specialist | Maya Fernandes | 87.5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E049-P003 | E049 | Nora Aydin | Consulting | Senior Business Consultant | P003 | Core Banking Modernisation | Senior Business Consultant | 2026-01-05 | 2026-11-30 | 50 | 20 | Primary Shared | Julien Bernard | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E049-P007 | E049 | Nora Aydin | Consulting | Senior Business Consultant | P007 | Cyber Resilience Programme | Senior Business Consultant | 2026-01-12 | 2026-12-18 | 20 | 8 | Shared Specialist | Nicolas Wagner | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E049-P009 | E049 | Nora Aydin | Consulting | Senior Business Consultant | P009 | ERP Integration | Senior Business Consultant | 2026-01-05 | 2026-09-30 | 30 | 12 | Shared Specialist | Maya Fernandes | 90 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E050-P009 | E050 | Mathis Girard | Consulting | Business Consultant | P009 | ERP Integration | Business Consultant | 2026-01-05 | 2026-09-30 | 50 | 20 | Primary Shared | Maya Fernandes | 60 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E050-P005 | E050 | Mathis Girard | Consulting | Business Consultant | P005 | Cloud Landing Zone | Business Consultant | 2026-01-05 | 2026-08-31 | 20 | 8 | Shared Specialist | Sara Khan | 60 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
A-E050-P008 | E050 | Mathis Girard | Consulting | Business Consultant | P008 | Customer 360 Platform | Business Consultant | 2026-04-06 | 2026-12-18 | 30 | 12 | Shared Specialist | Nicolas Wagner | 60 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE

## Timesheets
timesheet_line_id | week_start_date | employee_id | employee_name | department | project_id | project_name | work_package_id | activity_description | billable_flag | hours_logged | standard_cost_rate_eur | labor_cost_eur | approval_status | approver_name | approval_comment | classification | synthetic_record
TS-000001 | 2026-01-05 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000002 | 2026-01-05 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000003 | 2026-01-05 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000004 | 2026-01-05 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000005 | 2026-01-05 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 97.5 | 2925 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000006 | 2026-01-05 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000007 | 2026-01-05 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000008 | 2026-01-05 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000009 | 2026-01-05 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000010 | 2026-01-05 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000011 | 2026-01-05 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 80 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000012 | 2026-01-05 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000013 | 2026-01-05 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000014 | 2026-01-05 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000015 | 2026-01-05 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000016 | 2026-01-05 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000017 | 2026-01-05 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000018 | 2026-01-05 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000019 | 2026-01-05 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000020 | 2026-01-05 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000021 | 2026-01-05 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000022 | 2026-01-05 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000023 | 2026-01-05 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000024 | 2026-01-05 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000025 | 2026-01-05 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 55 | 1650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000026 | 2026-01-05 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000027 | 2026-01-05 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000028 | 2026-01-05 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000029 | 2026-01-05 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 187.5 | 5625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000030 | 2026-01-05 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000031 | 2026-01-05 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000032 | 2026-01-05 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000033 | 2026-01-05 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000034 | 2026-01-05 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000035 | 2026-01-05 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 157.5 | 4725 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000036 | 2026-01-05 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000037 | 2026-01-05 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000038 | 2026-01-05 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30.5 | 162.5 | 4956.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000039 | 2026-01-05 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000040 | 2026-01-05 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000041 | 2026-01-05 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000042 | 2026-01-05 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000043 | 2026-01-05 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27.5 | 150 | 4125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000044 | 2026-01-05 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000045 | 2026-01-05 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000046 | 2026-01-05 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000047 | 2026-01-05 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000048 | 2026-01-05 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000049 | 2026-01-05 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000050 | 2026-01-05 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000051 | 2026-01-05 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 14.5 | 85 | 1232.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000052 | 2026-01-05 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5 | 85 | 425 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000053 | 2026-01-05 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 12.5 | 85 | 1062.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000054 | 2026-01-05 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000055 | 2026-01-05 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000056 | 2026-01-05 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 15 | 82.5 | 1237.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000057 | 2026-01-05 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000058 | 2026-01-05 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 15.5 | 67.5 | 1046.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000059 | 2026-01-05 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16.5 | 67.5 | 1113.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000060 | 2026-01-05 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000061 | 2026-01-05 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000062 | 2026-01-05 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000063 | 2026-01-05 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000064 | 2026-01-05 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000065 | 2026-01-05 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000066 | 2026-01-05 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000067 | 2026-01-05 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21.5 | 55 | 1182.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000068 | 2026-01-05 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000069 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000070 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000071 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000072 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000073 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000074 | 2026-01-05 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000075 | 2026-01-05 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 120 | 2100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000076 | 2026-01-05 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 120 | 1980 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000077 | 2026-01-05 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000078 | 2026-01-05 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 100 | 2050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000079 | 2026-01-05 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 100 | 1150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000080 | 2026-01-05 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000081 | 2026-01-05 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 100 | 3200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000082 | 2026-01-05 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000083 | 2026-01-05 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23.5 | 75 | 1762.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000084 | 2026-01-05 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 75 | 637.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000085 | 2026-01-05 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000086 | 2026-01-05 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000087 | 2026-01-05 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000088 | 2026-01-05 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000089 | 2026-01-05 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000090 | 2026-01-05 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 24.5 | 102.5 | 2511.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000091 | 2026-01-05 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 102.5 | 666.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000092 | 2026-01-05 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 102.5 | 102.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000093 | 2026-01-05 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000094 | 2026-01-05 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26.5 | 77.5 | 2053.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000095 | 2026-01-05 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 77.5 | 426.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000096 | 2026-01-05 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000097 | 2026-01-05 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 65 | 1462.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000098 | 2026-01-05 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9.5 | 65 | 617.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000099 | 2026-01-05 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000100 | 2026-01-05 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14 | 117.5 | 1645 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000101 | 2026-01-05 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 117.5 | 705 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000102 | 2026-01-05 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 117.5 | 705 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000103 | 2026-01-05 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000104 | 2026-01-05 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 82.5 | 1031.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000105 | 2026-01-05 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19.5 | 82.5 | 1608.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000106 | 2026-01-05 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000107 | 2026-01-05 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 95 | 1662.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000108 | 2026-01-05 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 95 | 617.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000109 | 2026-01-05 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8 | 95 | 760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000110 | 2026-01-05 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000111 | 2026-01-05 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 60 | 1920 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000112 | 2026-01-05 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000113 | 2026-01-05 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 90 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000114 | 2026-01-05 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000115 | 2026-01-05 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 90 | 585 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000116 | 2026-01-05 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000117 | 2026-01-05 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 62.5 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000118 | 2026-01-05 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 62.5 | 531.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000119 | 2026-01-05 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 62.5 | 406.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000120 | 2026-01-05 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000121 | 2026-01-05 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13.5 | 62.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000122 | 2026-01-05 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9 | 62.5 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000123 | 2026-01-05 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000124 | 2026-01-05 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000125 | 2026-01-05 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000126 | 2026-01-05 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000127 | 2026-01-05 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000128 | 2026-01-05 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 28.5 | 72.5 | 2066.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000129 | 2026-01-05 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000130 | 2026-01-05 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000131 | 2026-01-05 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000132 | 2026-01-05 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000133 | 2026-01-05 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000134 | 2026-01-05 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000135 | 2026-01-05 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000136 | 2026-01-05 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 120 | 2100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000137 | 2026-01-05 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 120 | 1740 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000138 | 2026-01-05 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000139 | 2026-01-05 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22 | 100 | 2200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000140 | 2026-01-05 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000141 | 2026-01-05 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000142 | 2026-01-05 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 90 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000143 | 2026-01-05 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000144 | 2026-01-05 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 67.5 | 1012.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000145 | 2026-01-05 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 67.5 | 1147.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000146 | 2026-01-05 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000147 | 2026-01-05 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 75 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000148 | 2026-01-05 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000149 | 2026-01-05 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 75 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000150 | 2026-01-05 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000151 | 2026-01-05 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10 | 97.5 | 975 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000152 | 2026-01-05 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 22 | 97.5 | 2145 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000153 | 2026-01-05 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000154 | 2026-01-05 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 75 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000155 | 2026-01-05 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000156 | 2026-01-05 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9.5 | 67.5 | 641.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000157 | 2026-01-05 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 67.5 | 405 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000158 | 2026-01-05 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 67.5 | 1113.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000159 | 2026-01-05 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000160 | 2026-01-05 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 115 | 805 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000161 | 2026-01-05 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 25 | 115 | 2875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000162 | 2026-01-05 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000163 | 2026-01-05 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 87.5 | 2800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000164 | 2026-01-05 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000165 | 2026-01-05 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 90 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000166 | 2026-01-05 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10 | 90 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000167 | 2026-01-05 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 90 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000168 | 2026-01-05 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000169 | 2026-01-05 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14.5 | 60 | 870 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000170 | 2026-01-05 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 60 | 360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000171 | 2026-01-05 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 60 | 690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000172 | 2026-01-05 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000173 | 2026-01-12 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000174 | 2026-01-12 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000175 | 2026-01-12 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000176 | 2026-01-12 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000177 | 2026-01-12 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000178 | 2026-01-12 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 37.5 | 97.5 | 3656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000179 | 2026-01-12 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000180 | 2026-01-12 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000181 | 2026-01-12 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000182 | 2026-01-12 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000183 | 2026-01-12 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000184 | 2026-01-12 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 80 | 2840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000185 | 2026-01-12 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000186 | 2026-01-12 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000187 | 2026-01-12 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000188 | 2026-01-12 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000189 | 2026-01-12 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000190 | 2026-01-12 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 62.5 | 2156.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000191 | 2026-01-12 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000192 | 2026-01-12 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000193 | 2026-01-12 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000194 | 2026-01-12 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000195 | 2026-01-12 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000196 | 2026-01-12 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000197 | 2026-01-12 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 55 | 1952.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000198 | 2026-01-12 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000199 | 2026-01-12 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000200 | 2026-01-12 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000201 | 2026-01-12 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 187.5 | 6937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000202 | 2026-01-12 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000203 | 2026-01-12 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000204 | 2026-01-12 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000205 | 2026-01-12 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000206 | 2026-01-12 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000207 | 2026-01-12 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 157.5 | 5591.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000208 | 2026-01-12 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000209 | 2026-01-12 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000210 | 2026-01-12 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 162.5 | 5850 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000211 | 2026-01-12 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000212 | 2026-01-12 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000213 | 2026-01-12 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000214 | 2026-01-12 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 150 | 5325 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000215 | 2026-01-12 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000216 | 2026-01-12 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000217 | 2026-01-12 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000218 | 2026-01-12 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000219 | 2026-01-12 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000220 | 2026-01-12 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 105 | 3150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000221 | 2026-01-12 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19.5 | 85 | 1657.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000222 | 2026-01-12 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000223 | 2026-01-12 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14.5 | 85 | 1232.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000224 | 2026-01-12 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000225 | 2026-01-12 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19 | 82.5 | 1567.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000226 | 2026-01-12 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000227 | 2026-01-12 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21.5 | 67.5 | 1451.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000228 | 2026-01-12 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 22 | 67.5 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000229 | 2026-01-12 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 67.5 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000230 | 2026-01-12 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000231 | 2026-01-12 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000232 | 2026-01-12 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000233 | 2026-01-12 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000234 | 2026-01-12 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000235 | 2026-01-12 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24.5 | 55 | 1347.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000236 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000237 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000238 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000239 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000240 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000241 | 2026-01-12 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 65 | 1950 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000242 | 2026-01-12 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 120 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000243 | 2026-01-12 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 120 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000244 | 2026-01-12 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27.5 | 100 | 2750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000245 | 2026-01-12 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 100 | 1250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000246 | 2026-01-12 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 100 | 4000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000247 | 2026-01-12 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26.5 | 75 | 1987.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000248 | 2026-01-12 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 75 | 1012.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000249 | 2026-01-12 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000250 | 2026-01-12 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000251 | 2026-01-12 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 102.5 | 3023.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000252 | 2026-01-12 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000253 | 2026-01-12 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 102.5 | 307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000254 | 2026-01-12 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32.5 | 77.5 | 2518.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000255 | 2026-01-12 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 77.5 | 581.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000256 | 2026-01-12 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27.5 | 65 | 1787.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000257 | 2026-01-12 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000258 | 2026-01-12 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000259 | 2026-01-12 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000260 | 2026-01-12 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000261 | 2026-01-12 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000262 | 2026-01-12 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 82.5 | 1443.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000263 | 2026-01-12 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 82.5 | 1402.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000264 | 2026-01-12 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 82.5 | 288.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000265 | 2026-01-12 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000266 | 2026-01-12 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000267 | 2026-01-12 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 95 | 1140 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000268 | 2026-01-12 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 60 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000269 | 2026-01-12 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000270 | 2026-01-12 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000271 | 2026-01-12 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000272 | 2026-01-12 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 62.5 | 1343.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000273 | 2026-01-12 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 62.5 | 781.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000274 | 2026-01-12 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 62.5 | 375 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000275 | 2026-01-12 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14.5 | 62.5 | 906.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000276 | 2026-01-12 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000277 | 2026-01-12 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 62.5 | 906.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000278 | 2026-01-12 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 40 | 105 | 4200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000279 | 2026-01-12 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000280 | 2026-01-12 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 72.5 | 2573.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000281 | 2026-01-12 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000282 | 2026-01-12 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000283 | 2026-01-12 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000284 | 2026-01-12 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25 | 120 | 3000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000285 | 2026-01-12 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15 | 120 | 1800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000286 | 2026-01-12 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000287 | 2026-01-12 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 100 | 1200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000288 | 2026-01-12 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000289 | 2026-01-12 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000290 | 2026-01-12 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 67.5 | 1451.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000291 | 2026-01-12 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000292 | 2026-01-12 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000293 | 2026-01-12 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 97.5 | 2047.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000294 | 2026-01-12 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 97.5 | 1218.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000295 | 2026-01-12 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 97.5 | 633.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000296 | 2026-01-12 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000297 | 2026-01-12 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 75 | 787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000298 | 2026-01-12 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000299 | 2026-01-12 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000300 | 2026-01-12 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000301 | 2026-01-12 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 115 | 2357.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000302 | 2026-01-12 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000303 | 2026-01-12 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 115 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000304 | 2026-01-12 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000305 | 2026-01-12 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 87.5 | 1837.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000306 | 2026-01-12 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000307 | 2026-01-12 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000308 | 2026-01-12 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000309 | 2026-01-12 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000310 | 2026-01-12 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 60 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000311 | 2026-01-12 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 60 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000312 | 2026-01-12 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 60 | 780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000313 | 2026-01-19 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000314 | 2026-01-19 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000315 | 2026-01-19 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000316 | 2026-01-19 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000317 | 2026-01-19 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000318 | 2026-01-19 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 37.5 | 97.5 | 3656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000319 | 2026-01-19 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000320 | 2026-01-19 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000321 | 2026-01-19 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000322 | 2026-01-19 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000323 | 2026-01-19 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000324 | 2026-01-19 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 80 | 2840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000325 | 2026-01-19 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000326 | 2026-01-19 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000327 | 2026-01-19 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000328 | 2026-01-19 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000329 | 2026-01-19 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000330 | 2026-01-19 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 62.5 | 2125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000331 | 2026-01-19 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000332 | 2026-01-19 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000333 | 2026-01-19 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000334 | 2026-01-19 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000335 | 2026-01-19 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000336 | 2026-01-19 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000337 | 2026-01-19 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 55 | 1925 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000338 | 2026-01-19 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000339 | 2026-01-19 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000340 | 2026-01-19 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000341 | 2026-01-19 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 187.5 | 6187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000342 | 2026-01-19 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000343 | 2026-01-19 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000344 | 2026-01-19 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000345 | 2026-01-19 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000346 | 2026-01-19 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000347 | 2026-01-19 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35 | 157.5 | 5512.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000348 | 2026-01-19 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000349 | 2026-01-19 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000350 | 2026-01-19 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 162.5 | 5850 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000351 | 2026-01-19 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000352 | 2026-01-19 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000353 | 2026-01-19 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000354 | 2026-01-19 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 150 | 5325 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000355 | 2026-01-19 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000356 | 2026-01-19 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000357 | 2026-01-19 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000358 | 2026-01-19 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000359 | 2026-01-19 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000360 | 2026-01-19 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 105 | 3150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000361 | 2026-01-19 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000362 | 2026-01-19 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000363 | 2026-01-19 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 85 | 1530 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000364 | 2026-01-19 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21.5 | 82.5 | 1773.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000365 | 2026-01-19 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18.5 | 82.5 | 1526.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000366 | 2026-01-19 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 22 | 67.5 | 1485 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000367 | 2026-01-19 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 67.5 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000368 | 2026-01-19 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000369 | 2026-01-19 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000370 | 2026-01-19 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000371 | 2026-01-19 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000372 | 2026-01-19 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000373 | 2026-01-19 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000374 | 2026-01-19 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000375 | 2026-01-19 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24.5 | 55 | 1347.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000376 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000377 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000378 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000379 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000380 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000381 | 2026-01-19 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 65 | 1950 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000382 | 2026-01-19 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000383 | 2026-01-19 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15 | 120 | 1800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000384 | 2026-01-19 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26 | 100 | 2600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000385 | 2026-01-19 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 100 | 1400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000386 | 2026-01-19 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 100 | 4000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000387 | 2026-01-19 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000388 | 2026-01-19 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 75 | 1087.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000389 | 2026-01-19 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000390 | 2026-01-19 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000391 | 2026-01-19 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32 | 102.5 | 3280 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000392 | 2026-01-19 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000393 | 2026-01-19 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 77.5 | 2286.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000394 | 2026-01-19 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 77.5 | 813.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000395 | 2026-01-19 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000396 | 2026-01-19 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000397 | 2026-01-19 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000398 | 2026-01-19 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000399 | 2026-01-19 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000400 | 2026-01-19 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 117.5 | 117.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000401 | 2026-01-19 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14.5 | 82.5 | 1196.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000402 | 2026-01-19 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000403 | 2026-01-19 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 82.5 | 825 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000404 | 2026-01-19 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 95 | 1805 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000405 | 2026-01-19 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000406 | 2026-01-19 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 95 | 1282.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000407 | 2026-01-19 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 60 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000408 | 2026-01-19 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000409 | 2026-01-19 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000410 | 2026-01-19 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000411 | 2026-01-19 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000412 | 2026-01-19 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 62.5 | 718.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000413 | 2026-01-19 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 62.5 | 562.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000414 | 2026-01-19 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 62.5 | 937.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000415 | 2026-01-19 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 62.5 | 781.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000416 | 2026-01-19 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 62.5 | 781.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000417 | 2026-01-19 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 40 | 105 | 4200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000418 | 2026-01-19 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000419 | 2026-01-19 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 72.5 | 2610 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000420 | 2026-01-19 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000421 | 2026-01-19 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000422 | 2026-01-19 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000423 | 2026-01-19 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000424 | 2026-01-19 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 120 | 2040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000425 | 2026-01-19 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26.5 | 100 | 2650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000426 | 2026-01-19 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 100 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000427 | 2026-01-19 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000428 | 2026-01-19 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 67.5 | 1282.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000429 | 2026-01-19 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 67.5 | 1417.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000430 | 2026-01-19 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000431 | 2026-01-19 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000432 | 2026-01-19 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 97.5 | 1852.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000433 | 2026-01-19 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 97.5 | 1218.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000434 | 2026-01-19 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 97.5 | 828.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000435 | 2026-01-19 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000436 | 2026-01-19 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 75 | 637.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000437 | 2026-01-19 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 67.5 | 1451.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000438 | 2026-01-19 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000439 | 2026-01-19 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000440 | 2026-01-19 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000441 | 2026-01-19 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000442 | 2026-01-19 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 115 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000443 | 2026-01-19 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000444 | 2026-01-19 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20.5 | 87.5 | 1793.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000445 | 2026-01-19 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000446 | 2026-01-19 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000447 | 2026-01-19 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000448 | 2026-01-19 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000449 | 2026-01-19 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22 | 60 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000450 | 2026-01-19 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000451 | 2026-01-19 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 60 | 570 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000452 | 2026-01-26 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000453 | 2026-01-26 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000454 | 2026-01-26 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000455 | 2026-01-26 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000456 | 2026-01-26 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000457 | 2026-01-26 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 37.5 | 97.5 | 3656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000458 | 2026-01-26 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000459 | 2026-01-26 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000460 | 2026-01-26 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000461 | 2026-01-26 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000462 | 2026-01-26 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000463 | 2026-01-26 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 80 | 2800 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000464 | 2026-01-26 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000465 | 2026-01-26 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000466 | 2026-01-26 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000467 | 2026-01-26 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000468 | 2026-01-26 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000469 | 2026-01-26 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 62.5 | 2156.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000470 | 2026-01-26 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000471 | 2026-01-26 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000472 | 2026-01-26 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000473 | 2026-01-26 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000474 | 2026-01-26 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000475 | 2026-01-26 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000476 | 2026-01-26 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 55 | 1925 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000477 | 2026-01-26 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000478 | 2026-01-26 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000479 | 2026-01-26 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000480 | 2026-01-26 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 22.5 | 187.5 | 4218.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000481 | 2026-01-26 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000482 | 2026-01-26 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000483 | 2026-01-26 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000484 | 2026-01-26 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000485 | 2026-01-26 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000486 | 2026-01-26 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000487 | 2026-01-26 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35 | 157.5 | 5512.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000488 | 2026-01-26 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000489 | 2026-01-26 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000490 | 2026-01-26 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 162.5 | 5850 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000491 | 2026-01-26 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000492 | 2026-01-26 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000493 | 2026-01-26 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000494 | 2026-01-26 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 150 | 5325 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000495 | 2026-01-26 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000496 | 2026-01-26 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000497 | 2026-01-26 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000498 | 2026-01-26 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000499 | 2026-01-26 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000500 | 2026-01-26 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 105 | 3150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000501 | 2026-01-26 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000502 | 2026-01-26 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000503 | 2026-01-26 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 15 | 85 | 1275 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000504 | 2026-01-26 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000505 | 2026-01-26 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 82.5 | 1402.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000506 | 2026-01-26 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 21.5 | 67.5 | 1451.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000507 | 2026-01-26 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18.5 | 67.5 | 1248.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000508 | 2026-01-26 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000509 | 2026-01-26 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000510 | 2026-01-26 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000511 | 2026-01-26 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000512 | 2026-01-26 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000513 | 2026-01-26 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000514 | 2026-01-26 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000515 | 2026-01-26 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000516 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000517 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000518 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000519 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000520 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000521 | 2026-01-26 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 30 | 65 | 1950 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000522 | 2026-01-26 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 120 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000523 | 2026-01-26 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 120 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000524 | 2026-01-26 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30 | 100 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000525 | 2026-01-26 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000526 | 2026-01-26 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16 | 100 | 1600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000527 | 2026-01-26 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000528 | 2026-01-26 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26.5 | 75 | 1987.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000529 | 2026-01-26 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 75 | 1012.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000530 | 2026-01-26 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000531 | 2026-01-26 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000532 | 2026-01-26 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 31 | 102.5 | 3177.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000533 | 2026-01-26 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000534 | 2026-01-26 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000535 | 2026-01-26 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33 | 77.5 | 2557.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000536 | 2026-01-26 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 77.5 | 542.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000537 | 2026-01-26 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000538 | 2026-01-26 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000539 | 2026-01-26 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000540 | 2026-01-26 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000541 | 2026-01-26 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000542 | 2026-01-26 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14 | 82.5 | 1155 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000543 | 2026-01-26 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13.5 | 82.5 | 1113.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000544 | 2026-01-26 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 82.5 | 371.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000545 | 2026-01-26 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000546 | 2026-01-26 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000547 | 2026-01-26 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000548 | 2026-01-26 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 95 | 1187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000549 | 2026-01-26 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 60 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000550 | 2026-01-26 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000551 | 2026-01-26 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000552 | 2026-01-26 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000553 | 2026-01-26 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000554 | 2026-01-26 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000555 | 2026-01-26 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 62.5 | 406.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000556 | 2026-01-26 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 62.5 | 343.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000557 | 2026-01-26 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000558 | 2026-01-26 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 62.5 | 1062.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000559 | 2026-01-26 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000560 | 2026-01-26 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000561 | 2026-01-26 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 40 | 105 | 4200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000562 | 2026-01-26 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000563 | 2026-01-26 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 72.5 | 2573.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000564 | 2026-01-26 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 65 | 1040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000565 | 2026-01-26 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000566 | 2026-01-26 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000567 | 2026-01-26 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000568 | 2026-01-26 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14 | 120 | 1680 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000569 | 2026-01-26 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 120 | 1200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000570 | 2026-01-26 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000571 | 2026-01-26 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 100 | 2950 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000572 | 2026-01-26 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 100 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000573 | 2026-01-26 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000574 | 2026-01-26 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 67.5 | 1316.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000575 | 2026-01-26 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20.5 | 67.5 | 1383.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000576 | 2026-01-26 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000577 | 2026-01-26 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000578 | 2026-01-26 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000579 | 2026-01-26 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000580 | 2026-01-26 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 97.5 | 731.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000581 | 2026-01-26 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30.5 | 75 | 2287.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000582 | 2026-01-26 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 75 | 712.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000583 | 2026-01-26 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000584 | 2026-01-26 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 67.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000585 | 2026-01-26 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000586 | 2026-01-26 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 115 | 2472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000587 | 2026-01-26 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000588 | 2026-01-26 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 115 | 1207.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000589 | 2026-01-26 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000590 | 2026-01-26 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 87.5 | 1837.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000591 | 2026-01-26 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000592 | 2026-01-26 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000593 | 2026-01-26 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000594 | 2026-01-26 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 60 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000595 | 2026-01-26 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000596 | 2026-01-26 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 60 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000597 | 2026-02-02 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000598 | 2026-02-02 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000599 | 2026-02-02 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000600 | 2026-02-02 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000601 | 2026-02-02 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000602 | 2026-02-02 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000603 | 2026-02-02 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000604 | 2026-02-02 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000605 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000606 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000607 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000608 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000609 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000610 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000611 | 2026-02-02 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000612 | 2026-02-02 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 80 | 2640 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000613 | 2026-02-02 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000614 | 2026-02-02 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000615 | 2026-02-02 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000616 | 2026-02-02 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000617 | 2026-02-02 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000618 | 2026-02-02 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000619 | 2026-02-02 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000620 | 2026-02-02 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 62.5 | 2000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000621 | 2026-02-02 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000622 | 2026-02-02 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000623 | 2026-02-02 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000624 | 2026-02-02 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000625 | 2026-02-02 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000626 | 2026-02-02 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000627 | 2026-02-02 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000628 | 2026-02-02 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000629 | 2026-02-02 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 55 | 1842.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000630 | 2026-02-02 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000631 | 2026-02-02 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000632 | 2026-02-02 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000633 | 2026-02-02 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000634 | 2026-02-02 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000635 | 2026-02-02 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000636 | 2026-02-02 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000637 | 2026-02-02 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000638 | 2026-02-02 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000639 | 2026-02-02 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000640 | 2026-02-02 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000641 | 2026-02-02 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000642 | 2026-02-02 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34.5 | 157.5 | 5433.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000643 | 2026-02-02 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000644 | 2026-02-02 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000645 | 2026-02-02 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000646 | 2026-02-02 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 162.5 | 5525 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000647 | 2026-02-02 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000648 | 2026-02-02 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000649 | 2026-02-02 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000650 | 2026-02-02 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000651 | 2026-02-02 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 150 | 4800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000652 | 2026-02-02 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000653 | 2026-02-02 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000654 | 2026-02-02 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000655 | 2026-02-02 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000656 | 2026-02-02 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000657 | 2026-02-02 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000658 | 2026-02-02 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000659 | 2026-02-02 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000660 | 2026-02-02 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000661 | 2026-02-02 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 14.5 | 85 | 1232.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000662 | 2026-02-02 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000663 | 2026-02-02 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 85 | 85 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000664 | 2026-02-02 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20.5 | 82.5 | 1691.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000665 | 2026-02-02 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19.5 | 82.5 | 1608.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000666 | 2026-02-02 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000667 | 2026-02-02 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000668 | 2026-02-02 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000669 | 2026-02-02 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 11.5 | 67.5 | 776.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000670 | 2026-02-02 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000671 | 2026-02-02 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000672 | 2026-02-02 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000673 | 2026-02-02 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000674 | 2026-02-02 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000675 | 2026-02-02 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000676 | 2026-02-02 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000677 | 2026-02-02 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000678 | 2026-02-02 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6.5 | 55 | 357.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000679 | 2026-02-02 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000680 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000681 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000682 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000683 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000684 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000685 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000686 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000687 | 2026-02-02 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000688 | 2026-02-02 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000689 | 2026-02-02 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 120 | 1560 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000690 | 2026-02-02 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000691 | 2026-02-02 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27 | 100 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000692 | 2026-02-02 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000693 | 2026-02-02 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 100 | 500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000694 | 2026-02-02 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26 | 100 | 2600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000695 | 2026-02-02 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 100 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000696 | 2026-02-02 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000697 | 2026-02-02 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28.5 | 75 | 2137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000698 | 2026-02-02 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000699 | 2026-02-02 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 34.5 | 67.5 | 2328.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000700 | 2026-02-02 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 67.5 | 371.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000701 | 2026-02-02 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000702 | 2026-02-02 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32 | 102.5 | 3280 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000703 | 2026-02-02 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000704 | 2026-02-02 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 77.5 | 2286.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000705 | 2026-02-02 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000706 | 2026-02-02 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 77.5 | 232.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000707 | 2026-02-02 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000708 | 2026-02-02 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000709 | 2026-02-02 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000710 | 2026-02-02 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000711 | 2026-02-02 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000712 | 2026-02-02 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 82.5 | 1278.75 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000713 | 2026-02-02 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 82.5 | 1237.5 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000714 | 2026-02-02 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 82.5 | 660 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000715 | 2026-02-02 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 95 | 2042.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000716 | 2026-02-02 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10.5 | 95 | 997.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000717 | 2026-02-02 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 95 | 760 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000718 | 2026-02-02 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16.5 | 60 | 990 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000719 | 2026-02-02 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 23.5 | 60 | 1410 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000720 | 2026-02-02 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000721 | 2026-02-02 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000722 | 2026-02-02 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000723 | 2026-02-02 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000724 | 2026-02-02 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 62.5 | 1343.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000725 | 2026-02-02 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000726 | 2026-02-02 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 62.5 | 468.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000727 | 2026-02-02 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000728 | 2026-02-02 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000729 | 2026-02-02 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000730 | 2026-02-02 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000731 | 2026-02-02 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000732 | 2026-02-02 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 72.5 | 181.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000733 | 2026-02-02 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 21.5 | 72.5 | 1558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000734 | 2026-02-02 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000735 | 2026-02-02 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000736 | 2026-02-02 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000737 | 2026-02-02 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000738 | 2026-02-02 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 24.5 | 120 | 2940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000739 | 2026-02-02 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15.5 | 120 | 1860 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000740 | 2026-02-02 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29 | 100 | 2900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000741 | 2026-02-02 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 100 | 1100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000742 | 2026-02-02 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000743 | 2026-02-02 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000744 | 2026-02-02 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000745 | 2026-02-02 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000746 | 2026-02-02 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000747 | 2026-02-02 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000748 | 2026-02-02 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000749 | 2026-02-02 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 97.5 | 828.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000750 | 2026-02-02 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000751 | 2026-02-02 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000752 | 2026-02-02 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000753 | 2026-02-02 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000754 | 2026-02-02 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000755 | 2026-02-02 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18 | 115 | 2070 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000756 | 2026-02-02 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000757 | 2026-02-02 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000758 | 2026-02-02 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 115 | 172.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000759 | 2026-02-02 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 87.5 | 1837.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000760 | 2026-02-02 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000761 | 2026-02-02 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000762 | 2026-02-02 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000763 | 2026-02-02 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000764 | 2026-02-02 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000765 | 2026-02-02 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 60 | 1110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000766 | 2026-02-02 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000767 | 2026-02-02 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 60 | 780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000768 | 2026-02-09 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000769 | 2026-02-09 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000770 | 2026-02-09 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23 | 97.5 | 2242.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000771 | 2026-02-09 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000772 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000773 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000774 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000775 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000776 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000777 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000778 | 2026-02-09 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000779 | 2026-02-09 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 80 | 2680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000780 | 2026-02-09 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000781 | 2026-02-09 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000782 | 2026-02-09 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000783 | 2026-02-09 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000784 | 2026-02-09 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000785 | 2026-02-09 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000786 | 2026-02-09 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000787 | 2026-02-09 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 18.5 | 62.5 | 1156.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000788 | 2026-02-09 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000789 | 2026-02-09 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000790 | 2026-02-09 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000791 | 2026-02-09 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000792 | 2026-02-09 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000793 | 2026-02-09 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000794 | 2026-02-09 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000795 | 2026-02-09 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000796 | 2026-02-09 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000797 | 2026-02-09 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 55 | 1842.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000798 | 2026-02-09 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000799 | 2026-02-09 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000800 | 2026-02-09 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000801 | 2026-02-09 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000802 | 2026-02-09 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000803 | 2026-02-09 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000804 | 2026-02-09 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000805 | 2026-02-09 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000806 | 2026-02-09 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000807 | 2026-02-09 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000808 | 2026-02-09 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000809 | 2026-02-09 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000810 | 2026-02-09 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000811 | 2026-02-09 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000812 | 2026-02-09 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000813 | 2026-02-09 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000814 | 2026-02-09 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 162.5 | 5525 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000815 | 2026-02-09 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000816 | 2026-02-09 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000817 | 2026-02-09 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000818 | 2026-02-09 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000819 | 2026-02-09 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000820 | 2026-02-09 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000821 | 2026-02-09 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000822 | 2026-02-09 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000823 | 2026-02-09 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000824 | 2026-02-09 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000825 | 2026-02-09 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000826 | 2026-02-09 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000827 | 2026-02-09 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000828 | 2026-02-09 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000829 | 2026-02-09 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000830 | 2026-02-09 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000831 | 2026-02-09 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 85 | 212.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000832 | 2026-02-09 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000833 | 2026-02-09 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17.5 | 82.5 | 1443.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000834 | 2026-02-09 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000835 | 2026-02-09 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000836 | 2026-02-09 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000837 | 2026-02-09 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000838 | 2026-02-09 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000839 | 2026-02-09 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19 | 67.5 | 1282.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000840 | 2026-02-09 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000841 | 2026-02-09 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000842 | 2026-02-09 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000843 | 2026-02-09 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000844 | 2026-02-09 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000845 | 2026-02-09 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000846 | 2026-02-09 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000847 | 2026-02-09 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17.5 | 55 | 962.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000848 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000849 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000850 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000851 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000852 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000853 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000854 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000855 | 2026-02-09 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000856 | 2026-02-09 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000857 | 2026-02-09 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000858 | 2026-02-09 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 120 | 840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000859 | 2026-02-09 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27.5 | 100 | 2750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000860 | 2026-02-09 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000861 | 2026-02-09 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 100 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000862 | 2026-02-09 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33.5 | 100 | 3350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000863 | 2026-02-09 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 100 | 650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000864 | 2026-02-09 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27.5 | 75 | 2062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000865 | 2026-02-09 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 75 | 937.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000866 | 2026-02-09 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000867 | 2026-02-09 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 67.5 | 506.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000868 | 2026-02-09 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000869 | 2026-02-09 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 30 | 102.5 | 3075 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000870 | 2026-02-09 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 102.5 | 871.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000871 | 2026-02-09 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000872 | 2026-02-09 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 32.5 | 77.5 | 2518.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000873 | 2026-02-09 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000874 | 2026-02-09 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000875 | 2026-02-09 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000876 | 2026-02-09 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000877 | 2026-02-09 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000878 | 2026-02-09 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000879 | 2026-02-09 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000880 | 2026-02-09 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000881 | 2026-02-09 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000882 | 2026-02-09 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 95 | 1995 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000883 | 2026-02-09 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000884 | 2026-02-09 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000885 | 2026-02-09 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 60 | 1050 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000886 | 2026-02-09 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 22.5 | 60 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000887 | 2026-02-09 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000888 | 2026-02-09 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000889 | 2026-02-09 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000890 | 2026-02-09 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 62.5 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000891 | 2026-02-09 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 62.5 | 718.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000892 | 2026-02-09 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 62.5 | 593.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000893 | 2026-02-09 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9.5 | 62.5 | 593.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000894 | 2026-02-09 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 62.5 | 406.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000895 | 2026-02-09 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8 | 62.5 | 500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000896 | 2026-02-09 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000897 | 2026-02-09 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000898 | 2026-02-09 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36.5 | 105 | 3832.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000899 | 2026-02-09 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000900 | 2026-02-09 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 72.5 | 2610 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000901 | 2026-02-09 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000902 | 2026-02-09 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000903 | 2026-02-09 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 55 | 880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000904 | 2026-02-09 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000905 | 2026-02-09 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000906 | 2026-02-09 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000907 | 2026-02-09 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 120 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000908 | 2026-02-09 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30 | 100 | 3000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000909 | 2026-02-09 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000910 | 2026-02-09 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000911 | 2026-02-09 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 67.5 | 1417.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000912 | 2026-02-09 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 67.5 | 1282.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000913 | 2026-02-09 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000914 | 2026-02-09 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000915 | 2026-02-09 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000916 | 2026-02-09 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000917 | 2026-02-09 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 97.5 | 731.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000918 | 2026-02-09 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000919 | 2026-02-09 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000920 | 2026-02-09 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000921 | 2026-02-09 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000922 | 2026-02-09 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000923 | 2026-02-09 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000924 | 2026-02-09 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000925 | 2026-02-09 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000926 | 2026-02-09 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000927 | 2026-02-09 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 87.5 | 1793.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000928 | 2026-02-09 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000929 | 2026-02-09 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000930 | 2026-02-09 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000931 | 2026-02-09 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000932 | 2026-02-09 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000933 | 2026-02-09 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 60 | 1260 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000934 | 2026-02-09 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000935 | 2026-02-09 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 60 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000936 | 2026-02-16 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000937 | 2026-02-16 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000938 | 2026-02-16 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000939 | 2026-02-16 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000940 | 2026-02-16 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000941 | 2026-02-16 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000942 | 2026-02-16 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000943 | 2026-02-16 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000944 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000945 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000946 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000947 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000948 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000949 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000950 | 2026-02-16 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000951 | 2026-02-16 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 80 | 2680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000952 | 2026-02-16 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000953 | 2026-02-16 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000954 | 2026-02-16 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000955 | 2026-02-16 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000956 | 2026-02-16 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000957 | 2026-02-16 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000958 | 2026-02-16 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000959 | 2026-02-16 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 62.5 | 1968.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000960 | 2026-02-16 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000961 | 2026-02-16 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000962 | 2026-02-16 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000963 | 2026-02-16 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000964 | 2026-02-16 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000965 | 2026-02-16 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000966 | 2026-02-16 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000967 | 2026-02-16 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000968 | 2026-02-16 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 55 | 1842.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000969 | 2026-02-16 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000970 | 2026-02-16 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000971 | 2026-02-16 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000972 | 2026-02-16 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000973 | 2026-02-16 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000974 | 2026-02-16 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000975 | 2026-02-16 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000976 | 2026-02-16 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000977 | 2026-02-16 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000978 | 2026-02-16 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000979 | 2026-02-16 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000980 | 2026-02-16 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000981 | 2026-02-16 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000982 | 2026-02-16 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000983 | 2026-02-16 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000984 | 2026-02-16 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000985 | 2026-02-16 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 162.5 | 5525 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000986 | 2026-02-16 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000987 | 2026-02-16 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000988 | 2026-02-16 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000989 | 2026-02-16 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000990 | 2026-02-16 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000991 | 2026-02-16 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000992 | 2026-02-16 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000993 | 2026-02-16 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000994 | 2026-02-16 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000995 | 2026-02-16 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000996 | 2026-02-16 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000997 | 2026-02-16 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000998 | 2026-02-16 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-000999 | 2026-02-16 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001000 | 2026-02-16 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001001 | 2026-02-16 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001002 | 2026-02-16 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20.5 | 82.5 | 1691.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001003 | 2026-02-16 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21.5 | 82.5 | 1773.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001004 | 2026-02-16 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001005 | 2026-02-16 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001006 | 2026-02-16 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001007 | 2026-02-16 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001008 | 2026-02-16 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20.5 | 67.5 | 1383.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001009 | 2026-02-16 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001010 | 2026-02-16 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001011 | 2026-02-16 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001012 | 2026-02-16 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001013 | 2026-02-16 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001014 | 2026-02-16 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001015 | 2026-02-16 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001016 | 2026-02-16 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16.5 | 55 | 907.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001017 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001018 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001019 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001020 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001021 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001022 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001023 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001024 | 2026-02-16 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001025 | 2026-02-16 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 24.5 | 120 | 2940 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001026 | 2026-02-16 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001027 | 2026-02-16 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001028 | 2026-02-16 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27 | 100 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001029 | 2026-02-16 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001030 | 2026-02-16 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 100 | 550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001031 | 2026-02-16 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33 | 100 | 3300 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001032 | 2026-02-16 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 100 | 700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001033 | 2026-02-16 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23.5 | 75 | 1762.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001034 | 2026-02-16 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 75 | 637.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001035 | 2026-02-16 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001036 | 2026-02-16 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33 | 67.5 | 2227.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001037 | 2026-02-16 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 67.5 | 472.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001038 | 2026-02-16 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001039 | 2026-02-16 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001040 | 2026-02-16 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 102.5 | 3177.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001041 | 2026-02-16 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001042 | 2026-02-16 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001043 | 2026-02-16 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 32.5 | 77.5 | 2518.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001044 | 2026-02-16 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001045 | 2026-02-16 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001046 | 2026-02-16 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001047 | 2026-02-16 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001048 | 2026-02-16 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001049 | 2026-02-16 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001050 | 2026-02-16 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001051 | 2026-02-16 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001052 | 2026-02-16 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 82.5 | 701.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001053 | 2026-02-16 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 95 | 1757.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001054 | 2026-02-16 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 95 | 1235 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001055 | 2026-02-16 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001056 | 2026-02-16 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001057 | 2026-02-16 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 14.5 | 60 | 870 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001058 | 2026-02-16 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 25.5 | 60 | 1530 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001059 | 2026-02-16 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001060 | 2026-02-16 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001061 | 2026-02-16 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001062 | 2026-02-16 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001063 | 2026-02-16 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 62.5 | 812.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001064 | 2026-02-16 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 62.5 | 468.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001065 | 2026-02-16 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001066 | 2026-02-16 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001067 | 2026-02-16 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001068 | 2026-02-16 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001069 | 2026-02-16 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001070 | 2026-02-16 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001071 | 2026-02-16 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 72.5 | 2573.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001072 | 2026-02-16 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001073 | 2026-02-16 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001074 | 2026-02-16 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001075 | 2026-02-16 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 26 | 120 | 3120 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001076 | 2026-02-16 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 120 | 1680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001077 | 2026-02-16 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30 | 100 | 3000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001078 | 2026-02-16 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001079 | 2026-02-16 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001080 | 2026-02-16 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001081 | 2026-02-16 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 67.5 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001082 | 2026-02-16 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001083 | 2026-02-16 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001084 | 2026-02-16 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 38 | 75 | 2850 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001085 | 2026-02-16 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 97.5 | 1901.25 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001086 | 2026-02-16 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 97.5 | 1121.25 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001087 | 2026-02-16 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 97.5 | 97.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001088 | 2026-02-16 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001089 | 2026-02-16 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001090 | 2026-02-16 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001091 | 2026-02-16 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001092 | 2026-02-16 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001093 | 2026-02-16 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001094 | 2026-02-16 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 115 | 2127.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001095 | 2026-02-16 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 115 | 1437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001096 | 2026-02-16 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001097 | 2026-02-16 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001098 | 2026-02-16 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 87.5 | 1837.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001099 | 2026-02-16 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001100 | 2026-02-16 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001101 | 2026-02-16 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001102 | 2026-02-16 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001103 | 2026-02-16 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001104 | 2026-02-16 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001105 | 2026-02-16 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 60 | 1260 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001106 | 2026-02-16 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001107 | 2026-02-16 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 60 | 630 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001108 | 2026-02-23 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 97.5 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001109 | 2026-02-23 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001110 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001111 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001112 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001113 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001114 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001115 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001116 | 2026-02-23 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001117 | 2026-02-23 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 80 | 2760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001118 | 2026-02-23 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001119 | 2026-02-23 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001120 | 2026-02-23 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001121 | 2026-02-23 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001122 | 2026-02-23 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001123 | 2026-02-23 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001124 | 2026-02-23 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001125 | 2026-02-23 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 62.5 | 2000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001126 | 2026-02-23 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 57.5 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001127 | 2026-02-23 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001128 | 2026-02-23 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001129 | 2026-02-23 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001130 | 2026-02-23 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001131 | 2026-02-23 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001132 | 2026-02-23 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001133 | 2026-02-23 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001134 | 2026-02-23 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001135 | 2026-02-23 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 55 | 1870 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001136 | 2026-02-23 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001137 | 2026-02-23 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001138 | 2026-02-23 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001139 | 2026-02-23 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001140 | 2026-02-23 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001141 | 2026-02-23 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001142 | 2026-02-23 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001143 | 2026-02-23 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001144 | 2026-02-23 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001145 | 2026-02-23 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001146 | 2026-02-23 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001147 | 2026-02-23 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001148 | 2026-02-23 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001149 | 2026-02-23 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001150 | 2026-02-23 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001151 | 2026-02-23 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001152 | 2026-02-23 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 162.5 | 5525 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001153 | 2026-02-23 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001154 | 2026-02-23 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001155 | 2026-02-23 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001156 | 2026-02-23 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001157 | 2026-02-23 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001158 | 2026-02-23 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001159 | 2026-02-23 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001160 | 2026-02-23 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001161 | 2026-02-23 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001162 | 2026-02-23 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001163 | 2026-02-23 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001164 | 2026-02-23 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001165 | 2026-02-23 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 15.5 | 105 | 1627.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001166 | 2026-02-23 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001167 | 2026-02-23 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001168 | 2026-02-23 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001169 | 2026-02-23 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001170 | 2026-02-23 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21.5 | 82.5 | 1773.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001171 | 2026-02-23 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18.5 | 82.5 | 1526.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001172 | 2026-02-23 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001173 | 2026-02-23 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001174 | 2026-02-23 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001175 | 2026-02-23 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001176 | 2026-02-23 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001177 | 2026-02-23 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001178 | 2026-02-23 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001179 | 2026-02-23 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001180 | 2026-02-23 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001181 | 2026-02-23 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001182 | 2026-02-23 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001183 | 2026-02-23 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 55 | 990 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001184 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001185 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001186 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001187 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001188 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001189 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001190 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001191 | 2026-02-23 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001192 | 2026-02-23 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001193 | 2026-02-23 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001194 | 2026-02-23 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 120 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001195 | 2026-02-23 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 17 | 100 | 1700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001196 | 2026-02-23 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001197 | 2026-02-23 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 100 | 200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001198 | 2026-02-23 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001199 | 2026-02-23 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33.5 | 100 | 3350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001200 | 2026-02-23 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 100 | 650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001201 | 2026-02-23 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 27 | 75 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001202 | 2026-02-23 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001203 | 2026-02-23 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001204 | 2026-02-23 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30.5 | 67.5 | 2058.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001205 | 2026-02-23 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 67.5 | 641.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001206 | 2026-02-23 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001207 | 2026-02-23 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 30 | 102.5 | 3075 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001208 | 2026-02-23 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001209 | 2026-02-23 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 102.5 | 205 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001210 | 2026-02-23 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 32 | 77.5 | 2480 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001211 | 2026-02-23 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 77.5 | 620 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001212 | 2026-02-23 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 27.5 | 65 | 1787.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001213 | 2026-02-23 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001214 | 2026-02-23 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001215 | 2026-02-23 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001216 | 2026-02-23 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001217 | 2026-02-23 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 117.5 | 235 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001218 | 2026-02-23 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001219 | 2026-02-23 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001220 | 2026-02-23 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001221 | 2026-02-23 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001222 | 2026-02-23 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001223 | 2026-02-23 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001224 | 2026-02-23 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001225 | 2026-02-23 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17 | 60 | 1020 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001226 | 2026-02-23 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 23 | 60 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001227 | 2026-02-23 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001228 | 2026-02-23 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001229 | 2026-02-23 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001230 | 2026-02-23 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001231 | 2026-02-23 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001232 | 2026-02-23 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001233 | 2026-02-23 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 62.5 | 312.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001234 | 2026-02-23 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001235 | 2026-02-23 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001236 | 2026-02-23 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001237 | 2026-02-23 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 62.5 | 1062.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001238 | 2026-02-23 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001239 | 2026-02-23 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001240 | 2026-02-23 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 72.5 | 108.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001241 | 2026-02-23 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 14.5 | 72.5 | 1051.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001242 | 2026-02-23 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001243 | 2026-02-23 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001244 | 2026-02-23 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001245 | 2026-02-23 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001246 | 2026-02-23 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 26.5 | 120 | 3180 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001247 | 2026-02-23 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 120 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001248 | 2026-02-23 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 29.5 | 100 | 2950 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001249 | 2026-02-23 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 100 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001250 | 2026-02-23 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 90 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001251 | 2026-02-23 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001252 | 2026-02-23 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001253 | 2026-02-23 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 67.5 | 843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001254 | 2026-02-23 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001255 | 2026-02-23 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001256 | 2026-02-23 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 75 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001257 | 2026-02-23 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001258 | 2026-02-23 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 97.5 | 633.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001259 | 2026-02-23 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 97.5 | 536.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001260 | 2026-02-23 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001261 | 2026-02-23 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001262 | 2026-02-23 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001263 | 2026-02-23 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 75 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001264 | 2026-02-23 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001265 | 2026-02-23 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001266 | 2026-02-23 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001267 | 2026-02-23 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001268 | 2026-02-23 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001269 | 2026-02-23 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001270 | 2026-02-23 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 115 | 517.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001271 | 2026-02-23 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001272 | 2026-02-23 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001273 | 2026-02-23 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001274 | 2026-02-23 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001275 | 2026-02-23 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 87.5 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001276 | 2026-02-23 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001277 | 2026-02-23 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001278 | 2026-02-23 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001279 | 2026-02-23 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 60 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001280 | 2026-02-23 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 9 | 60 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001281 | 2026-02-23 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 60 | 720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001282 | 2026-03-02 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001283 | 2026-03-02 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001284 | 2026-03-02 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23 | 97.5 | 2242.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001285 | 2026-03-02 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001286 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001287 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001288 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001289 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001290 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001291 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001292 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001293 | 2026-03-02 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001294 | 2026-03-02 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 80 | 2640 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001295 | 2026-03-02 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001296 | 2026-03-02 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001297 | 2026-03-02 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001298 | 2026-03-02 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001299 | 2026-03-02 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001300 | 2026-03-02 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001301 | 2026-03-02 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001302 | 2026-03-02 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001303 | 2026-03-02 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 12 | 62.5 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001304 | 2026-03-02 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001305 | 2026-03-02 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001306 | 2026-03-02 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001307 | 2026-03-02 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001308 | 2026-03-02 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001309 | 2026-03-02 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001310 | 2026-03-02 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001311 | 2026-03-02 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001312 | 2026-03-02 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001313 | 2026-03-02 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001314 | 2026-03-02 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 55 | 1815 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001315 | 2026-03-02 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001316 | 2026-03-02 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001317 | 2026-03-02 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001318 | 2026-03-02 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001319 | 2026-03-02 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001320 | 2026-03-02 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001321 | 2026-03-02 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001322 | 2026-03-02 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001323 | 2026-03-02 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001324 | 2026-03-02 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001325 | 2026-03-02 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001326 | 2026-03-02 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001327 | 2026-03-02 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001328 | 2026-03-02 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 157.5 | 5118.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001329 | 2026-03-02 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 162.5 | 81.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001330 | 2026-03-02 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001331 | 2026-03-02 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001332 | 2026-03-02 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001333 | 2026-03-02 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 12.5 | 162.5 | 2031.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001334 | 2026-03-02 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001335 | 2026-03-02 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001336 | 2026-03-02 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001337 | 2026-03-02 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001338 | 2026-03-02 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001339 | 2026-03-02 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001340 | 2026-03-02 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001341 | 2026-03-02 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001342 | 2026-03-02 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001343 | 2026-03-02 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001344 | 2026-03-02 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001345 | 2026-03-02 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001346 | 2026-03-02 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001347 | 2026-03-02 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001348 | 2026-03-02 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001349 | 2026-03-02 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001350 | 2026-03-02 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 14.5 | 85 | 1232.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001351 | 2026-03-02 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001352 | 2026-03-02 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 85 | 127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001353 | 2026-03-02 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001354 | 2026-03-02 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001355 | 2026-03-02 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 82.5 | 206.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001356 | 2026-03-02 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001357 | 2026-03-02 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001358 | 2026-03-02 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 22 | 67.5 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001359 | 2026-03-02 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 67.5 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001360 | 2026-03-02 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001361 | 2026-03-02 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001362 | 2026-03-02 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001363 | 2026-03-02 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001364 | 2026-03-02 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001365 | 2026-03-02 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001366 | 2026-03-02 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001367 | 2026-03-02 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001368 | 2026-03-02 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 15 | 55 | 825 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001369 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001370 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001371 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001372 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001373 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001374 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001375 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001376 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001377 | 2026-03-02 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001378 | 2026-03-02 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 24 | 120 | 2880 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001379 | 2026-03-02 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 120 | 1500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001380 | 2026-03-02 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001381 | 2026-03-02 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001382 | 2026-03-02 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001383 | 2026-03-02 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001384 | 2026-03-02 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 32.5 | 100 | 3250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001385 | 2026-03-02 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 100 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001386 | 2026-03-02 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 28.5 | 75 | 2137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001387 | 2026-03-02 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001388 | 2026-03-02 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001389 | 2026-03-02 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 30.5 | 67.5 | 2058.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001390 | 2026-03-02 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 67.5 | 641.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001391 | 2026-03-02 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 17.5 | 67.5 | 1181.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001392 | 2026-03-02 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 67.5 | 438.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001393 | 2026-03-02 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001394 | 2026-03-02 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 33 | 102.5 | 3382.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001395 | 2026-03-02 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 102.5 | 717.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001396 | 2026-03-02 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 33 | 77.5 | 2557.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001397 | 2026-03-02 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 77.5 | 542.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001398 | 2026-03-02 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001399 | 2026-03-02 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001400 | 2026-03-02 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001401 | 2026-03-02 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001402 | 2026-03-02 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001403 | 2026-03-02 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001404 | 2026-03-02 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001405 | 2026-03-02 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001406 | 2026-03-02 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001407 | 2026-03-02 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001408 | 2026-03-02 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001409 | 2026-03-02 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 5 | 95 | 475 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001410 | 2026-03-02 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 95 | 285 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001411 | 2026-03-02 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001412 | 2026-03-02 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 60 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001413 | 2026-03-02 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001414 | 2026-03-02 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001415 | 2026-03-02 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001416 | 2026-03-02 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001417 | 2026-03-02 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001418 | 2026-03-02 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001419 | 2026-03-02 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001420 | 2026-03-02 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 62.5 | 812.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001421 | 2026-03-02 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001422 | 2026-03-02 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 17 | 62.5 | 1062.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001423 | 2026-03-02 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001424 | 2026-03-02 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001425 | 2026-03-02 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001426 | 2026-03-02 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001427 | 2026-03-02 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001428 | 2026-03-02 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36.5 | 72.5 | 2646.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001429 | 2026-03-02 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001430 | 2026-03-02 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001431 | 2026-03-02 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001432 | 2026-03-02 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001433 | 2026-03-02 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001434 | 2026-03-02 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 120 | 1500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001435 | 2026-03-02 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 100 | 3100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001436 | 2026-03-02 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 100 | 900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001437 | 2026-03-02 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001438 | 2026-03-02 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 21.5 | 67.5 | 1451.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001439 | 2026-03-02 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001440 | 2026-03-02 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 67.5 | 438.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001441 | 2026-03-02 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 75 | 1575 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001442 | 2026-03-02 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 75 | 1425 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001443 | 2026-03-02 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23.5 | 75 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001444 | 2026-03-02 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 75 | 1237.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001445 | 2026-03-02 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001446 | 2026-03-02 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001447 | 2026-03-02 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 97.5 | 1218.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001448 | 2026-03-02 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001449 | 2026-03-02 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001450 | 2026-03-02 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001451 | 2026-03-02 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 67.5 | 303.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001452 | 2026-03-02 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 67.5 | 202.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001453 | 2026-03-02 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001454 | 2026-03-02 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001455 | 2026-03-02 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001456 | 2026-03-02 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001457 | 2026-03-02 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001458 | 2026-03-02 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 115 | 632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001459 | 2026-03-02 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001460 | 2026-03-02 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001461 | 2026-03-02 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001462 | 2026-03-02 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001463 | 2026-03-02 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001464 | 2026-03-02 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001465 | 2026-03-02 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 60 | 1110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001466 | 2026-03-02 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001467 | 2026-03-02 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 60 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001468 | 2026-03-09 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001469 | 2026-03-09 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001470 | 2026-03-09 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001471 | 2026-03-09 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001472 | 2026-03-09 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001473 | 2026-03-09 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001474 | 2026-03-09 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001475 | 2026-03-09 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001476 | 2026-03-09 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001477 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001478 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001479 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001480 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001481 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001482 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001483 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001484 | 2026-03-09 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001485 | 2026-03-09 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 80 | 2560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001486 | 2026-03-09 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001487 | 2026-03-09 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001488 | 2026-03-09 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001489 | 2026-03-09 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001490 | 2026-03-09 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001491 | 2026-03-09 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001492 | 2026-03-09 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001493 | 2026-03-09 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001494 | 2026-03-09 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 62.5 | 1937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001495 | 2026-03-09 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001496 | 2026-03-09 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001497 | 2026-03-09 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001498 | 2026-03-09 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001499 | 2026-03-09 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001500 | 2026-03-09 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001501 | 2026-03-09 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001502 | 2026-03-09 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001503 | 2026-03-09 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001504 | 2026-03-09 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 55 | 1815 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001505 | 2026-03-09 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001506 | 2026-03-09 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001507 | 2026-03-09 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001508 | 2026-03-09 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001509 | 2026-03-09 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001510 | 2026-03-09 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001511 | 2026-03-09 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001512 | 2026-03-09 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001513 | 2026-03-09 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001514 | 2026-03-09 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001515 | 2026-03-09 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001516 | 2026-03-09 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001517 | 2026-03-09 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001518 | 2026-03-09 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 12 | 157.5 | 1890 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001519 | 2026-03-09 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001520 | 2026-03-09 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001521 | 2026-03-09 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001522 | 2026-03-09 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001523 | 2026-03-09 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001524 | 2026-03-09 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 162.5 | 5200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001525 | 2026-03-09 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001526 | 2026-03-09 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001527 | 2026-03-09 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001528 | 2026-03-09 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001529 | 2026-03-09 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001530 | 2026-03-09 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001531 | 2026-03-09 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001532 | 2026-03-09 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001533 | 2026-03-09 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001534 | 2026-03-09 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001535 | 2026-03-09 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001536 | 2026-03-09 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001537 | 2026-03-09 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001538 | 2026-03-09 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001539 | 2026-03-09 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 85 | 935 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001540 | 2026-03-09 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 9 | 85 | 765 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001541 | 2026-03-09 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4 | 85 | 340 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001542 | 2026-03-09 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001543 | 2026-03-09 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23.5 | 82.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001544 | 2026-03-09 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001545 | 2026-03-09 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 7 | 67.5 | 472.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001546 | 2026-03-09 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001547 | 2026-03-09 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001548 | 2026-03-09 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001549 | 2026-03-09 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001550 | 2026-03-09 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001551 | 2026-03-09 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001552 | 2026-03-09 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001553 | 2026-03-09 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001554 | 2026-03-09 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001555 | 2026-03-09 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001556 | 2026-03-09 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001557 | 2026-03-09 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001558 | 2026-03-09 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001559 | 2026-03-09 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 55 | 770 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001560 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001561 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001562 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001563 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001564 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001565 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001566 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001567 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001568 | 2026-03-09 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001569 | 2026-03-09 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001570 | 2026-03-09 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001571 | 2026-03-09 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 120 | 840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001572 | 2026-03-09 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 27.5 | 100 | 2750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001573 | 2026-03-09 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001574 | 2026-03-09 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 100 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001575 | 2026-03-09 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 35 | 100 | 3500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001576 | 2026-03-09 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 100 | 500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001577 | 2026-03-09 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001578 | 2026-03-09 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001579 | 2026-03-09 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001580 | 2026-03-09 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 33 | 67.5 | 2227.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001581 | 2026-03-09 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 67.5 | 472.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001582 | 2026-03-09 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001583 | 2026-03-09 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 67.5 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001584 | 2026-03-09 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 17.5 | 102.5 | 1793.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001585 | 2026-03-09 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 102.5 | 512.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001586 | 2026-03-09 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001587 | 2026-03-09 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001588 | 2026-03-09 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 32.5 | 77.5 | 2518.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001589 | 2026-03-09 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 77.5 | 581.25 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001590 | 2026-03-09 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 26 | 65 | 1690 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001591 | 2026-03-09 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001592 | 2026-03-09 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 65 | 130 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001593 | 2026-03-09 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001594 | 2026-03-09 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001595 | 2026-03-09 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001596 | 2026-03-09 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 117.5 | 293.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001597 | 2026-03-09 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001598 | 2026-03-09 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001599 | 2026-03-09 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001600 | 2026-03-09 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001601 | 2026-03-09 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 95 | 1757.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001602 | 2026-03-09 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 95 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001603 | 2026-03-09 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001604 | 2026-03-09 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001605 | 2026-03-09 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23.5 | 60 | 1410 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001606 | 2026-03-09 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001607 | 2026-03-09 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001608 | 2026-03-09 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001609 | 2026-03-09 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 90 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001610 | 2026-03-09 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001611 | 2026-03-09 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001612 | 2026-03-09 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 62.5 | 781.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001613 | 2026-03-09 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001614 | 2026-03-09 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 62.5 | 906.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001615 | 2026-03-09 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001616 | 2026-03-09 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 62.5 | 906.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001617 | 2026-03-09 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001618 | 2026-03-09 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 105 | 3727.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001619 | 2026-03-09 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001620 | 2026-03-09 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 72.5 | 2573.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001621 | 2026-03-09 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001622 | 2026-03-09 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001623 | 2026-03-09 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001624 | 2026-03-09 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001625 | 2026-03-09 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001626 | 2026-03-09 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 120 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001627 | 2026-03-09 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 100 | 2550 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001628 | 2026-03-09 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 100 | 1450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001629 | 2026-03-09 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001630 | 2026-03-09 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001631 | 2026-03-09 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001632 | 2026-03-09 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 67.5 | 607.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001633 | 2026-03-09 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001634 | 2026-03-09 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 75 | 1612.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001635 | 2026-03-09 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001636 | 2026-03-09 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15 | 75 | 1125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001637 | 2026-03-09 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 97.5 | 1852.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001638 | 2026-03-09 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001639 | 2026-03-09 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001640 | 2026-03-09 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001641 | 2026-03-09 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 26 | 75 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001642 | 2026-03-09 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 75 | 450 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001643 | 2026-03-09 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001644 | 2026-03-09 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001645 | 2026-03-09 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001646 | 2026-03-09 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001647 | 2026-03-09 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001648 | 2026-03-09 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001649 | 2026-03-09 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 115 | 1495 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001650 | 2026-03-09 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001651 | 2026-03-09 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001652 | 2026-03-09 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001653 | 2026-03-09 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001654 | 2026-03-09 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 87.5 | 87.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001655 | 2026-03-09 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001656 | 2026-03-09 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001657 | 2026-03-09 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001658 | 2026-03-09 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 60 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001659 | 2026-03-09 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001660 | 2026-03-09 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 60 | 720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001661 | 2026-03-16 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001662 | 2026-03-16 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001663 | 2026-03-16 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001664 | 2026-03-16 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001665 | 2026-03-16 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001666 | 2026-03-16 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001667 | 2026-03-16 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001668 | 2026-03-16 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001669 | 2026-03-16 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001670 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001671 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001672 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001673 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001674 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001675 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001676 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001677 | 2026-03-16 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001678 | 2026-03-16 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 80 | 2560 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001679 | 2026-03-16 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001680 | 2026-03-16 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001681 | 2026-03-16 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001682 | 2026-03-16 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001683 | 2026-03-16 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001684 | 2026-03-16 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001685 | 2026-03-16 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001686 | 2026-03-16 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001687 | 2026-03-16 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23 | 62.5 | 1437.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001688 | 2026-03-16 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001689 | 2026-03-16 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001690 | 2026-03-16 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001691 | 2026-03-16 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001692 | 2026-03-16 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001693 | 2026-03-16 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001694 | 2026-03-16 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001695 | 2026-03-16 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001696 | 2026-03-16 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001697 | 2026-03-16 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 55 | 1815 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001698 | 2026-03-16 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001699 | 2026-03-16 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001700 | 2026-03-16 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001701 | 2026-03-16 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001702 | 2026-03-16 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001703 | 2026-03-16 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001704 | 2026-03-16 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001705 | 2026-03-16 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001706 | 2026-03-16 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001707 | 2026-03-16 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001708 | 2026-03-16 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001709 | 2026-03-16 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001710 | 2026-03-16 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001711 | 2026-03-16 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001712 | 2026-03-16 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001713 | 2026-03-16 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001714 | 2026-03-16 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001715 | 2026-03-16 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001716 | 2026-03-16 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 19 | 162.5 | 3087.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001717 | 2026-03-16 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001718 | 2026-03-16 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001719 | 2026-03-16 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001720 | 2026-03-16 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001721 | 2026-03-16 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001722 | 2026-03-16 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001723 | 2026-03-16 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001724 | 2026-03-16 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001725 | 2026-03-16 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001726 | 2026-03-16 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001727 | 2026-03-16 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001728 | 2026-03-16 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001729 | 2026-03-16 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001730 | 2026-03-16 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001731 | 2026-03-16 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001732 | 2026-03-16 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001733 | 2026-03-16 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001734 | 2026-03-16 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001735 | 2026-03-16 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 85 | 212.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001736 | 2026-03-16 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 12.5 | 82.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001737 | 2026-03-16 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 11.5 | 82.5 | 948.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001738 | 2026-03-16 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001739 | 2026-03-16 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001740 | 2026-03-16 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001741 | 2026-03-16 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001742 | 2026-03-16 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001743 | 2026-03-16 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19.5 | 67.5 | 1316.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001744 | 2026-03-16 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001745 | 2026-03-16 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001746 | 2026-03-16 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001747 | 2026-03-16 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001748 | 2026-03-16 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001749 | 2026-03-16 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001750 | 2026-03-16 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001751 | 2026-03-16 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001752 | 2026-03-16 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 55 | 770 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001753 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001754 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001755 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001756 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001757 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001758 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001759 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001760 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001761 | 2026-03-16 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001762 | 2026-03-16 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001763 | 2026-03-16 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001764 | 2026-03-16 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 120 | 780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001765 | 2026-03-16 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001766 | 2026-03-16 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001767 | 2026-03-16 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001768 | 2026-03-16 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 100 | 2050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001769 | 2026-03-16 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001770 | 2026-03-16 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001771 | 2026-03-16 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 28 | 75 | 2100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001772 | 2026-03-16 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 75 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001773 | 2026-03-16 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 67.5 | 1991.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001774 | 2026-03-16 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 67.5 | 708.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001775 | 2026-03-16 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 27.5 | 67.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001776 | 2026-03-16 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 67.5 | 843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001777 | 2026-03-16 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 102.5 | 2050 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001778 | 2026-03-16 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 102.5 | 410 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001779 | 2026-03-16 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001780 | 2026-03-16 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 33 | 77.5 | 2557.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001781 | 2026-03-16 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 77.5 | 542.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001782 | 2026-03-16 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001783 | 2026-03-16 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 65 | 715 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001784 | 2026-03-16 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 65 | 65 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001785 | 2026-03-16 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001786 | 2026-03-16 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001787 | 2026-03-16 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001788 | 2026-03-16 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 17 | 82.5 | 1402.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001789 | 2026-03-16 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001790 | 2026-03-16 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001791 | 2026-03-16 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001792 | 2026-03-16 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 95 | 1995 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001793 | 2026-03-16 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001794 | 2026-03-16 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001795 | 2026-03-16 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001796 | 2026-03-16 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13.5 | 60 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001797 | 2026-03-16 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 9 | 60 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001798 | 2026-03-16 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001799 | 2026-03-16 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001800 | 2026-03-16 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 90 | 1845 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001801 | 2026-03-16 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001802 | 2026-03-16 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001803 | 2026-03-16 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18 | 62.5 | 1125 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001804 | 2026-03-16 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001805 | 2026-03-16 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001806 | 2026-03-16 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 62.5 | 125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001807 | 2026-03-16 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001808 | 2026-03-16 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001809 | 2026-03-16 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 62.5 | 781.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001810 | 2026-03-16 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001811 | 2026-03-16 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 35.5 | 105 | 3727.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001812 | 2026-03-16 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001813 | 2026-03-16 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 72.5 | 2610 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001814 | 2026-03-16 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001815 | 2026-03-16 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001816 | 2026-03-16 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001817 | 2026-03-16 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 120 | 3060 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001818 | 2026-03-16 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001819 | 2026-03-16 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 120 | 1260 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001820 | 2026-03-16 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 21.5 | 100 | 2150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001821 | 2026-03-16 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 100 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001822 | 2026-03-16 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001823 | 2026-03-16 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001824 | 2026-03-16 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 21.5 | 67.5 | 1451.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001825 | 2026-03-16 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 67.5 | 877.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001826 | 2026-03-16 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 67.5 | 371.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001827 | 2026-03-16 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20 | 75 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001828 | 2026-03-16 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20 | 75 | 1500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001829 | 2026-03-16 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 23 | 75 | 1725 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001830 | 2026-03-16 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 75 | 1275 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001831 | 2026-03-16 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001832 | 2026-03-16 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001833 | 2026-03-16 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 97.5 | 1072.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001834 | 2026-03-16 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001835 | 2026-03-16 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9 | 75 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001836 | 2026-03-16 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001837 | 2026-03-16 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 67.5 | 1046.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001838 | 2026-03-16 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 67.5 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001839 | 2026-03-16 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 67.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001840 | 2026-03-16 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001841 | 2026-03-16 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001842 | 2026-03-16 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 115 | 1495 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001843 | 2026-03-16 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001844 | 2026-03-16 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 87.5 | 1793.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001845 | 2026-03-16 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001846 | 2026-03-16 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001847 | 2026-03-16 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001848 | 2026-03-16 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001849 | 2026-03-16 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001850 | 2026-03-16 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001851 | 2026-03-16 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001852 | 2026-03-16 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 60 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001853 | 2026-03-16 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001854 | 2026-03-16 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 60 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001855 | 2026-03-23 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001856 | 2026-03-23 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001857 | 2026-03-23 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001858 | 2026-03-23 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001859 | 2026-03-23 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001860 | 2026-03-23 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001861 | 2026-03-23 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001862 | 2026-03-23 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001863 | 2026-03-23 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001864 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001865 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001866 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001867 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001868 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001869 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001870 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001871 | 2026-03-23 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001872 | 2026-03-23 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 80 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001873 | 2026-03-23 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001874 | 2026-03-23 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001875 | 2026-03-23 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001876 | 2026-03-23 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001877 | 2026-03-23 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001878 | 2026-03-23 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001879 | 2026-03-23 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001880 | 2026-03-23 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001881 | 2026-03-23 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 62.5 | 2000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001882 | 2026-03-23 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001883 | 2026-03-23 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001884 | 2026-03-23 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001885 | 2026-03-23 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001886 | 2026-03-23 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001887 | 2026-03-23 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001888 | 2026-03-23 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001889 | 2026-03-23 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001890 | 2026-03-23 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001891 | 2026-03-23 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 12 | 55 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001892 | 2026-03-23 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001893 | 2026-03-23 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001894 | 2026-03-23 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001895 | 2026-03-23 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001896 | 2026-03-23 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001897 | 2026-03-23 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001898 | 2026-03-23 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001899 | 2026-03-23 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001900 | 2026-03-23 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001901 | 2026-03-23 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001902 | 2026-03-23 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001903 | 2026-03-23 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001904 | 2026-03-23 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001905 | 2026-03-23 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001906 | 2026-03-23 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001907 | 2026-03-23 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001908 | 2026-03-23 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001909 | 2026-03-23 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001910 | 2026-03-23 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001911 | 2026-03-23 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 162.5 | 5200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001912 | 2026-03-23 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001913 | 2026-03-23 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001914 | 2026-03-23 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001915 | 2026-03-23 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001916 | 2026-03-23 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 20 | 150 | 3000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001917 | 2026-03-23 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001918 | 2026-03-23 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001919 | 2026-03-23 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001920 | 2026-03-23 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001921 | 2026-03-23 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001922 | 2026-03-23 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001923 | 2026-03-23 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001924 | 2026-03-23 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001925 | 2026-03-23 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001926 | 2026-03-23 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001927 | 2026-03-23 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001928 | 2026-03-23 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001929 | 2026-03-23 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001930 | 2026-03-23 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001931 | 2026-03-23 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001932 | 2026-03-23 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001933 | 2026-03-23 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001934 | 2026-03-23 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001935 | 2026-03-23 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001936 | 2026-03-23 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21 | 67.5 | 1417.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001937 | 2026-03-23 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001938 | 2026-03-23 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001939 | 2026-03-23 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001940 | 2026-03-23 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001941 | 2026-03-23 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001942 | 2026-03-23 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001943 | 2026-03-23 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001944 | 2026-03-23 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001945 | 2026-03-23 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 55 | 770 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001946 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001947 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001948 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001949 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001950 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001951 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001952 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001953 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001954 | 2026-03-23 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001955 | 2026-03-23 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 120 | 2220 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001956 | 2026-03-23 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 120 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001957 | 2026-03-23 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001958 | 2026-03-23 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001959 | 2026-03-23 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 100 | 2550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001960 | 2026-03-23 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001961 | 2026-03-23 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 100 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001962 | 2026-03-23 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 33.5 | 100 | 3350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001963 | 2026-03-23 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 100 | 650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001964 | 2026-03-23 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 29 | 75 | 2175 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001965 | 2026-03-23 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001966 | 2026-03-23 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 33 | 67.5 | 2227.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001967 | 2026-03-23 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 67.5 | 472.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001968 | 2026-03-23 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25.5 | 67.5 | 1721.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001969 | 2026-03-23 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 67.5 | 978.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001970 | 2026-03-23 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30.5 | 102.5 | 3126.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001971 | 2026-03-23 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001972 | 2026-03-23 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001973 | 2026-03-23 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 29 | 77.5 | 2247.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001974 | 2026-03-23 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 77.5 | 620 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001975 | 2026-03-23 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 77.5 | 232.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001976 | 2026-03-23 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 29.5 | 65 | 1917.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001977 | 2026-03-23 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 10.5 | 65 | 682.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001978 | 2026-03-23 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001979 | 2026-03-23 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001980 | 2026-03-23 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001981 | 2026-03-23 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001982 | 2026-03-23 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 9 | 82.5 | 742.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001983 | 2026-03-23 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 82.5 | 825 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001984 | 2026-03-23 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 82.5 | 412.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001985 | 2026-03-23 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001986 | 2026-03-23 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001987 | 2026-03-23 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001988 | 2026-03-23 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001989 | 2026-03-23 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 60 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001990 | 2026-03-23 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001991 | 2026-03-23 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001992 | 2026-03-23 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001993 | 2026-03-23 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001994 | 2026-03-23 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001995 | 2026-03-23 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 62.5 | 1281.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001996 | 2026-03-23 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001997 | 2026-03-23 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001998 | 2026-03-23 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-001999 | 2026-03-23 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 62.5 | 906.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002000 | 2026-03-23 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002001 | 2026-03-23 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16 | 62.5 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002002 | 2026-03-23 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 105 | 262.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002003 | 2026-03-23 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 21.5 | 105 | 2257.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002004 | 2026-03-23 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002005 | 2026-03-23 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002006 | 2026-03-23 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36.5 | 72.5 | 2646.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002007 | 2026-03-23 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002008 | 2026-03-23 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002009 | 2026-03-23 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002010 | 2026-03-23 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002011 | 2026-03-23 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002012 | 2026-03-23 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 120 | 1680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002013 | 2026-03-23 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 30 | 100 | 3000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002014 | 2026-03-23 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002015 | 2026-03-23 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 90 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002016 | 2026-03-23 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002017 | 2026-03-23 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002018 | 2026-03-23 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 67.5 | 877.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002019 | 2026-03-23 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 67.5 | 472.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002020 | 2026-03-23 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 75 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002021 | 2026-03-23 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 75 | 862.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002022 | 2026-03-23 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002023 | 2026-03-23 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 25.5 | 75 | 1912.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002024 | 2026-03-23 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 75 | 1087.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002025 | 2026-03-23 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002026 | 2026-03-23 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002027 | 2026-03-23 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 13 | 97.5 | 1267.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002028 | 2026-03-23 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 75 | 2325 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002029 | 2026-03-23 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002030 | 2026-03-23 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002031 | 2026-03-23 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002032 | 2026-03-23 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002033 | 2026-03-23 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002034 | 2026-03-23 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002035 | 2026-03-23 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 115 | 1495 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002036 | 2026-03-23 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002037 | 2026-03-23 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002038 | 2026-03-23 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002039 | 2026-03-23 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002040 | 2026-03-23 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002041 | 2026-03-23 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002042 | 2026-03-23 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002043 | 2026-03-23 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002044 | 2026-03-23 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 60 | 780 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002045 | 2026-03-23 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 4.5 | 60 | 270 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002046 | 2026-03-23 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 60 | 390 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002047 | 2026-03-23 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002048 | 2026-03-30 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002049 | 2026-03-30 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002050 | 2026-03-30 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002051 | 2026-03-30 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002052 | 2026-03-30 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002053 | 2026-03-30 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002054 | 2026-03-30 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002055 | 2026-03-30 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002056 | 2026-03-30 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002057 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002058 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002059 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002060 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002061 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002062 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002063 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002064 | 2026-03-30 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002065 | 2026-03-30 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 80 | 2560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002066 | 2026-03-30 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002067 | 2026-03-30 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002068 | 2026-03-30 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002069 | 2026-03-30 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002070 | 2026-03-30 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002071 | 2026-03-30 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002072 | 2026-03-30 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002073 | 2026-03-30 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002074 | 2026-03-30 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 62.5 | 1937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002075 | 2026-03-30 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002076 | 2026-03-30 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002077 | 2026-03-30 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002078 | 2026-03-30 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002079 | 2026-03-30 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002080 | 2026-03-30 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002081 | 2026-03-30 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002082 | 2026-03-30 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002083 | 2026-03-30 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002084 | 2026-03-30 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 55 | 1815 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002085 | 2026-03-30 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002086 | 2026-03-30 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002087 | 2026-03-30 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002088 | 2026-03-30 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002089 | 2026-03-30 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002090 | 2026-03-30 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002091 | 2026-03-30 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002092 | 2026-03-30 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002093 | 2026-03-30 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002094 | 2026-03-30 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002095 | 2026-03-30 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002096 | 2026-03-30 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002097 | 2026-03-30 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002098 | 2026-03-30 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002099 | 2026-03-30 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002100 | 2026-03-30 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002101 | 2026-03-30 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002102 | 2026-03-30 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002103 | 2026-03-30 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 162.5 | 5200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002104 | 2026-03-30 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002105 | 2026-03-30 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002106 | 2026-03-30 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002107 | 2026-03-30 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002108 | 2026-03-30 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 150 | 4500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002109 | 2026-03-30 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002110 | 2026-03-30 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002111 | 2026-03-30 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002112 | 2026-03-30 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002113 | 2026-03-30 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002114 | 2026-03-30 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002115 | 2026-03-30 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002116 | 2026-03-30 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002117 | 2026-03-30 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002118 | 2026-03-30 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002119 | 2026-03-30 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002120 | 2026-03-30 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002121 | 2026-03-30 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22 | 82.5 | 1815 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002122 | 2026-03-30 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002123 | 2026-03-30 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002124 | 2026-03-30 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002125 | 2026-03-30 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002126 | 2026-03-30 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002127 | 2026-03-30 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 12.5 | 67.5 | 843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002128 | 2026-03-30 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002129 | 2026-03-30 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002130 | 2026-03-30 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002131 | 2026-03-30 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002132 | 2026-03-30 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002133 | 2026-03-30 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002134 | 2026-03-30 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002135 | 2026-03-30 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002136 | 2026-03-30 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002137 | 2026-03-30 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14.5 | 55 | 797.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002138 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002139 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002140 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002141 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002142 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002143 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002144 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002145 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002146 | 2026-03-30 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002147 | 2026-03-30 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002148 | 2026-03-30 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002149 | 2026-03-30 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002150 | 2026-03-30 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002151 | 2026-03-30 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002152 | 2026-03-30 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002153 | 2026-03-30 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 33.5 | 100 | 3350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002154 | 2026-03-30 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 100 | 650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002155 | 2026-03-30 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 29 | 75 | 2175 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002156 | 2026-03-30 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002157 | 2026-03-30 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 67.5 | 2092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002158 | 2026-03-30 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 67.5 | 607.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002159 | 2026-03-30 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 29.5 | 67.5 | 1991.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002160 | 2026-03-30 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 67.5 | 708.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002161 | 2026-03-30 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 32.5 | 102.5 | 3331.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002162 | 2026-03-30 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002163 | 2026-03-30 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 31.5 | 77.5 | 2441.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002164 | 2026-03-30 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 77.5 | 658.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002165 | 2026-03-30 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 25.5 | 65 | 1657.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002166 | 2026-03-30 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002167 | 2026-03-30 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 65 | 130 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002168 | 2026-03-30 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 117.5 | 1116.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002169 | 2026-03-30 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 117.5 | 1116.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002170 | 2026-03-30 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 117.5 | 528.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002171 | 2026-03-30 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002172 | 2026-03-30 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002173 | 2026-03-30 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002174 | 2026-03-30 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002175 | 2026-03-30 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002176 | 2026-03-30 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002177 | 2026-03-30 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002178 | 2026-03-30 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002179 | 2026-03-30 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002180 | 2026-03-30 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 95 | 190 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002181 | 2026-03-30 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 24.5 | 60 | 1470 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002182 | 2026-03-30 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002183 | 2026-03-30 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002184 | 2026-03-30 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 13 | 90 | 1170 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002185 | 2026-03-30 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002186 | 2026-03-30 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002187 | 2026-03-30 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 5 | 62.5 | 312.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002188 | 2026-03-30 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 3 | 62.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002189 | 2026-03-30 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002190 | 2026-03-30 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002191 | 2026-03-30 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002192 | 2026-03-30 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002193 | 2026-03-30 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 62.5 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002194 | 2026-03-30 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002195 | 2026-03-30 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002196 | 2026-03-30 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002197 | 2026-03-30 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36.5 | 72.5 | 2646.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002198 | 2026-03-30 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002199 | 2026-03-30 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002200 | 2026-03-30 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002201 | 2026-03-30 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002202 | 2026-03-30 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002203 | 2026-03-30 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002204 | 2026-03-30 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 120 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002205 | 2026-03-30 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002206 | 2026-03-30 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 100 | 1150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002207 | 2026-03-30 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 90 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002208 | 2026-03-30 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 67.5 | 1316.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002209 | 2026-03-30 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002210 | 2026-03-30 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8 | 67.5 | 540 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002211 | 2026-03-30 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 75 | 1612.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002212 | 2026-03-30 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18.5 | 75 | 1387.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002213 | 2026-03-30 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 22.5 | 75 | 1687.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002214 | 2026-03-30 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 75 | 1312.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002215 | 2026-03-30 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 97.5 | 1121.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002216 | 2026-03-30 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4.5 | 97.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002217 | 2026-03-30 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002218 | 2026-03-30 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002219 | 2026-03-30 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002220 | 2026-03-30 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 75 | 975 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002221 | 2026-03-30 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 75 | 225 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002222 | 2026-03-30 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002223 | 2026-03-30 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002224 | 2026-03-30 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002225 | 2026-03-30 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002226 | 2026-03-30 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 18 | 115 | 2070 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002227 | 2026-03-30 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002228 | 2026-03-30 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002229 | 2026-03-30 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 115 | 345 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002230 | 2026-03-30 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002231 | 2026-03-30 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002232 | 2026-03-30 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002233 | 2026-03-30 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 87.5 | 87.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002234 | 2026-03-30 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002235 | 2026-03-30 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 90 | 270 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002236 | 2026-03-30 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 5 | 90 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002237 | 2026-03-30 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002238 | 2026-03-30 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002239 | 2026-03-30 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 20.5 | 60 | 1230 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002240 | 2026-03-30 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002241 | 2026-03-30 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 60 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002242 | 2026-04-06 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002243 | 2026-04-06 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002244 | 2026-04-06 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002245 | 2026-04-06 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002246 | 2026-04-06 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002247 | 2026-04-06 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002248 | 2026-04-06 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002249 | 2026-04-06 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002250 | 2026-04-06 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002251 | 2026-04-06 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27.5 | 97.5 | 2681.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002252 | 2026-04-06 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002253 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002254 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002255 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002256 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002257 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002258 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002259 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002260 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002261 | 2026-04-06 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002262 | 2026-04-06 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27.5 | 80 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002263 | 2026-04-06 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002264 | 2026-04-06 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002265 | 2026-04-06 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002266 | 2026-04-06 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002267 | 2026-04-06 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002268 | 2026-04-06 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002269 | 2026-04-06 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002270 | 2026-04-06 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002271 | 2026-04-06 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002272 | 2026-04-06 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002273 | 2026-04-06 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23 | 62.5 | 1437.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002274 | 2026-04-06 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002275 | 2026-04-06 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002276 | 2026-04-06 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002277 | 2026-04-06 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002278 | 2026-04-06 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002279 | 2026-04-06 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002280 | 2026-04-06 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002281 | 2026-04-06 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002282 | 2026-04-06 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002283 | 2026-04-06 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002284 | 2026-04-06 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002285 | 2026-04-06 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002286 | 2026-04-06 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27.5 | 55 | 1512.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002287 | 2026-04-06 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002288 | 2026-04-06 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002289 | 2026-04-06 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002290 | 2026-04-06 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002291 | 2026-04-06 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002292 | 2026-04-06 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 28 | 187.5 | 5250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002293 | 2026-04-06 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002294 | 2026-04-06 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 8 | 157.5 | 1260 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002295 | 2026-04-06 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002296 | 2026-04-06 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002297 | 2026-04-06 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 162.5 | 81.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002298 | 2026-04-06 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 162.5 | 81.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002299 | 2026-04-06 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 162.5 | 81.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002300 | 2026-04-06 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 162.5 | 81.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002301 | 2026-04-06 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 6 | 162.5 | 975 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002302 | 2026-04-06 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002303 | 2026-04-06 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002304 | 2026-04-06 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002305 | 2026-04-06 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002306 | 2026-04-06 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002307 | 2026-04-06 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002308 | 2026-04-06 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002309 | 2026-04-06 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 5.5 | 150 | 825 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002310 | 2026-04-06 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002311 | 2026-04-06 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002312 | 2026-04-06 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002313 | 2026-04-06 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002314 | 2026-04-06 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002315 | 2026-04-06 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002316 | 2026-04-06 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002317 | 2026-04-06 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002318 | 2026-04-06 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002319 | 2026-04-06 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002320 | 2026-04-06 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002321 | 2026-04-06 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18.5 | 105 | 1942.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002322 | 2026-04-06 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002323 | 2026-04-06 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002324 | 2026-04-06 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 12.5 | 85 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002325 | 2026-04-06 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4.5 | 85 | 382.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002326 | 2026-04-06 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002327 | 2026-04-06 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 8.5 | 82.5 | 701.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002328 | 2026-04-06 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 7.5 | 82.5 | 618.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002329 | 2026-04-06 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002330 | 2026-04-06 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002331 | 2026-04-06 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002332 | 2026-04-06 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002333 | 2026-04-06 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002334 | 2026-04-06 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002335 | 2026-04-06 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002336 | 2026-04-06 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 17.5 | 67.5 | 1181.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002337 | 2026-04-06 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 9 | 67.5 | 607.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002338 | 2026-04-06 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 5.5 | 67.5 | 371.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002339 | 2026-04-06 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002340 | 2026-04-06 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002341 | 2026-04-06 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002342 | 2026-04-06 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002343 | 2026-04-06 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002344 | 2026-04-06 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002345 | 2026-04-06 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002346 | 2026-04-06 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002347 | 2026-04-06 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002348 | 2026-04-06 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002349 | 2026-04-06 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 9 | 55 | 495 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002350 | 2026-04-06 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002351 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002352 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002353 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002354 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002355 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002356 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002357 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002358 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002359 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002360 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22.5 | 65 | 1462.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002361 | 2026-04-06 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002362 | 2026-04-06 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18 | 120 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002363 | 2026-04-06 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 120 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002364 | 2026-04-06 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002365 | 2026-04-06 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002366 | 2026-04-06 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 21.5 | 100 | 2150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002367 | 2026-04-06 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002368 | 2026-04-06 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 100 | 400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002369 | 2026-04-06 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002370 | 2026-04-06 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 13.5 | 100 | 1350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002371 | 2026-04-06 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002372 | 2026-04-06 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002373 | 2026-04-06 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002374 | 2026-04-06 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 75 | 1650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002375 | 2026-04-06 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 75 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002376 | 2026-04-06 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002377 | 2026-04-06 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 67.5 | 1721.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002378 | 2026-04-06 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 67.5 | 438.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002379 | 2026-04-06 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002380 | 2026-04-06 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 67.5 | 1417.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002381 | 2026-04-06 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 67.5 | 742.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002382 | 2026-04-06 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002383 | 2026-04-06 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 24 | 102.5 | 2460 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002384 | 2026-04-06 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 102.5 | 615 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002385 | 2026-04-06 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 102.5 | 205 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002386 | 2026-04-06 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002387 | 2026-04-06 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 25.5 | 77.5 | 1976.25 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002388 | 2026-04-06 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 77.5 | 503.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002389 | 2026-04-06 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002390 | 2026-04-06 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 22 | 65 | 1430 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002391 | 2026-04-06 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 65 | 650 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002392 | 2026-04-06 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002393 | 2026-04-06 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 117.5 | 1468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002394 | 2026-04-06 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 117.5 | 1527.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002395 | 2026-04-06 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002396 | 2026-04-06 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002397 | 2026-04-06 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002398 | 2026-04-06 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 13.5 | 82.5 | 1113.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002399 | 2026-04-06 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 82.5 | 1072.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002400 | 2026-04-06 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 82.5 | 495 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002401 | 2026-04-06 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002402 | 2026-04-06 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 95 | 1472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002403 | 2026-04-06 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 95 | 902.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002404 | 2026-04-06 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 95 | 617.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002405 | 2026-04-06 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002406 | 2026-04-06 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002407 | 2026-04-06 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18 | 60 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002408 | 2026-04-06 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 60 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002409 | 2026-04-06 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002410 | 2026-04-06 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 90 | 1395 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002411 | 2026-04-06 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002412 | 2026-04-06 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 90 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002413 | 2026-04-06 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002414 | 2026-04-06 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002415 | 2026-04-06 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 62.5 | 937.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002416 | 2026-04-06 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002417 | 2026-04-06 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 62.5 | 406.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002418 | 2026-04-06 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 62.5 | 93.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002419 | 2026-04-06 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002420 | 2026-04-06 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 13.5 | 62.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002421 | 2026-04-06 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 9.5 | 62.5 | 593.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002422 | 2026-04-06 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 62.5 | 562.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002423 | 2026-04-06 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002424 | 2026-04-06 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002425 | 2026-04-06 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 28.5 | 105 | 2992.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002426 | 2026-04-06 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002427 | 2026-04-06 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002428 | 2026-04-06 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002429 | 2026-04-06 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25.5 | 72.5 | 1848.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002430 | 2026-04-06 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002431 | 2026-04-06 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002432 | 2026-04-06 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002433 | 2026-04-06 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002434 | 2026-04-06 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002435 | 2026-04-06 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002436 | 2026-04-06 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002437 | 2026-04-06 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 120 | 2220 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002438 | 2026-04-06 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10 | 120 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002439 | 2026-04-06 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002440 | 2026-04-06 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002441 | 2026-04-06 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 21.5 | 100 | 2150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002442 | 2026-04-06 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 100 | 850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002443 | 2026-04-06 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 100 | 200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002444 | 2026-04-06 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002445 | 2026-04-06 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15 | 90 | 1350 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002446 | 2026-04-06 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 90 | 810 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002447 | 2026-04-06 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002448 | 2026-04-06 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 67.5 | 270 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002449 | 2026-04-06 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 2.5 | 67.5 | 168.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002450 | 2026-04-06 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 1.5 | 67.5 | 101.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002451 | 2026-04-06 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002452 | 2026-04-06 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002453 | 2026-04-06 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 75 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002454 | 2026-04-06 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16 | 75 | 1200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002455 | 2026-04-06 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002456 | 2026-04-06 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002457 | 2026-04-06 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 75 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002458 | 2026-04-06 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 75 | 487.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002459 | 2026-04-06 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002460 | 2026-04-06 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 97.5 | 1462.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002461 | 2026-04-06 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 97.5 | 682.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002462 | 2026-04-06 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 9 | 97.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002463 | 2026-04-06 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 97.5 | 97.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002464 | 2026-04-06 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002465 | 2026-04-06 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 75 | 937.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002466 | 2026-04-06 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 75 | 262.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002467 | 2026-04-06 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002468 | 2026-04-06 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002469 | 2026-04-06 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 67.5 | 1046.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002470 | 2026-04-06 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 67.5 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002471 | 2026-04-06 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 6.5 | 67.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002472 | 2026-04-06 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002473 | 2026-04-06 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 115 | 1782.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002474 | 2026-04-06 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 115 | 1150 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002475 | 2026-04-06 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002476 | 2026-04-06 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002477 | 2026-04-06 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 87.5 | 1312.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002478 | 2026-04-06 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 87.5 | 831.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002479 | 2026-04-06 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 87.5 | 612.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002480 | 2026-04-06 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002481 | 2026-04-06 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002482 | 2026-04-06 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002483 | 2026-04-06 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 90 | 315 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002484 | 2026-04-06 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002485 | 2026-04-06 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002486 | 2026-04-06 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002487 | 2026-04-06 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 16.5 | 60 | 990 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002488 | 2026-04-06 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 6.5 | 60 | 390 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002489 | 2026-04-06 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9 | 60 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002490 | 2026-04-06 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002491 | 2026-04-13 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002492 | 2026-04-13 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002493 | 2026-04-13 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002494 | 2026-04-13 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002495 | 2026-04-13 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002496 | 2026-04-13 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002497 | 2026-04-13 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002498 | 2026-04-13 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002499 | 2026-04-13 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002500 | 2026-04-13 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002501 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002502 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002503 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002504 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002505 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002506 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002507 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002508 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002509 | 2026-04-13 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002510 | 2026-04-13 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 80 | 2560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002511 | 2026-04-13 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002512 | 2026-04-13 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002513 | 2026-04-13 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002514 | 2026-04-13 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002515 | 2026-04-13 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002516 | 2026-04-13 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002517 | 2026-04-13 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002518 | 2026-04-13 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002519 | 2026-04-13 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002520 | 2026-04-13 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23 | 62.5 | 1437.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002521 | 2026-04-13 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002522 | 2026-04-13 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002523 | 2026-04-13 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002524 | 2026-04-13 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002525 | 2026-04-13 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002526 | 2026-04-13 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002527 | 2026-04-13 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002528 | 2026-04-13 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002529 | 2026-04-13 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002530 | 2026-04-13 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002531 | 2026-04-13 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002532 | 2026-04-13 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 19.5 | 55 | 1072.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002533 | 2026-04-13 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002534 | 2026-04-13 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002535 | 2026-04-13 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002536 | 2026-04-13 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002537 | 2026-04-13 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002538 | 2026-04-13 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002539 | 2026-04-13 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002540 | 2026-04-13 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002541 | 2026-04-13 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002542 | 2026-04-13 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002543 | 2026-04-13 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002544 | 2026-04-13 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002545 | 2026-04-13 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002546 | 2026-04-13 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002547 | 2026-04-13 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002548 | 2026-04-13 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 157.5 | 5040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002549 | 2026-04-13 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002550 | 2026-04-13 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002551 | 2026-04-13 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002552 | 2026-04-13 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002553 | 2026-04-13 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 19 | 162.5 | 3087.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002554 | 2026-04-13 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002555 | 2026-04-13 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002556 | 2026-04-13 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002557 | 2026-04-13 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002558 | 2026-04-13 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002559 | 2026-04-13 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002560 | 2026-04-13 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002561 | 2026-04-13 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002562 | 2026-04-13 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002563 | 2026-04-13 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002564 | 2026-04-13 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002565 | 2026-04-13 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002566 | 2026-04-13 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002567 | 2026-04-13 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002568 | 2026-04-13 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002569 | 2026-04-13 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002570 | 2026-04-13 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 105 | 1470 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002571 | 2026-04-13 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002572 | 2026-04-13 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002573 | 2026-04-13 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 14.5 | 85 | 1232.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002574 | 2026-04-13 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002575 | 2026-04-13 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 85 | 170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002576 | 2026-04-13 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002577 | 2026-04-13 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002578 | 2026-04-13 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002579 | 2026-04-13 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002580 | 2026-04-13 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002581 | 2026-04-13 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 21.5 | 67.5 | 1451.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002582 | 2026-04-13 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002583 | 2026-04-13 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7.5 | 67.5 | 506.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002584 | 2026-04-13 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002585 | 2026-04-13 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002586 | 2026-04-13 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002587 | 2026-04-13 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002588 | 2026-04-13 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002589 | 2026-04-13 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002590 | 2026-04-13 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002591 | 2026-04-13 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002592 | 2026-04-13 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002593 | 2026-04-13 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6.5 | 55 | 357.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002594 | 2026-04-13 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002595 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002596 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002597 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002598 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002599 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002600 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002601 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002602 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002603 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002604 | 2026-04-13 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 65 | 1430 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002605 | 2026-04-13 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002606 | 2026-04-13 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002607 | 2026-04-13 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 120 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002608 | 2026-04-13 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002609 | 2026-04-13 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002610 | 2026-04-13 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002611 | 2026-04-13 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 100 | 3100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002612 | 2026-04-13 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 100 | 900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002613 | 2026-04-13 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002614 | 2026-04-13 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 75 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002615 | 2026-04-13 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002616 | 2026-04-13 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002617 | 2026-04-13 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 67.5 | 675 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002618 | 2026-04-13 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 67.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002619 | 2026-04-13 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 67.5 | 675 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002620 | 2026-04-13 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002621 | 2026-04-13 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30 | 102.5 | 3075 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002622 | 2026-04-13 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 102.5 | 871.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002623 | 2026-04-13 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 102.5 | 153.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002624 | 2026-04-13 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30 | 77.5 | 2325 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002625 | 2026-04-13 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002626 | 2026-04-13 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 77.5 | 193.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002627 | 2026-04-13 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 29 | 65 | 1885 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002628 | 2026-04-13 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 65 | 715 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002629 | 2026-04-13 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 117.5 | 1527.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002630 | 2026-04-13 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 117.5 | 1351.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002631 | 2026-04-13 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002632 | 2026-04-13 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 117.5 | 646.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002633 | 2026-04-13 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002634 | 2026-04-13 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002635 | 2026-04-13 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002636 | 2026-04-13 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002637 | 2026-04-13 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 95 | 1757.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002638 | 2026-04-13 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002639 | 2026-04-13 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002640 | 2026-04-13 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 95 | 95 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002641 | 2026-04-13 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 25 | 60 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002642 | 2026-04-13 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 60 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002643 | 2026-04-13 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002644 | 2026-04-13 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002645 | 2026-04-13 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002646 | 2026-04-13 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002647 | 2026-04-13 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002648 | 2026-04-13 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 62.5 | 281.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002649 | 2026-04-13 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002650 | 2026-04-13 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 62.5 | 968.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002651 | 2026-04-13 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002652 | 2026-04-13 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 62.5 | 812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002653 | 2026-04-13 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002654 | 2026-04-13 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 27.5 | 105 | 2887.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002655 | 2026-04-13 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002656 | 2026-04-13 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002657 | 2026-04-13 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002658 | 2026-04-13 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002659 | 2026-04-13 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002660 | 2026-04-13 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002661 | 2026-04-13 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002662 | 2026-04-13 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 120 | 2280 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002663 | 2026-04-13 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10 | 120 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002664 | 2026-04-13 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 120 | 360 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002665 | 2026-04-13 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002666 | 2026-04-13 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002667 | 2026-04-13 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002668 | 2026-04-13 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 90 | 1935 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002669 | 2026-04-13 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18.5 | 90 | 1665 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002670 | 2026-04-13 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002671 | 2026-04-13 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002672 | 2026-04-13 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 67.5 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002673 | 2026-04-13 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002674 | 2026-04-13 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002675 | 2026-04-13 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 75 | 1612.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002676 | 2026-04-13 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 75 | 1912.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002677 | 2026-04-13 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 75 | 600 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002678 | 2026-04-13 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 75 | 487.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002679 | 2026-04-13 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002680 | 2026-04-13 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002681 | 2026-04-13 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002682 | 2026-04-13 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 30.5 | 75 | 2287.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002683 | 2026-04-13 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002684 | 2026-04-13 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002685 | 2026-04-13 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002686 | 2026-04-13 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002687 | 2026-04-13 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002688 | 2026-04-13 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002689 | 2026-04-13 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 115 | 2185 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002690 | 2026-04-13 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 115 | 1437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002691 | 2026-04-13 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002692 | 2026-04-13 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002693 | 2026-04-13 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 87.5 | 437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002694 | 2026-04-13 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 87.5 | 306.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002695 | 2026-04-13 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002696 | 2026-04-13 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002697 | 2026-04-13 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002698 | 2026-04-13 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002699 | 2026-04-13 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 19 | 60 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002700 | 2026-04-13 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002701 | 2026-04-13 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11 | 60 | 660 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002702 | 2026-04-13 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002703 | 2026-04-20 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002704 | 2026-04-20 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002705 | 2026-04-20 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002706 | 2026-04-20 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002707 | 2026-04-20 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002708 | 2026-04-20 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002709 | 2026-04-20 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002710 | 2026-04-20 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002711 | 2026-04-20 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002712 | 2026-04-20 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002713 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002714 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002715 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002716 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002717 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002718 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002719 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002720 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002721 | 2026-04-20 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002722 | 2026-04-20 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002723 | 2026-04-20 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002724 | 2026-04-20 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002725 | 2026-04-20 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002726 | 2026-04-20 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002727 | 2026-04-20 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002728 | 2026-04-20 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002729 | 2026-04-20 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002730 | 2026-04-20 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002731 | 2026-04-20 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002732 | 2026-04-20 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 62.5 | 1937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002733 | 2026-04-20 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002734 | 2026-04-20 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002735 | 2026-04-20 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002736 | 2026-04-20 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002737 | 2026-04-20 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002738 | 2026-04-20 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002739 | 2026-04-20 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002740 | 2026-04-20 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002741 | 2026-04-20 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002742 | 2026-04-20 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002743 | 2026-04-20 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 55 | 1732.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002744 | 2026-04-20 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002745 | 2026-04-20 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002746 | 2026-04-20 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002747 | 2026-04-20 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002748 | 2026-04-20 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 22 | 187.5 | 4125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002749 | 2026-04-20 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002750 | 2026-04-20 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002751 | 2026-04-20 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002752 | 2026-04-20 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002753 | 2026-04-20 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002754 | 2026-04-20 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002755 | 2026-04-20 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002756 | 2026-04-20 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002757 | 2026-04-20 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002758 | 2026-04-20 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002759 | 2026-04-20 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31.5 | 157.5 | 4961.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002760 | 2026-04-20 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002761 | 2026-04-20 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002762 | 2026-04-20 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002763 | 2026-04-20 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002764 | 2026-04-20 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 162.5 | 5200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002765 | 2026-04-20 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002766 | 2026-04-20 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002767 | 2026-04-20 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002768 | 2026-04-20 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002769 | 2026-04-20 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002770 | 2026-04-20 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002771 | 2026-04-20 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002772 | 2026-04-20 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002773 | 2026-04-20 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002774 | 2026-04-20 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002775 | 2026-04-20 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002776 | 2026-04-20 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002777 | 2026-04-20 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002778 | 2026-04-20 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002779 | 2026-04-20 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002780 | 2026-04-20 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 105 | 2310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002781 | 2026-04-20 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002782 | 2026-04-20 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 17 | 85 | 1445 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002783 | 2026-04-20 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002784 | 2026-04-20 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 9 | 82.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002785 | 2026-04-20 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 7 | 82.5 | 577.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002786 | 2026-04-20 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002787 | 2026-04-20 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002788 | 2026-04-20 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002789 | 2026-04-20 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 22 | 67.5 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002790 | 2026-04-20 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002791 | 2026-04-20 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 67.5 | 472.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002792 | 2026-04-20 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002793 | 2026-04-20 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002794 | 2026-04-20 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002795 | 2026-04-20 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002796 | 2026-04-20 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002797 | 2026-04-20 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002798 | 2026-04-20 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002799 | 2026-04-20 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002800 | 2026-04-20 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002801 | 2026-04-20 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 11 | 55 | 605 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002802 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002803 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002804 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002805 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002806 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002807 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002808 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002809 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002810 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002811 | 2026-04-20 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 65 | 1430 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002812 | 2026-04-20 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 120 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002813 | 2026-04-20 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 120 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002814 | 2026-04-20 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002815 | 2026-04-20 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002816 | 2026-04-20 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 100 | 1100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002817 | 2026-04-20 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 100 | 350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002818 | 2026-04-20 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002819 | 2026-04-20 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002820 | 2026-04-20 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 34 | 100 | 3400 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002821 | 2026-04-20 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 100 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002822 | 2026-04-20 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002823 | 2026-04-20 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002824 | 2026-04-20 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 75 | 262.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002825 | 2026-04-20 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 67.5 | 1316.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002826 | 2026-04-20 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 67.5 | 303.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002827 | 2026-04-20 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002828 | 2026-04-20 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 29 | 67.5 | 1957.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002829 | 2026-04-20 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 67.5 | 742.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002830 | 2026-04-20 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 13 | 102.5 | 1332.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002831 | 2026-04-20 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 102.5 | 307.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002832 | 2026-04-20 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002833 | 2026-04-20 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30.5 | 77.5 | 2363.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002834 | 2026-04-20 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002835 | 2026-04-20 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 77.5 | 155 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002836 | 2026-04-20 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 27.5 | 65 | 1787.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002837 | 2026-04-20 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002838 | 2026-04-20 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002839 | 2026-04-20 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002840 | 2026-04-20 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002841 | 2026-04-20 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002842 | 2026-04-20 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 82.5 | 1196.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002843 | 2026-04-20 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 82.5 | 701.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002844 | 2026-04-20 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002845 | 2026-04-20 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 95 | 1995 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002846 | 2026-04-20 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002847 | 2026-04-20 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002848 | 2026-04-20 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002849 | 2026-04-20 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002850 | 2026-04-20 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 18 | 90 | 1620 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002851 | 2026-04-20 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 13 | 90 | 1170 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002852 | 2026-04-20 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002853 | 2026-04-20 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002854 | 2026-04-20 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 18 | 62.5 | 1125 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002855 | 2026-04-20 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002856 | 2026-04-20 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002857 | 2026-04-20 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 62.5 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002858 | 2026-04-20 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002859 | 2026-04-20 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002860 | 2026-04-20 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 62.5 | 812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002861 | 2026-04-20 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002862 | 2026-04-20 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002863 | 2026-04-20 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002864 | 2026-04-20 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002865 | 2026-04-20 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002866 | 2026-04-20 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002867 | 2026-04-20 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002868 | 2026-04-20 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002869 | 2026-04-20 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002870 | 2026-04-20 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002871 | 2026-04-20 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002872 | 2026-04-20 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002873 | 2026-04-20 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002874 | 2026-04-20 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002875 | 2026-04-20 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 90 | 630 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002876 | 2026-04-20 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 90 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002877 | 2026-04-20 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002878 | 2026-04-20 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 19 | 67.5 | 1282.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002879 | 2026-04-20 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002880 | 2026-04-20 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002881 | 2026-04-20 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002882 | 2026-04-20 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002883 | 2026-04-20 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20.5 | 75 | 1537.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002884 | 2026-04-20 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 23.5 | 75 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002885 | 2026-04-20 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002886 | 2026-04-20 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 75 | 675 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002887 | 2026-04-20 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002888 | 2026-04-20 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002889 | 2026-04-20 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 11 | 97.5 | 1072.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002890 | 2026-04-20 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002891 | 2026-04-20 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002892 | 2026-04-20 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002893 | 2026-04-20 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002894 | 2026-04-20 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002895 | 2026-04-20 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 115 | 2357.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002896 | 2026-04-20 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 115 | 1437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002897 | 2026-04-20 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002898 | 2026-04-20 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002899 | 2026-04-20 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 87.5 | 437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002900 | 2026-04-20 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 87.5 | 262.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002901 | 2026-04-20 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002902 | 2026-04-20 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002903 | 2026-04-20 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 21.5 | 90 | 1935 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002904 | 2026-04-20 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002905 | 2026-04-20 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10.5 | 90 | 945 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002906 | 2026-04-20 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 19.5 | 60 | 1170 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002907 | 2026-04-20 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002908 | 2026-04-20 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 13 | 60 | 780 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002909 | 2026-04-27 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002910 | 2026-04-27 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002911 | 2026-04-27 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002912 | 2026-04-27 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002913 | 2026-04-27 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002914 | 2026-04-27 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002915 | 2026-04-27 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002916 | 2026-04-27 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002917 | 2026-04-27 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002918 | 2026-04-27 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002919 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002920 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002921 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002922 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002923 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002924 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002925 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002926 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002927 | 2026-04-27 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002928 | 2026-04-27 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002929 | 2026-04-27 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002930 | 2026-04-27 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002931 | 2026-04-27 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002932 | 2026-04-27 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002933 | 2026-04-27 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002934 | 2026-04-27 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002935 | 2026-04-27 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002936 | 2026-04-27 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002937 | 2026-04-27 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002938 | 2026-04-27 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29 | 62.5 | 1812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002939 | 2026-04-27 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002940 | 2026-04-27 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002941 | 2026-04-27 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002942 | 2026-04-27 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002943 | 2026-04-27 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002944 | 2026-04-27 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002945 | 2026-04-27 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002946 | 2026-04-27 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002947 | 2026-04-27 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002948 | 2026-04-27 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002949 | 2026-04-27 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002950 | 2026-04-27 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002951 | 2026-04-27 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002952 | 2026-04-27 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002953 | 2026-04-27 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002954 | 2026-04-27 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002955 | 2026-04-27 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002956 | 2026-04-27 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002957 | 2026-04-27 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002958 | 2026-04-27 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002959 | 2026-04-27 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002960 | 2026-04-27 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002961 | 2026-04-27 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002962 | 2026-04-27 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002963 | 2026-04-27 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002964 | 2026-04-27 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 157.5 | 5040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002965 | 2026-04-27 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002966 | 2026-04-27 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002967 | 2026-04-27 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002968 | 2026-04-27 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002969 | 2026-04-27 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 162.5 | 5200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002970 | 2026-04-27 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002971 | 2026-04-27 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002972 | 2026-04-27 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002973 | 2026-04-27 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002974 | 2026-04-27 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002975 | 2026-04-27 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002976 | 2026-04-27 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002977 | 2026-04-27 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002978 | 2026-04-27 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002979 | 2026-04-27 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002980 | 2026-04-27 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002981 | 2026-04-27 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002982 | 2026-04-27 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002983 | 2026-04-27 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002984 | 2026-04-27 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002985 | 2026-04-27 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 105 | 1890 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002986 | 2026-04-27 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002987 | 2026-04-27 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002988 | 2026-04-27 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002989 | 2026-04-27 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002990 | 2026-04-27 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002991 | 2026-04-27 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 19 | 82.5 | 1567.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002992 | 2026-04-27 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002993 | 2026-04-27 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002994 | 2026-04-27 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002995 | 2026-04-27 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 5 | 67.5 | 337.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002996 | 2026-04-27 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4 | 67.5 | 270 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002997 | 2026-04-27 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002998 | 2026-04-27 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-002999 | 2026-04-27 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003000 | 2026-04-27 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003001 | 2026-04-27 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003002 | 2026-04-27 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003003 | 2026-04-27 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003004 | 2026-04-27 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003005 | 2026-04-27 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003006 | 2026-04-27 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003007 | 2026-04-27 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 11.5 | 55 | 632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003008 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003009 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003010 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003011 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003012 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003013 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003014 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003015 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003016 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003017 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 65 | 455 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003018 | 2026-04-27 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003019 | 2026-04-27 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003020 | 2026-04-27 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003021 | 2026-04-27 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 120 | 840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003022 | 2026-04-27 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 30 | 100 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003023 | 2026-04-27 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003024 | 2026-04-27 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003025 | 2026-04-27 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 31 | 100 | 3100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003026 | 2026-04-27 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 100 | 900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003027 | 2026-04-27 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 27 | 75 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003028 | 2026-04-27 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003029 | 2026-04-27 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 33.5 | 67.5 | 2261.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003030 | 2026-04-27 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 67.5 | 438.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003031 | 2026-04-27 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003032 | 2026-04-27 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 67.5 | 270 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003033 | 2026-04-27 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003034 | 2026-04-27 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 29.5 | 102.5 | 3023.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003035 | 2026-04-27 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003036 | 2026-04-27 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 102.5 | 307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003037 | 2026-04-27 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 17.5 | 77.5 | 1356.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003038 | 2026-04-27 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 77.5 | 387.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003039 | 2026-04-27 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003040 | 2026-04-27 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 27 | 65 | 1755 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003041 | 2026-04-27 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003042 | 2026-04-27 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 65 | 97.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003043 | 2026-04-27 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003044 | 2026-04-27 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003045 | 2026-04-27 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003046 | 2026-04-27 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003047 | 2026-04-27 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003048 | 2026-04-27 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003049 | 2026-04-27 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003050 | 2026-04-27 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 18 | 95 | 1710 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003051 | 2026-04-27 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003052 | 2026-04-27 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003053 | 2026-04-27 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 95 | 190 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003054 | 2026-04-27 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 23.5 | 60 | 1410 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003055 | 2026-04-27 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003056 | 2026-04-27 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003057 | 2026-04-27 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003058 | 2026-04-27 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003059 | 2026-04-27 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 21.5 | 62.5 | 1343.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003060 | 2026-04-27 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003061 | 2026-04-27 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003062 | 2026-04-27 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 14.5 | 62.5 | 906.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003063 | 2026-04-27 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 13 | 62.5 | 812.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003064 | 2026-04-27 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 62.5 | 781.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003065 | 2026-04-27 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003066 | 2026-04-27 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 36 | 105 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003067 | 2026-04-27 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003068 | 2026-04-27 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003069 | 2026-04-27 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003070 | 2026-04-27 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003071 | 2026-04-27 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003072 | 2026-04-27 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003073 | 2026-04-27 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003074 | 2026-04-27 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 120 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003075 | 2026-04-27 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003076 | 2026-04-27 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 120 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003077 | 2026-04-27 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 16.5 | 100 | 1650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003078 | 2026-04-27 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 100 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003079 | 2026-04-27 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003080 | 2026-04-27 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003081 | 2026-04-27 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 90 | 1935 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003082 | 2026-04-27 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003083 | 2026-04-27 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003084 | 2026-04-27 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 67.5 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003085 | 2026-04-27 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003086 | 2026-04-27 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003087 | 2026-04-27 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 75 | 1575 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003088 | 2026-04-27 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 75 | 1650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003089 | 2026-04-27 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003090 | 2026-04-27 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 75 | 712.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003091 | 2026-04-27 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003092 | 2026-04-27 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003093 | 2026-04-27 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003094 | 2026-04-27 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 97.5 | 195 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003095 | 2026-04-27 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 33 | 75 | 2475 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003096 | 2026-04-27 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 75 | 525 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003097 | 2026-04-27 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003098 | 2026-04-27 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003099 | 2026-04-27 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003100 | 2026-04-27 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003101 | 2026-04-27 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003102 | 2026-04-27 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 115 | 1265 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003103 | 2026-04-27 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003104 | 2026-04-27 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003105 | 2026-04-27 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003106 | 2026-04-27 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 7 | 87.5 | 612.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003107 | 2026-04-27 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 87.5 | 393.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003108 | 2026-04-27 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 87.5 | 87.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003109 | 2026-04-27 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003110 | 2026-04-27 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003111 | 2026-04-27 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003112 | 2026-04-27 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003113 | 2026-04-27 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003114 | 2026-04-27 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 60 | 660 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003115 | 2026-04-27 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 5 | 60 | 300 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003116 | 2026-04-27 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003117 | 2026-04-27 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003118 | 2026-04-27 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003119 | 2026-05-04 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 14 | 97.5 | 1365 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003120 | 2026-05-04 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003121 | 2026-05-04 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003122 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003123 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003124 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003125 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003126 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003127 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003128 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003129 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003130 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003131 | 2026-05-04 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003132 | 2026-05-04 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 80 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003133 | 2026-05-04 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003134 | 2026-05-04 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003135 | 2026-05-04 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003136 | 2026-05-04 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003137 | 2026-05-04 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003138 | 2026-05-04 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003139 | 2026-05-04 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003140 | 2026-05-04 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003141 | 2026-05-04 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003142 | 2026-05-04 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003143 | 2026-05-04 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003144 | 2026-05-04 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 22 | 62.5 | 1375 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003145 | 2026-05-04 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003146 | 2026-05-04 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003147 | 2026-05-04 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003148 | 2026-05-04 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003149 | 2026-05-04 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003150 | 2026-05-04 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003151 | 2026-05-04 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003152 | 2026-05-04 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003153 | 2026-05-04 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003154 | 2026-05-04 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003155 | 2026-05-04 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003156 | 2026-05-04 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003157 | 2026-05-04 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003158 | 2026-05-04 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 55 | 1485 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003159 | 2026-05-04 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003160 | 2026-05-04 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003161 | 2026-05-04 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003162 | 2026-05-04 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003163 | 2026-05-04 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003164 | 2026-05-04 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 29 | 187.5 | 5437.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003165 | 2026-05-04 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003166 | 2026-05-04 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003167 | 2026-05-04 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003168 | 2026-05-04 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003169 | 2026-05-04 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003170 | 2026-05-04 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003171 | 2026-05-04 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003172 | 2026-05-04 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003173 | 2026-05-04 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003174 | 2026-05-04 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003175 | 2026-05-04 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003176 | 2026-05-04 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27 | 157.5 | 4252.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003177 | 2026-05-04 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003178 | 2026-05-04 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003179 | 2026-05-04 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003180 | 2026-05-04 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003181 | 2026-05-04 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003182 | 2026-05-04 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003183 | 2026-05-04 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24.5 | 162.5 | 3981.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003184 | 2026-05-04 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003185 | 2026-05-04 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003186 | 2026-05-04 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003187 | 2026-05-04 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003188 | 2026-05-04 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003189 | 2026-05-04 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003190 | 2026-05-04 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 13.5 | 150 | 2025 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003191 | 2026-05-04 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003192 | 2026-05-04 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003193 | 2026-05-04 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003194 | 2026-05-04 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003195 | 2026-05-04 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003196 | 2026-05-04 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003197 | 2026-05-04 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003198 | 2026-05-04 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003199 | 2026-05-04 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003200 | 2026-05-04 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003201 | 2026-05-04 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003202 | 2026-05-04 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003203 | 2026-05-04 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 105 | 1785 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003204 | 2026-05-04 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003205 | 2026-05-04 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 13.5 | 85 | 1147.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003206 | 2026-05-04 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 12 | 85 | 1020 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003207 | 2026-05-04 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4.5 | 85 | 382.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003208 | 2026-05-04 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 85 | 170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003209 | 2026-05-04 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003210 | 2026-05-04 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 18 | 82.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003211 | 2026-05-04 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 14 | 82.5 | 1155 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003212 | 2026-05-04 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003213 | 2026-05-04 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003214 | 2026-05-04 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003215 | 2026-05-04 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003216 | 2026-05-04 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003217 | 2026-05-04 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003218 | 2026-05-04 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 15 | 67.5 | 1012.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003219 | 2026-05-04 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 10 | 67.5 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003220 | 2026-05-04 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 6.5 | 67.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003221 | 2026-05-04 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003222 | 2026-05-04 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003223 | 2026-05-04 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003224 | 2026-05-04 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003225 | 2026-05-04 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003226 | 2026-05-04 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003227 | 2026-05-04 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003228 | 2026-05-04 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003229 | 2026-05-04 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003230 | 2026-05-04 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003231 | 2026-05-04 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003232 | 2026-05-04 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003233 | 2026-05-04 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 5.5 | 55 | 302.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003234 | 2026-05-04 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003235 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003236 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003237 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003238 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003239 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003240 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003241 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003242 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003243 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003244 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003245 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 65 | 1105 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003246 | 2026-05-04 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003247 | 2026-05-04 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 18 | 120 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003248 | 2026-05-04 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 120 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003249 | 2026-05-04 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003250 | 2026-05-04 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003251 | 2026-05-04 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 23 | 100 | 2300 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003252 | 2026-05-04 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003253 | 2026-05-04 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003254 | 2026-05-04 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003255 | 2026-05-04 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 25.5 | 100 | 2550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003256 | 2026-05-04 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003257 | 2026-05-04 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003258 | 2026-05-04 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 22.5 | 75 | 1687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003259 | 2026-05-04 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9.5 | 75 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003260 | 2026-05-04 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003261 | 2026-05-04 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 25 | 67.5 | 1687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003262 | 2026-05-04 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 67.5 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003263 | 2026-05-04 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003264 | 2026-05-04 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 22 | 67.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003265 | 2026-05-04 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9.5 | 67.5 | 641.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003266 | 2026-05-04 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003267 | 2026-05-04 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003268 | 2026-05-04 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 25.5 | 102.5 | 2613.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003269 | 2026-05-04 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 102.5 | 666.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003270 | 2026-05-04 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003271 | 2026-05-04 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 25.5 | 77.5 | 1976.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003272 | 2026-05-04 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 77.5 | 465 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003273 | 2026-05-04 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 77.5 | 38.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003274 | 2026-05-04 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003275 | 2026-05-04 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 22 | 65 | 1430 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003276 | 2026-05-04 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 65 | 650 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003277 | 2026-05-04 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003278 | 2026-05-04 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 12.5 | 117.5 | 1468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003279 | 2026-05-04 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 13.5 | 117.5 | 1586.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003280 | 2026-05-04 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003281 | 2026-05-04 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003282 | 2026-05-04 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 12.5 | 82.5 | 1031.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003283 | 2026-05-04 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 13 | 82.5 | 1072.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003284 | 2026-05-04 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 82.5 | 536.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003285 | 2026-05-04 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003286 | 2026-05-04 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 16 | 95 | 1520 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003287 | 2026-05-04 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9 | 95 | 855 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003288 | 2026-05-04 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6.5 | 95 | 617.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003289 | 2026-05-04 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003290 | 2026-05-04 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003291 | 2026-05-04 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 60 | 270 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003292 | 2026-05-04 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 3.5 | 60 | 210 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003293 | 2026-05-04 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003294 | 2026-05-04 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003295 | 2026-05-04 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16 | 90 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003296 | 2026-05-04 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003297 | 2026-05-04 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 6.5 | 90 | 585 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003298 | 2026-05-04 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003299 | 2026-05-04 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003300 | 2026-05-04 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 17 | 62.5 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003301 | 2026-05-04 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 8.5 | 62.5 | 531.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003302 | 2026-05-04 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 62.5 | 406.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003303 | 2026-05-04 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003304 | 2026-05-04 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 13.5 | 62.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003305 | 2026-05-04 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 62.5 | 625 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003306 | 2026-05-04 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 62.5 | 531.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003307 | 2026-05-04 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003308 | 2026-05-04 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003309 | 2026-05-04 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003310 | 2026-05-04 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003311 | 2026-05-04 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003312 | 2026-05-04 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003313 | 2026-05-04 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003314 | 2026-05-04 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25.5 | 72.5 | 1848.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003315 | 2026-05-04 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003316 | 2026-05-04 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003317 | 2026-05-04 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003318 | 2026-05-04 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003319 | 2026-05-04 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003320 | 2026-05-04 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003321 | 2026-05-04 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003322 | 2026-05-04 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 18.5 | 120 | 2220 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003323 | 2026-05-04 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9 | 120 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003324 | 2026-05-04 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003325 | 2026-05-04 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003326 | 2026-05-04 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003327 | 2026-05-04 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 23.5 | 100 | 2350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003328 | 2026-05-04 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 100 | 850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003329 | 2026-05-04 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003330 | 2026-05-04 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 90 | 1440 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003331 | 2026-05-04 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 90 | 1440 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003332 | 2026-05-04 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003333 | 2026-05-04 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16.5 | 67.5 | 1113.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003334 | 2026-05-04 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003335 | 2026-05-04 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 67.5 | 472.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003336 | 2026-05-04 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003337 | 2026-05-04 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 14.5 | 75 | 1087.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003338 | 2026-05-04 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 15.5 | 75 | 1162.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003339 | 2026-05-04 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003340 | 2026-05-04 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003341 | 2026-05-04 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 17.5 | 75 | 1312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003342 | 2026-05-04 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 75 | 525 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003343 | 2026-05-04 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 75 | 487.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003344 | 2026-05-04 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003345 | 2026-05-04 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003346 | 2026-05-04 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 97.5 | 1462.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003347 | 2026-05-04 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 97.5 | 585 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003348 | 2026-05-04 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 10.5 | 97.5 | 1023.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003349 | 2026-05-04 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003350 | 2026-05-04 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003351 | 2026-05-04 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12 | 75 | 900 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003352 | 2026-05-04 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 75 | 262.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003353 | 2026-05-04 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003354 | 2026-05-04 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003355 | 2026-05-04 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003356 | 2026-05-04 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 67.5 | 978.75 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003357 | 2026-05-04 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 9 | 67.5 | 607.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003358 | 2026-05-04 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 7 | 67.5 | 472.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003359 | 2026-05-04 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003360 | 2026-05-04 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 115 | 1667.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003361 | 2026-05-04 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 10.5 | 115 | 1207.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003362 | 2026-05-04 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003363 | 2026-05-04 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003364 | 2026-05-04 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003365 | 2026-05-04 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16.5 | 87.5 | 1443.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003366 | 2026-05-04 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9.5 | 87.5 | 831.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003367 | 2026-05-04 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 87.5 | 525 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003368 | 2026-05-04 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003369 | 2026-05-04 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 17 | 90 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003370 | 2026-05-04 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 6 | 90 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003371 | 2026-05-04 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003372 | 2026-05-04 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003373 | 2026-05-04 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 15 | 60 | 900 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003374 | 2026-05-04 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 6 | 60 | 360 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003375 | 2026-05-04 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 10 | 60 | 600 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003376 | 2026-05-04 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003377 | 2026-05-04 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003378 | 2026-05-11 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003379 | 2026-05-11 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003380 | 2026-05-11 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003381 | 2026-05-11 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003382 | 2026-05-11 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003383 | 2026-05-11 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003384 | 2026-05-11 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003385 | 2026-05-11 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003386 | 2026-05-11 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003387 | 2026-05-11 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003388 | 2026-05-11 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003389 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003390 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003391 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003392 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003393 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003394 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003395 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003396 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003397 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003398 | 2026-05-11 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003399 | 2026-05-11 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 19 | 80 | 1520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003400 | 2026-05-11 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003401 | 2026-05-11 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003402 | 2026-05-11 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003403 | 2026-05-11 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003404 | 2026-05-11 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003405 | 2026-05-11 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003406 | 2026-05-11 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003407 | 2026-05-11 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003408 | 2026-05-11 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003409 | 2026-05-11 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003410 | 2026-05-11 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003411 | 2026-05-11 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28.5 | 62.5 | 1781.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003412 | 2026-05-11 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003413 | 2026-05-11 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003414 | 2026-05-11 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003415 | 2026-05-11 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003416 | 2026-05-11 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003417 | 2026-05-11 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003418 | 2026-05-11 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003419 | 2026-05-11 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003420 | 2026-05-11 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003421 | 2026-05-11 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003422 | 2026-05-11 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003423 | 2026-05-11 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 55 | 1677.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003424 | 2026-05-11 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003425 | 2026-05-11 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003426 | 2026-05-11 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003427 | 2026-05-11 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003428 | 2026-05-11 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 22 | 187.5 | 4125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003429 | 2026-05-11 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003430 | 2026-05-11 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003431 | 2026-05-11 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003432 | 2026-05-11 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003433 | 2026-05-11 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003434 | 2026-05-11 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003435 | 2026-05-11 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003436 | 2026-05-11 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003437 | 2026-05-11 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003438 | 2026-05-11 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003439 | 2026-05-11 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003440 | 2026-05-11 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 157.5 | 4725 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003441 | 2026-05-11 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003442 | 2026-05-11 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003443 | 2026-05-11 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003444 | 2026-05-11 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003445 | 2026-05-11 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003446 | 2026-05-11 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003447 | 2026-05-11 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003448 | 2026-05-11 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003449 | 2026-05-11 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003450 | 2026-05-11 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003451 | 2026-05-11 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003452 | 2026-05-11 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 13.5 | 150 | 2025 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003453 | 2026-05-11 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003454 | 2026-05-11 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003455 | 2026-05-11 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003456 | 2026-05-11 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003457 | 2026-05-11 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003458 | 2026-05-11 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003459 | 2026-05-11 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003460 | 2026-05-11 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003461 | 2026-05-11 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003462 | 2026-05-11 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003463 | 2026-05-11 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003464 | 2026-05-11 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003465 | 2026-05-11 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003466 | 2026-05-11 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003467 | 2026-05-11 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003468 | 2026-05-11 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 85 | 42.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003469 | 2026-05-11 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003470 | 2026-05-11 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003471 | 2026-05-11 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003472 | 2026-05-11 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003473 | 2026-05-11 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003474 | 2026-05-11 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003475 | 2026-05-11 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003476 | 2026-05-11 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003477 | 2026-05-11 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003478 | 2026-05-11 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003479 | 2026-05-11 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003480 | 2026-05-11 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003481 | 2026-05-11 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003482 | 2026-05-11 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003483 | 2026-05-11 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003484 | 2026-05-11 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003485 | 2026-05-11 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003486 | 2026-05-11 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 55 | 440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003487 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003488 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003489 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003490 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003491 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003492 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003493 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003494 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003495 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003496 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003497 | 2026-05-11 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003498 | 2026-05-11 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 26 | 120 | 3120 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003499 | 2026-05-11 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003500 | 2026-05-11 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 120 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003501 | 2026-05-11 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 30.5 | 100 | 3050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003502 | 2026-05-11 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003503 | 2026-05-11 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003504 | 2026-05-11 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 31.5 | 100 | 3150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003505 | 2026-05-11 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003506 | 2026-05-11 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003507 | 2026-05-11 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003508 | 2026-05-11 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003509 | 2026-05-11 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003510 | 2026-05-11 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003511 | 2026-05-11 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003512 | 2026-05-11 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4.5 | 67.5 | 303.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003513 | 2026-05-11 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003514 | 2026-05-11 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003515 | 2026-05-11 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 26 | 102.5 | 2665 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003516 | 2026-05-11 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6 | 102.5 | 615 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003517 | 2026-05-11 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003518 | 2026-05-11 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30.5 | 77.5 | 2363.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003519 | 2026-05-11 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 77.5 | 658.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003520 | 2026-05-11 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 77.5 | 77.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003521 | 2026-05-11 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003522 | 2026-05-11 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003523 | 2026-05-11 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003524 | 2026-05-11 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003525 | 2026-05-11 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003526 | 2026-05-11 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 17.5 | 82.5 | 1443.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003527 | 2026-05-11 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 82.5 | 1196.25 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003528 | 2026-05-11 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 82.5 | 701.25 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003529 | 2026-05-11 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19 | 95 | 1805 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003530 | 2026-05-11 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 95 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003531 | 2026-05-11 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003532 | 2026-05-11 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003533 | 2026-05-11 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 24.5 | 60 | 1470 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003534 | 2026-05-11 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003535 | 2026-05-11 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003536 | 2026-05-11 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 90 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003537 | 2026-05-11 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003538 | 2026-05-11 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003539 | 2026-05-11 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003540 | 2026-05-11 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003541 | 2026-05-11 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003542 | 2026-05-11 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 17 | 62.5 | 1062.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003543 | 2026-05-11 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003544 | 2026-05-11 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003545 | 2026-05-11 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003546 | 2026-05-11 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003547 | 2026-05-11 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003548 | 2026-05-11 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003549 | 2026-05-11 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003550 | 2026-05-11 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003551 | 2026-05-11 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003552 | 2026-05-11 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003553 | 2026-05-11 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003554 | 2026-05-11 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 24.5 | 120 | 2940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003555 | 2026-05-11 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 120 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003556 | 2026-05-11 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003557 | 2026-05-11 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 27 | 100 | 2700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003558 | 2026-05-11 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003559 | 2026-05-11 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003560 | 2026-05-11 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21.5 | 90 | 1935 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003561 | 2026-05-11 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003562 | 2026-05-11 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003563 | 2026-05-11 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003564 | 2026-05-11 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 67.5 | 472.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003565 | 2026-05-11 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003566 | 2026-05-11 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 75 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003567 | 2026-05-11 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003568 | 2026-05-11 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003569 | 2026-05-11 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003570 | 2026-05-11 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7 | 75 | 525 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003571 | 2026-05-11 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003572 | 2026-05-11 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003573 | 2026-05-11 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21 | 97.5 | 2047.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003574 | 2026-05-11 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003575 | 2026-05-11 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 11 | 97.5 | 1072.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003576 | 2026-05-11 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003577 | 2026-05-11 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003578 | 2026-05-11 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003579 | 2026-05-11 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003580 | 2026-05-11 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003581 | 2026-05-11 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21.5 | 115 | 2472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003582 | 2026-05-11 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003583 | 2026-05-11 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003584 | 2026-05-11 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003585 | 2026-05-11 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003586 | 2026-05-11 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP02 | Architecture, detailed design and backlog refinement | Yes | 4 | 87.5 | 350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003587 | 2026-05-11 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003588 | 2026-05-11 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003589 | 2026-05-11 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16 | 90 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003590 | 2026-05-11 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 6.5 | 90 | 585 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003591 | 2026-05-11 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 90 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003592 | 2026-05-11 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003593 | 2026-05-11 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003594 | 2026-05-11 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 3 | 60 | 180 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003595 | 2026-05-11 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4.5 | 60 | 270 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003596 | 2026-05-11 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003597 | 2026-05-11 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003598 | 2026-05-18 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003599 | 2026-05-18 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 23.5 | 97.5 | 2291.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003600 | 2026-05-18 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003601 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003602 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003603 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003604 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003605 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003606 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003607 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003608 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003609 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003610 | 2026-05-18 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003611 | 2026-05-18 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003612 | 2026-05-18 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003613 | 2026-05-18 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003614 | 2026-05-18 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003615 | 2026-05-18 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003616 | 2026-05-18 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003617 | 2026-05-18 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003618 | 2026-05-18 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003619 | 2026-05-18 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003620 | 2026-05-18 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003621 | 2026-05-18 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003622 | 2026-05-18 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003623 | 2026-05-18 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003624 | 2026-05-18 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003625 | 2026-05-18 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003626 | 2026-05-18 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003627 | 2026-05-18 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003628 | 2026-05-18 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003629 | 2026-05-18 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003630 | 2026-05-18 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003631 | 2026-05-18 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003632 | 2026-05-18 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003633 | 2026-05-18 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003634 | 2026-05-18 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003635 | 2026-05-18 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003636 | 2026-05-18 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003637 | 2026-05-18 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003638 | 2026-05-18 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003639 | 2026-05-18 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003640 | 2026-05-18 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 28.5 | 187.5 | 5343.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003641 | 2026-05-18 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003642 | 2026-05-18 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003643 | 2026-05-18 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003644 | 2026-05-18 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003645 | 2026-05-18 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003646 | 2026-05-18 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003647 | 2026-05-18 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003648 | 2026-05-18 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003649 | 2026-05-18 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003650 | 2026-05-18 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003651 | 2026-05-18 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003652 | 2026-05-18 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31.5 | 157.5 | 4961.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003653 | 2026-05-18 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003654 | 2026-05-18 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003655 | 2026-05-18 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003656 | 2026-05-18 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003657 | 2026-05-18 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003658 | 2026-05-18 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003659 | 2026-05-18 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003660 | 2026-05-18 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003661 | 2026-05-18 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003662 | 2026-05-18 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003663 | 2026-05-18 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003664 | 2026-05-18 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003665 | 2026-05-18 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003666 | 2026-05-18 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003667 | 2026-05-18 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003668 | 2026-05-18 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003669 | 2026-05-18 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003670 | 2026-05-18 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003671 | 2026-05-18 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003672 | 2026-05-18 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003673 | 2026-05-18 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003674 | 2026-05-18 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003675 | 2026-05-18 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003676 | 2026-05-18 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 7 | 85 | 595 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003677 | 2026-05-18 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003678 | 2026-05-18 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 2.5 | 85 | 212.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003679 | 2026-05-18 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003680 | 2026-05-18 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003681 | 2026-05-18 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003682 | 2026-05-18 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003683 | 2026-05-18 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003684 | 2026-05-18 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003685 | 2026-05-18 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003686 | 2026-05-18 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003687 | 2026-05-18 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003688 | 2026-05-18 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003689 | 2026-05-18 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003690 | 2026-05-18 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003691 | 2026-05-18 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003692 | 2026-05-18 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003693 | 2026-05-18 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003694 | 2026-05-18 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003695 | 2026-05-18 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003696 | 2026-05-18 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003697 | 2026-05-18 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003698 | 2026-05-18 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003699 | 2026-05-18 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003700 | 2026-05-18 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7.5 | 55 | 412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003701 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003702 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003703 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003704 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003705 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003706 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003707 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003708 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003709 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003710 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003711 | 2026-05-18 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003712 | 2026-05-18 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003713 | 2026-05-18 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003714 | 2026-05-18 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 120 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003715 | 2026-05-18 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 26 | 100 | 2600 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003716 | 2026-05-18 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 8.5 | 100 | 850 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003717 | 2026-05-18 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 100 | 550 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003718 | 2026-05-18 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003719 | 2026-05-18 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003720 | 2026-05-18 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003721 | 2026-05-18 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003722 | 2026-05-18 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003723 | 2026-05-18 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003724 | 2026-05-18 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003725 | 2026-05-18 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003726 | 2026-05-18 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003727 | 2026-05-18 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 27.5 | 67.5 | 1856.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003728 | 2026-05-18 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 67.5 | 843.75 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003729 | 2026-05-18 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 13 | 102.5 | 1332.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003730 | 2026-05-18 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 3 | 102.5 | 307.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003731 | 2026-05-18 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003732 | 2026-05-18 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 30 | 77.5 | 2325 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003733 | 2026-05-18 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 77.5 | 620 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003734 | 2026-05-18 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 77.5 | 155 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003735 | 2026-05-18 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003736 | 2026-05-18 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003737 | 2026-05-18 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003738 | 2026-05-18 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003739 | 2026-05-18 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003740 | 2026-05-18 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 117.5 | 411.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003741 | 2026-05-18 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003742 | 2026-05-18 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003743 | 2026-05-18 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003744 | 2026-05-18 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19 | 95 | 1805 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003745 | 2026-05-18 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13 | 95 | 1235 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003746 | 2026-05-18 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003747 | 2026-05-18 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003748 | 2026-05-18 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003749 | 2026-05-18 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003750 | 2026-05-18 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003751 | 2026-05-18 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003752 | 2026-05-18 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003753 | 2026-05-18 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003754 | 2026-05-18 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003755 | 2026-05-18 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003756 | 2026-05-18 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003757 | 2026-05-18 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003758 | 2026-05-18 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003759 | 2026-05-18 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003760 | 2026-05-18 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003761 | 2026-05-18 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 105 | 262.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003762 | 2026-05-18 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 105 | 262.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003763 | 2026-05-18 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 19 | 105 | 1995 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003764 | 2026-05-18 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003765 | 2026-05-18 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003766 | 2026-05-18 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003767 | 2026-05-18 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003768 | 2026-05-18 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003769 | 2026-05-18 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003770 | 2026-05-18 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003771 | 2026-05-18 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003772 | 2026-05-18 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 120 | 1560 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003773 | 2026-05-18 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003774 | 2026-05-18 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 29 | 100 | 2900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003775 | 2026-05-18 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003776 | 2026-05-18 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 90 | 1890 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003777 | 2026-05-18 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 19 | 90 | 1710 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003778 | 2026-05-18 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003779 | 2026-05-18 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003780 | 2026-05-18 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 67.5 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003781 | 2026-05-18 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003782 | 2026-05-18 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003783 | 2026-05-18 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003784 | 2026-05-18 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003785 | 2026-05-18 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 23.5 | 75 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003786 | 2026-05-18 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003787 | 2026-05-18 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003788 | 2026-05-18 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003789 | 2026-05-18 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003790 | 2026-05-18 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003791 | 2026-05-18 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003792 | 2026-05-18 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003793 | 2026-05-18 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003794 | 2026-05-18 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003795 | 2026-05-18 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003796 | 2026-05-18 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 4.5 | 67.5 | 303.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003797 | 2026-05-18 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003798 | 2026-05-18 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003799 | 2026-05-18 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 115 | 1437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003800 | 2026-05-18 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003801 | 2026-05-18 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18.5 | 87.5 | 1618.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003802 | 2026-05-18 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003803 | 2026-05-18 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003804 | 2026-05-18 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 87.5 | 131.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003805 | 2026-05-18 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003806 | 2026-05-18 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003807 | 2026-05-18 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 13 | 90 | 1170 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003808 | 2026-05-18 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 19.5 | 60 | 1170 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003809 | 2026-05-18 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 8 | 60 | 480 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003810 | 2026-05-18 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 60 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003811 | 2026-05-25 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003812 | 2026-05-25 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003813 | 2026-05-25 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003814 | 2026-05-25 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003815 | 2026-05-25 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003816 | 2026-05-25 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003817 | 2026-05-25 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003818 | 2026-05-25 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003819 | 2026-05-25 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003820 | 2026-05-25 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003821 | 2026-05-25 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 97.5 | 2632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003822 | 2026-05-25 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003823 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003824 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003825 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003826 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003827 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003828 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003829 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003830 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003831 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003832 | 2026-05-25 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003833 | 2026-05-25 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 80 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003834 | 2026-05-25 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003835 | 2026-05-25 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003836 | 2026-05-25 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003837 | 2026-05-25 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003838 | 2026-05-25 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003839 | 2026-05-25 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003840 | 2026-05-25 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003841 | 2026-05-25 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003842 | 2026-05-25 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003843 | 2026-05-25 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003844 | 2026-05-25 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003845 | 2026-05-25 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 22 | 62.5 | 1375 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003846 | 2026-05-25 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003847 | 2026-05-25 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003848 | 2026-05-25 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003849 | 2026-05-25 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003850 | 2026-05-25 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003851 | 2026-05-25 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003852 | 2026-05-25 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003853 | 2026-05-25 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003854 | 2026-05-25 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003855 | 2026-05-25 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003856 | 2026-05-25 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003857 | 2026-05-25 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003858 | 2026-05-25 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003859 | 2026-05-25 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 55 | 1485 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003860 | 2026-05-25 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003861 | 2026-05-25 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003862 | 2026-05-25 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003863 | 2026-05-25 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003864 | 2026-05-25 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003865 | 2026-05-25 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 28 | 187.5 | 5250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003866 | 2026-05-25 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003867 | 2026-05-25 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003868 | 2026-05-25 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003869 | 2026-05-25 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003870 | 2026-05-25 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003871 | 2026-05-25 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003872 | 2026-05-25 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003873 | 2026-05-25 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003874 | 2026-05-25 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003875 | 2026-05-25 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003876 | 2026-05-25 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003877 | 2026-05-25 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27 | 157.5 | 4252.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003878 | 2026-05-25 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003879 | 2026-05-25 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003880 | 2026-05-25 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003881 | 2026-05-25 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003882 | 2026-05-25 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003883 | 2026-05-25 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003884 | 2026-05-25 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24.5 | 162.5 | 3981.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003885 | 2026-05-25 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003886 | 2026-05-25 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003887 | 2026-05-25 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003888 | 2026-05-25 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003889 | 2026-05-25 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003890 | 2026-05-25 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003891 | 2026-05-25 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24.5 | 150 | 3675 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003892 | 2026-05-25 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003893 | 2026-05-25 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003894 | 2026-05-25 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003895 | 2026-05-25 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003896 | 2026-05-25 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003897 | 2026-05-25 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003898 | 2026-05-25 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003899 | 2026-05-25 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003900 | 2026-05-25 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003901 | 2026-05-25 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003902 | 2026-05-25 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003903 | 2026-05-25 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 105 | 1785 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003904 | 2026-05-25 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003905 | 2026-05-25 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 14 | 85 | 1190 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003906 | 2026-05-25 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 11.5 | 85 | 977.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003907 | 2026-05-25 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4.5 | 85 | 382.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003908 | 2026-05-25 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 85 | 170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003909 | 2026-05-25 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003910 | 2026-05-25 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003911 | 2026-05-25 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 13.5 | 82.5 | 1113.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003912 | 2026-05-25 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003913 | 2026-05-25 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003914 | 2026-05-25 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 16 | 67.5 | 1080 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003915 | 2026-05-25 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 14.5 | 67.5 | 978.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003916 | 2026-05-25 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003917 | 2026-05-25 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003918 | 2026-05-25 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 14.5 | 67.5 | 978.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003919 | 2026-05-25 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003920 | 2026-05-25 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 6.5 | 67.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003921 | 2026-05-25 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003922 | 2026-05-25 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003923 | 2026-05-25 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003924 | 2026-05-25 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003925 | 2026-05-25 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003926 | 2026-05-25 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003927 | 2026-05-25 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003928 | 2026-05-25 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003929 | 2026-05-25 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003930 | 2026-05-25 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003931 | 2026-05-25 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003932 | 2026-05-25 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003933 | 2026-05-25 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 55 | 385 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003934 | 2026-05-25 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003935 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003936 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003937 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003938 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003939 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003940 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003941 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003942 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003943 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003944 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003945 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16.5 | 65 | 1072.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003946 | 2026-05-25 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003947 | 2026-05-25 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20.5 | 120 | 2460 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003948 | 2026-05-25 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 10 | 120 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003949 | 2026-05-25 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003950 | 2026-05-25 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003951 | 2026-05-25 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 24 | 100 | 2400 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003952 | 2026-05-25 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 6 | 100 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003953 | 2026-05-25 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 100 | 200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003954 | 2026-05-25 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003955 | 2026-05-25 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 24 | 100 | 2400 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003956 | 2026-05-25 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003957 | 2026-05-25 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003958 | 2026-05-25 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003959 | 2026-05-25 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003960 | 2026-05-25 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 5 | 75 | 375 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003961 | 2026-05-25 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003962 | 2026-05-25 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003963 | 2026-05-25 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 6 | 67.5 | 405 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003964 | 2026-05-25 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 1.5 | 67.5 | 101.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003965 | 2026-05-25 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003966 | 2026-05-25 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003967 | 2026-05-25 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003968 | 2026-05-25 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 67.5 | 1383.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003969 | 2026-05-25 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 9.5 | 67.5 | 641.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003970 | 2026-05-25 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003971 | 2026-05-25 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003972 | 2026-05-25 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 25.5 | 102.5 | 2613.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003973 | 2026-05-25 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 102.5 | 666.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003974 | 2026-05-25 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003975 | 2026-05-25 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 23.5 | 77.5 | 1821.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003976 | 2026-05-25 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7 | 77.5 | 542.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003977 | 2026-05-25 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 77.5 | 116.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003978 | 2026-05-25 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003979 | 2026-05-25 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 5.5 | 65 | 357.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003980 | 2026-05-25 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 2.5 | 65 | 162.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003981 | 2026-05-25 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003982 | 2026-05-25 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003983 | 2026-05-25 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 12.5 | 117.5 | 1468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003984 | 2026-05-25 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 13.5 | 117.5 | 1586.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003985 | 2026-05-25 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 117.5 | 763.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003986 | 2026-05-25 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003987 | 2026-05-25 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 12.5 | 82.5 | 1031.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003988 | 2026-05-25 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12.5 | 82.5 | 1031.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003989 | 2026-05-25 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6.5 | 82.5 | 536.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003990 | 2026-05-25 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003991 | 2026-05-25 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003992 | 2026-05-25 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 15.5 | 95 | 1472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003993 | 2026-05-25 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9.5 | 95 | 902.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003994 | 2026-05-25 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7 | 95 | 665 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003995 | 2026-05-25 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003996 | 2026-05-25 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 18 | 60 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003997 | 2026-05-25 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13.5 | 60 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003998 | 2026-05-25 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-003999 | 2026-05-25 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004000 | 2026-05-25 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 16 | 90 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004001 | 2026-05-25 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 9.5 | 90 | 855 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004002 | 2026-05-25 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004003 | 2026-05-25 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004004 | 2026-05-25 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 17 | 62.5 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004005 | 2026-05-25 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004006 | 2026-05-25 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 62.5 | 375 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004007 | 2026-05-25 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004008 | 2026-05-25 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 6.5 | 62.5 | 406.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004009 | 2026-05-25 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 5 | 62.5 | 312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004010 | 2026-05-25 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 4.5 | 62.5 | 281.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004011 | 2026-05-25 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004012 | 2026-05-25 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004013 | 2026-05-25 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004014 | 2026-05-25 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004015 | 2026-05-25 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25 | 105 | 2625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004016 | 2026-05-25 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004017 | 2026-05-25 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004018 | 2026-05-25 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004019 | 2026-05-25 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25.5 | 72.5 | 1848.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004020 | 2026-05-25 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004021 | 2026-05-25 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004022 | 2026-05-25 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004023 | 2026-05-25 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004024 | 2026-05-25 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004025 | 2026-05-25 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004026 | 2026-05-25 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004027 | 2026-05-25 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19.5 | 120 | 2340 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004028 | 2026-05-25 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 9 | 120 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004029 | 2026-05-25 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004030 | 2026-05-25 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004031 | 2026-05-25 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 21 | 100 | 2100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004032 | 2026-05-25 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 10 | 100 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004033 | 2026-05-25 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004034 | 2026-05-25 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004035 | 2026-05-25 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 16 | 90 | 1440 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004036 | 2026-05-25 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16 | 90 | 1440 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004037 | 2026-05-25 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004038 | 2026-05-25 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16 | 67.5 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004039 | 2026-05-25 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 67.5 | 641.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004040 | 2026-05-25 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 67.5 | 438.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004041 | 2026-05-25 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004042 | 2026-05-25 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 15 | 75 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004043 | 2026-05-25 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 16.5 | 75 | 1237.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004044 | 2026-05-25 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004045 | 2026-05-25 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004046 | 2026-05-25 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004047 | 2026-05-25 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 75 | 487.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004048 | 2026-05-25 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 6 | 75 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004049 | 2026-05-25 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004050 | 2026-05-25 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004051 | 2026-05-25 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16 | 97.5 | 1560 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004052 | 2026-05-25 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 97.5 | 585 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004053 | 2026-05-25 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 10 | 97.5 | 975 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004054 | 2026-05-25 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004055 | 2026-05-25 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 26 | 75 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004056 | 2026-05-25 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6 | 75 | 450 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004057 | 2026-05-25 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004058 | 2026-05-25 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16 | 67.5 | 1080 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004059 | 2026-05-25 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10 | 67.5 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004060 | 2026-05-25 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 6 | 67.5 | 405 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004061 | 2026-05-25 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004062 | 2026-05-25 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15.5 | 115 | 1782.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004063 | 2026-05-25 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 10 | 115 | 1150 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004064 | 2026-05-25 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004065 | 2026-05-25 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004066 | 2026-05-25 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 87.5 | 1268.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004067 | 2026-05-25 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9 | 87.5 | 787.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004068 | 2026-05-25 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6 | 87.5 | 525 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004069 | 2026-05-25 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 87.5 | 218.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004070 | 2026-05-25 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004071 | 2026-05-25 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16.5 | 90 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004072 | 2026-05-25 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004073 | 2026-05-25 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004074 | 2026-05-25 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004075 | 2026-05-25 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 16.5 | 60 | 990 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004076 | 2026-05-25 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP03 | Build, configuration and implementation | Yes | 6.5 | 60 | 390 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004077 | 2026-05-25 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004078 | 2026-05-25 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004079 | 2026-05-25 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004080 | 2026-06-01 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004081 | 2026-06-01 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004082 | 2026-06-01 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004083 | 2026-06-01 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004084 | 2026-06-01 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004085 | 2026-06-01 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004086 | 2026-06-01 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004087 | 2026-06-01 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004088 | 2026-06-01 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004089 | 2026-06-01 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004090 | 2026-06-01 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004091 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004092 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004093 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004094 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004095 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004096 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004097 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004098 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004099 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004100 | 2026-06-01 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004101 | 2026-06-01 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004102 | 2026-06-01 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004103 | 2026-06-01 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004104 | 2026-06-01 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004105 | 2026-06-01 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004106 | 2026-06-01 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004107 | 2026-06-01 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004108 | 2026-06-01 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004109 | 2026-06-01 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004110 | 2026-06-01 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004111 | 2026-06-01 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004112 | 2026-06-01 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004113 | 2026-06-01 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004114 | 2026-06-01 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004115 | 2026-06-01 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004116 | 2026-06-01 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004117 | 2026-06-01 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004118 | 2026-06-01 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004119 | 2026-06-01 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004120 | 2026-06-01 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004121 | 2026-06-01 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004122 | 2026-06-01 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004123 | 2026-06-01 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004124 | 2026-06-01 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 55 | 1677.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004125 | 2026-06-01 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004126 | 2026-06-01 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004127 | 2026-06-01 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004128 | 2026-06-01 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004129 | 2026-06-01 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004130 | 2026-06-01 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004131 | 2026-06-01 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004132 | 2026-06-01 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004133 | 2026-06-01 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004134 | 2026-06-01 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004135 | 2026-06-01 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004136 | 2026-06-01 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004137 | 2026-06-01 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004138 | 2026-06-01 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004139 | 2026-06-01 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004140 | 2026-06-01 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31.5 | 157.5 | 4961.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004141 | 2026-06-01 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004142 | 2026-06-01 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004143 | 2026-06-01 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004144 | 2026-06-01 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004145 | 2026-06-01 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004146 | 2026-06-01 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004147 | 2026-06-01 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004148 | 2026-06-01 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004149 | 2026-06-01 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004150 | 2026-06-01 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004151 | 2026-06-01 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004152 | 2026-06-01 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004153 | 2026-06-01 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004154 | 2026-06-01 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004155 | 2026-06-01 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004156 | 2026-06-01 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004157 | 2026-06-01 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004158 | 2026-06-01 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004159 | 2026-06-01 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004160 | 2026-06-01 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004161 | 2026-06-01 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004162 | 2026-06-01 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004163 | 2026-06-01 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004164 | 2026-06-01 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004165 | 2026-06-01 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004166 | 2026-06-01 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004167 | 2026-06-01 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004168 | 2026-06-01 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004169 | 2026-06-01 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004170 | 2026-06-01 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004171 | 2026-06-01 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004172 | 2026-06-01 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004173 | 2026-06-01 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004174 | 2026-06-01 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004175 | 2026-06-01 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6 | 67.5 | 405 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004176 | 2026-06-01 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004177 | 2026-06-01 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004178 | 2026-06-01 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004179 | 2026-06-01 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004180 | 2026-06-01 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004181 | 2026-06-01 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004182 | 2026-06-01 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004183 | 2026-06-01 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004184 | 2026-06-01 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004185 | 2026-06-01 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004186 | 2026-06-01 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 55 | 440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004187 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004188 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004189 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004190 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004191 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004192 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004193 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004194 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004195 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004196 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004197 | 2026-06-01 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004198 | 2026-06-01 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 24 | 120 | 2880 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004199 | 2026-06-01 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 13 | 120 | 1560 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004200 | 2026-06-01 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 120 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004201 | 2026-06-01 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 29 | 100 | 2900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004202 | 2026-06-01 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004203 | 2026-06-01 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004204 | 2026-06-01 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 32 | 100 | 3200 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004205 | 2026-06-01 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 100 | 800 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004206 | 2026-06-01 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 26.5 | 75 | 1987.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004207 | 2026-06-01 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004208 | 2026-06-01 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004209 | 2026-06-01 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 31.5 | 67.5 | 2126.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004210 | 2026-06-01 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004211 | 2026-06-01 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004212 | 2026-06-01 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004213 | 2026-06-01 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004214 | 2026-06-01 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 102.5 | 3331.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004215 | 2026-06-01 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004216 | 2026-06-01 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 33 | 77.5 | 2557.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004217 | 2026-06-01 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7 | 77.5 | 542.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004218 | 2026-06-01 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 29.5 | 65 | 1917.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004219 | 2026-06-01 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 10.5 | 65 | 682.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004220 | 2026-06-01 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004221 | 2026-06-01 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004222 | 2026-06-01 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004223 | 2026-06-01 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 117.5 | 293.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004224 | 2026-06-01 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 17.5 | 82.5 | 1443.75 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004225 | 2026-06-01 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004226 | 2026-06-01 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 82.5 | 660 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004227 | 2026-06-01 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004228 | 2026-06-01 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004229 | 2026-06-01 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004230 | 2026-06-01 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 23.5 | 60 | 1410 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004231 | 2026-06-01 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004232 | 2026-06-01 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004233 | 2026-06-01 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004234 | 2026-06-01 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004235 | 2026-06-01 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004236 | 2026-06-01 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004237 | 2026-06-01 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12.5 | 62.5 | 781.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004238 | 2026-06-01 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 7 | 62.5 | 437.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004239 | 2026-06-01 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004240 | 2026-06-01 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15 | 62.5 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004241 | 2026-06-01 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004242 | 2026-06-01 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004243 | 2026-06-01 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004244 | 2026-06-01 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004245 | 2026-06-01 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004246 | 2026-06-01 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004247 | 2026-06-01 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004248 | 2026-06-01 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004249 | 2026-06-01 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004250 | 2026-06-01 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004251 | 2026-06-01 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 55 | 880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004252 | 2026-06-01 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004253 | 2026-06-01 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 67.5 | 1080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004254 | 2026-06-01 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004255 | 2026-06-01 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 15.5 | 120 | 1860 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004256 | 2026-06-01 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 120 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004257 | 2026-06-01 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 2.5 | 120 | 300 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004258 | 2026-06-01 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004259 | 2026-06-01 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004260 | 2026-06-01 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 100 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004261 | 2026-06-01 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004262 | 2026-06-01 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004263 | 2026-06-01 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004264 | 2026-06-01 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004265 | 2026-06-01 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004266 | 2026-06-01 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 13 | 67.5 | 877.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004267 | 2026-06-01 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004268 | 2026-06-01 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 18 | 75 | 1350 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004269 | 2026-06-01 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 21 | 75 | 1575 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004270 | 2026-06-01 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 9.5 | 75 | 712.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004271 | 2026-06-01 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 75 | 262.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004272 | 2026-06-01 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP01 | Discovery workshops, requirements and delivery planning | Yes | 3 | 75 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004273 | 2026-06-01 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004274 | 2026-06-01 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004275 | 2026-06-01 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004276 | 2026-06-01 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 97.5 | 1121.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004277 | 2026-06-01 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 30.5 | 75 | 2287.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004278 | 2026-06-01 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004279 | 2026-06-01 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004280 | 2026-06-01 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004281 | 2026-06-01 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004282 | 2026-06-01 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004283 | 2026-06-01 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004284 | 2026-06-01 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 115 | 1437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004285 | 2026-06-01 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004286 | 2026-06-01 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 115 | 747.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004287 | 2026-06-01 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004288 | 2026-06-01 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004289 | 2026-06-01 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004290 | 2026-06-01 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004291 | 2026-06-01 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004292 | 2026-06-01 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004293 | 2026-06-01 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004294 | 2026-06-01 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 18 | 60 | 1080 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004295 | 2026-06-01 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004296 | 2026-06-01 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 60 | 660 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004297 | 2026-06-01 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 60 | 210 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004298 | 2026-06-08 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004299 | 2026-06-08 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004300 | 2026-06-08 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004301 | 2026-06-08 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004302 | 2026-06-08 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004303 | 2026-06-08 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004304 | 2026-06-08 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004305 | 2026-06-08 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004306 | 2026-06-08 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004307 | 2026-06-08 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004308 | 2026-06-08 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004309 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004310 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004311 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004312 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004313 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004314 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004315 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004316 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004317 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004318 | 2026-06-08 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004319 | 2026-06-08 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 80 | 2440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004320 | 2026-06-08 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004321 | 2026-06-08 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004322 | 2026-06-08 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004323 | 2026-06-08 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004324 | 2026-06-08 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004325 | 2026-06-08 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004326 | 2026-06-08 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004327 | 2026-06-08 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004328 | 2026-06-08 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004329 | 2026-06-08 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004330 | 2026-06-08 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28.5 | 62.5 | 1781.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004331 | 2026-06-08 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004332 | 2026-06-08 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004333 | 2026-06-08 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004334 | 2026-06-08 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004335 | 2026-06-08 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004336 | 2026-06-08 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004337 | 2026-06-08 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004338 | 2026-06-08 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004339 | 2026-06-08 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004340 | 2026-06-08 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004341 | 2026-06-08 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004342 | 2026-06-08 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 55 | 1732.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004343 | 2026-06-08 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004344 | 2026-06-08 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004345 | 2026-06-08 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004346 | 2026-06-08 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004347 | 2026-06-08 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004348 | 2026-06-08 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004349 | 2026-06-08 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004350 | 2026-06-08 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004351 | 2026-06-08 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004352 | 2026-06-08 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004353 | 2026-06-08 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004354 | 2026-06-08 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004355 | 2026-06-08 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004356 | 2026-06-08 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004357 | 2026-06-08 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004358 | 2026-06-08 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 19 | 157.5 | 2992.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004359 | 2026-06-08 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004360 | 2026-06-08 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004361 | 2026-06-08 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004362 | 2026-06-08 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004363 | 2026-06-08 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004364 | 2026-06-08 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004365 | 2026-06-08 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004366 | 2026-06-08 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004367 | 2026-06-08 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004368 | 2026-06-08 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004369 | 2026-06-08 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004370 | 2026-06-08 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004371 | 2026-06-08 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004372 | 2026-06-08 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004373 | 2026-06-08 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004374 | 2026-06-08 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004375 | 2026-06-08 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004376 | 2026-06-08 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004377 | 2026-06-08 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004378 | 2026-06-08 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004379 | 2026-06-08 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004380 | 2026-06-08 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004381 | 2026-06-08 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004382 | 2026-06-08 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004383 | 2026-06-08 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 10.5 | 85 | 892.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004384 | 2026-06-08 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 8.5 | 85 | 722.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004385 | 2026-06-08 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 3.5 | 85 | 297.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004386 | 2026-06-08 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 85 | 127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004387 | 2026-06-08 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004388 | 2026-06-08 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004389 | 2026-06-08 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004390 | 2026-06-08 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004391 | 2026-06-08 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004392 | 2026-06-08 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004393 | 2026-06-08 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004394 | 2026-06-08 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004395 | 2026-06-08 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004396 | 2026-06-08 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004397 | 2026-06-08 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004398 | 2026-06-08 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004399 | 2026-06-08 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004400 | 2026-06-08 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004401 | 2026-06-08 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004402 | 2026-06-08 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004403 | 2026-06-08 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004404 | 2026-06-08 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004405 | 2026-06-08 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004406 | 2026-06-08 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004407 | 2026-06-08 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4 | 55 | 220 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004408 | 2026-06-08 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004409 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004410 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004411 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004412 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004413 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004414 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004415 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004416 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004417 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004418 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004419 | 2026-06-08 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004420 | 2026-06-08 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004421 | 2026-06-08 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004422 | 2026-06-08 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004423 | 2026-06-08 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 25.5 | 100 | 2550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004424 | 2026-06-08 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004425 | 2026-06-08 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 100 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004426 | 2026-06-08 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 32.5 | 100 | 3250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004427 | 2026-06-08 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004428 | 2026-06-08 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 27.5 | 75 | 2062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004429 | 2026-06-08 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004430 | 2026-06-08 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004431 | 2026-06-08 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 29.5 | 67.5 | 1991.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004432 | 2026-06-08 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004433 | 2026-06-08 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004434 | 2026-06-08 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004435 | 2026-06-08 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004436 | 2026-06-08 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004437 | 2026-06-08 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 31 | 102.5 | 3177.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004438 | 2026-06-08 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004439 | 2026-06-08 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 102.5 | 102.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004440 | 2026-06-08 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 23.5 | 77.5 | 1821.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004441 | 2026-06-08 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6.5 | 77.5 | 503.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004442 | 2026-06-08 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 77.5 | 155 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004443 | 2026-06-08 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004444 | 2026-06-08 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 27.5 | 65 | 1787.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004445 | 2026-06-08 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004446 | 2026-06-08 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004447 | 2026-06-08 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004448 | 2026-06-08 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 3 | 117.5 | 352.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004449 | 2026-06-08 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 117.5 | 117.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004450 | 2026-06-08 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004451 | 2026-06-08 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004452 | 2026-06-08 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004453 | 2026-06-08 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004454 | 2026-06-08 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004455 | 2026-06-08 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 16 | 95 | 1520 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004456 | 2026-06-08 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 10 | 95 | 950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004457 | 2026-06-08 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6 | 95 | 570 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004458 | 2026-06-08 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004459 | 2026-06-08 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 22 | 60 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004460 | 2026-06-08 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004461 | 2026-06-08 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 60 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004462 | 2026-06-08 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15 | 90 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004463 | 2026-06-08 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004464 | 2026-06-08 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 6 | 90 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004465 | 2026-06-08 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004466 | 2026-06-08 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004467 | 2026-06-08 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20.5 | 62.5 | 1281.25 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004468 | 2026-06-08 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP04 | Data integration, migration and validation | Yes | 11.5 | 62.5 | 718.75 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004469 | 2026-06-08 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 8 | 62.5 | 500 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004470 | 2026-06-08 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 15.5 | 62.5 | 968.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004471 | 2026-06-08 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004472 | 2026-06-08 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004473 | 2026-06-08 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 62.5 | 125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004474 | 2026-06-08 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004475 | 2026-06-08 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004476 | 2026-06-08 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004477 | 2026-06-08 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 72.5 | 108.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004478 | 2026-06-08 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 72.5 | 108.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004479 | 2026-06-08 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 13 | 72.5 | 942.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004480 | 2026-06-08 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004481 | 2026-06-08 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004482 | 2026-06-08 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004483 | 2026-06-08 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004484 | 2026-06-08 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004485 | 2026-06-08 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004486 | 2026-06-08 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004487 | 2026-06-08 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 17 | 100 | 1700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004488 | 2026-06-08 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 100 | 700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004489 | 2026-06-08 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004490 | 2026-06-08 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 90 | 1890 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004491 | 2026-06-08 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 19 | 90 | 1710 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004492 | 2026-06-08 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004493 | 2026-06-08 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004494 | 2026-06-08 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004495 | 2026-06-08 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004496 | 2026-06-08 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 11 | 75 | 825 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004497 | 2026-06-08 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 75 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004498 | 2026-06-08 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004499 | 2026-06-08 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004500 | 2026-06-08 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 23 | 75 | 1725 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004501 | 2026-06-08 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004502 | 2026-06-08 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004503 | 2026-06-08 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004504 | 2026-06-08 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 3 | 97.5 | 292.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004505 | 2026-06-08 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 97.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004506 | 2026-06-08 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004507 | 2026-06-08 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004508 | 2026-06-08 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004509 | 2026-06-08 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004510 | 2026-06-08 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004511 | 2026-06-08 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20.5 | 67.5 | 1383.75 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004512 | 2026-06-08 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11 | 67.5 | 742.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004513 | 2026-06-08 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 67.5 | 472.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004514 | 2026-06-08 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004515 | 2026-06-08 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004516 | 2026-06-08 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 5 | 115 | 575 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004517 | 2026-06-08 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004518 | 2026-06-08 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004519 | 2026-06-08 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004520 | 2026-06-08 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004521 | 2026-06-08 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004522 | 2026-06-08 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004523 | 2026-06-08 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004524 | 2026-06-08 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004525 | 2026-06-08 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP03 | Build, configuration and implementation | Yes | 18 | 60 | 1080 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004526 | 2026-06-08 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004527 | 2026-06-08 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 60 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004528 | 2026-06-08 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004529 | 2026-06-15 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004530 | 2026-06-15 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004531 | 2026-06-15 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004532 | 2026-06-15 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004533 | 2026-06-15 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004534 | 2026-06-15 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004535 | 2026-06-15 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004536 | 2026-06-15 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004537 | 2026-06-15 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004538 | 2026-06-15 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004539 | 2026-06-15 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004540 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004541 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004542 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004543 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004544 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004545 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004546 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004547 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004548 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004549 | 2026-06-15 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004550 | 2026-06-15 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 80 | 2440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004551 | 2026-06-15 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004552 | 2026-06-15 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004553 | 2026-06-15 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004554 | 2026-06-15 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004555 | 2026-06-15 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004556 | 2026-06-15 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004557 | 2026-06-15 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004558 | 2026-06-15 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004559 | 2026-06-15 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004560 | 2026-06-15 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004561 | 2026-06-15 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29.5 | 62.5 | 1843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004562 | 2026-06-15 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 57.5 | 920 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004563 | 2026-06-15 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004564 | 2026-06-15 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004565 | 2026-06-15 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004566 | 2026-06-15 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004567 | 2026-06-15 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004568 | 2026-06-15 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004569 | 2026-06-15 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004570 | 2026-06-15 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004571 | 2026-06-15 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004572 | 2026-06-15 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004573 | 2026-06-15 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004574 | 2026-06-15 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004575 | 2026-06-15 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004576 | 2026-06-15 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004577 | 2026-06-15 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004578 | 2026-06-15 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004579 | 2026-06-15 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004580 | 2026-06-15 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004581 | 2026-06-15 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004582 | 2026-06-15 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004583 | 2026-06-15 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004584 | 2026-06-15 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004585 | 2026-06-15 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004586 | 2026-06-15 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004587 | 2026-06-15 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004588 | 2026-06-15 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004589 | 2026-06-15 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004590 | 2026-06-15 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 157.5 | 5040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004591 | 2026-06-15 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004592 | 2026-06-15 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004593 | 2026-06-15 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004594 | 2026-06-15 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004595 | 2026-06-15 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004596 | 2026-06-15 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004597 | 2026-06-15 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004598 | 2026-06-15 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004599 | 2026-06-15 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004600 | 2026-06-15 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004601 | 2026-06-15 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004602 | 2026-06-15 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004603 | 2026-06-15 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004604 | 2026-06-15 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004605 | 2026-06-15 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004606 | 2026-06-15 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004607 | 2026-06-15 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004608 | 2026-06-15 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004609 | 2026-06-15 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004610 | 2026-06-15 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004611 | 2026-06-15 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004612 | 2026-06-15 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004613 | 2026-06-15 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004614 | 2026-06-15 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004615 | 2026-06-15 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004616 | 2026-06-15 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004617 | 2026-06-15 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 85 | 85 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004618 | 2026-06-15 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21.5 | 82.5 | 1773.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004619 | 2026-06-15 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18.5 | 82.5 | 1526.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004620 | 2026-06-15 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004621 | 2026-06-15 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004622 | 2026-06-15 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004623 | 2026-06-15 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004624 | 2026-06-15 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004625 | 2026-06-15 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004626 | 2026-06-15 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004627 | 2026-06-15 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004628 | 2026-06-15 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004629 | 2026-06-15 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004630 | 2026-06-15 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004631 | 2026-06-15 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004632 | 2026-06-15 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004633 | 2026-06-15 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004634 | 2026-06-15 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004635 | 2026-06-15 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004636 | 2026-06-15 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7.5 | 55 | 412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004637 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004638 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004639 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004640 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004641 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004642 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004643 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004644 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004645 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004646 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004647 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 12.5 | 65 | 812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004648 | 2026-06-15 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004649 | 2026-06-15 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 22 | 120 | 2640 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004650 | 2026-06-15 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004651 | 2026-06-15 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 120 | 840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004652 | 2026-06-15 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 28 | 100 | 2800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004653 | 2026-06-15 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004654 | 2026-06-15 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004655 | 2026-06-15 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 19 | 100 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004656 | 2026-06-15 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004657 | 2026-06-15 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004658 | 2026-06-15 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004659 | 2026-06-15 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 75 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004660 | 2026-06-15 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004661 | 2026-06-15 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004662 | 2026-06-15 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004663 | 2026-06-15 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004664 | 2026-06-15 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 28.5 | 67.5 | 1923.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004665 | 2026-06-15 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004666 | 2026-06-15 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 102.5 | 3228.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004667 | 2026-06-15 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 102.5 | 768.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004668 | 2026-06-15 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 102.5 | 102.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004669 | 2026-06-15 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 77.5 | 2441.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004670 | 2026-06-15 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 77.5 | 620 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004671 | 2026-06-15 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 77.5 | 38.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004672 | 2026-06-15 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 65 | 715 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004673 | 2026-06-15 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 65 | 292.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004674 | 2026-06-15 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 65 | 32.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004675 | 2026-06-15 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004676 | 2026-06-15 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 9.5 | 117.5 | 1116.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004677 | 2026-06-15 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 10 | 117.5 | 1175 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004678 | 2026-06-15 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 4.5 | 117.5 | 528.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004679 | 2026-06-15 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004680 | 2026-06-15 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004681 | 2026-06-15 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004682 | 2026-06-15 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004683 | 2026-06-15 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004684 | 2026-06-15 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004685 | 2026-06-15 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004686 | 2026-06-15 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 95 | 95 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004687 | 2026-06-15 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 18.5 | 60 | 1110 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004688 | 2026-06-15 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13.5 | 60 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004689 | 2026-06-15 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004690 | 2026-06-15 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004691 | 2026-06-15 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004692 | 2026-06-15 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004693 | 2026-06-15 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004694 | 2026-06-15 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004695 | 2026-06-15 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004696 | 2026-06-15 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 62.5 | 93.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004697 | 2026-06-15 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 6.5 | 62.5 | 406.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004698 | 2026-06-15 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 62.5 | 312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004699 | 2026-06-15 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 4.5 | 62.5 | 281.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004700 | 2026-06-15 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004701 | 2026-06-15 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004702 | 2026-06-15 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004703 | 2026-06-15 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004704 | 2026-06-15 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004705 | 2026-06-15 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004706 | 2026-06-15 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31 | 72.5 | 2247.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004707 | 2026-06-15 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004708 | 2026-06-15 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004709 | 2026-06-15 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004710 | 2026-06-15 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004711 | 2026-06-15 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004712 | 2026-06-15 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 120 | 1380 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004713 | 2026-06-15 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004714 | 2026-06-15 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 120 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004715 | 2026-06-15 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004716 | 2026-06-15 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004717 | 2026-06-15 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004718 | 2026-06-15 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004719 | 2026-06-15 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 19.5 | 67.5 | 1316.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004720 | 2026-06-15 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004721 | 2026-06-15 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 67.5 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004722 | 2026-06-15 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004723 | 2026-06-15 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 20 | 75 | 1500 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004724 | 2026-06-15 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 20 | 75 | 1500 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004725 | 2026-06-15 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 14 | 75 | 1050 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004726 | 2026-06-15 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 75 | 375 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004727 | 2026-06-15 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 75 | 375 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004728 | 2026-06-15 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004729 | 2026-06-15 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004730 | 2026-06-15 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 3 | 97.5 | 292.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004731 | 2026-06-15 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 97.5 | 487.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004732 | 2026-06-15 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004733 | 2026-06-15 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004734 | 2026-06-15 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 30 | 75 | 2250 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004735 | 2026-06-15 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004736 | 2026-06-15 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8 | 75 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004737 | 2026-06-15 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004738 | 2026-06-15 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004739 | 2026-06-15 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004740 | 2026-06-15 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21 | 115 | 2415 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004741 | 2026-06-15 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 115 | 1265 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004742 | 2026-06-15 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004743 | 2026-06-15 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20.5 | 87.5 | 1793.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004744 | 2026-06-15 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004745 | 2026-06-15 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004746 | 2026-06-15 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004747 | 2026-06-15 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004748 | 2026-06-15 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004749 | 2026-06-15 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004750 | 2026-06-15 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 90 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004751 | 2026-06-15 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 60 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004752 | 2026-06-15 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004753 | 2026-06-15 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004754 | 2026-06-15 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004755 | 2026-06-22 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004756 | 2026-06-22 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004757 | 2026-06-22 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004758 | 2026-06-22 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004759 | 2026-06-22 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004760 | 2026-06-22 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004761 | 2026-06-22 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004762 | 2026-06-22 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004763 | 2026-06-22 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004764 | 2026-06-22 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004765 | 2026-06-22 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 97.5 | 2632.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004766 | 2026-06-22 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004767 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004768 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004769 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004770 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004771 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004772 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004773 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004774 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004775 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004776 | 2026-06-22 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004777 | 2026-06-22 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 80 | 880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004778 | 2026-06-22 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004779 | 2026-06-22 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004780 | 2026-06-22 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004781 | 2026-06-22 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004782 | 2026-06-22 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004783 | 2026-06-22 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004784 | 2026-06-22 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004785 | 2026-06-22 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004786 | 2026-06-22 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004787 | 2026-06-22 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004788 | 2026-06-22 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004789 | 2026-06-22 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004790 | 2026-06-22 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004791 | 2026-06-22 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004792 | 2026-06-22 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004793 | 2026-06-22 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004794 | 2026-06-22 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004795 | 2026-06-22 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004796 | 2026-06-22 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004797 | 2026-06-22 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004798 | 2026-06-22 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004799 | 2026-06-22 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004800 | 2026-06-22 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004801 | 2026-06-22 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004802 | 2026-06-22 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004803 | 2026-06-22 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004804 | 2026-06-22 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004805 | 2026-06-22 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 55 | 605 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004806 | 2026-06-22 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004807 | 2026-06-22 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004808 | 2026-06-22 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004809 | 2026-06-22 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004810 | 2026-06-22 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004811 | 2026-06-22 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004812 | 2026-06-22 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 14 | 187.5 | 2625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004813 | 2026-06-22 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004814 | 2026-06-22 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004815 | 2026-06-22 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004816 | 2026-06-22 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004817 | 2026-06-22 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004818 | 2026-06-22 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004819 | 2026-06-22 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004820 | 2026-06-22 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004821 | 2026-06-22 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004822 | 2026-06-22 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004823 | 2026-06-22 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004824 | 2026-06-22 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004825 | 2026-06-22 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27 | 157.5 | 4252.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004826 | 2026-06-22 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004827 | 2026-06-22 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004828 | 2026-06-22 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004829 | 2026-06-22 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004830 | 2026-06-22 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004831 | 2026-06-22 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004832 | 2026-06-22 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24.5 | 162.5 | 3981.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004833 | 2026-06-22 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004834 | 2026-06-22 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004835 | 2026-06-22 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004836 | 2026-06-22 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004837 | 2026-06-22 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004838 | 2026-06-22 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004839 | 2026-06-22 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 25.5 | 150 | 3825 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004840 | 2026-06-22 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004841 | 2026-06-22 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004842 | 2026-06-22 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004843 | 2026-06-22 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004844 | 2026-06-22 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004845 | 2026-06-22 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004846 | 2026-06-22 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004847 | 2026-06-22 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004848 | 2026-06-22 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004849 | 2026-06-22 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004850 | 2026-06-22 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004851 | 2026-06-22 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 105 | 1785 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004852 | 2026-06-22 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004853 | 2026-06-22 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004854 | 2026-06-22 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 12.5 | 85 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004855 | 2026-06-22 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5 | 85 | 425 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004856 | 2026-06-22 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004857 | 2026-06-22 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 16 | 82.5 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004858 | 2026-06-22 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 14.5 | 82.5 | 1196.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004859 | 2026-06-22 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004860 | 2026-06-22 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004861 | 2026-06-22 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 17 | 67.5 | 1147.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004862 | 2026-06-22 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 15 | 67.5 | 1012.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004863 | 2026-06-22 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004864 | 2026-06-22 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 15.5 | 67.5 | 1046.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004865 | 2026-06-22 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 9.5 | 67.5 | 641.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004866 | 2026-06-22 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004867 | 2026-06-22 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004868 | 2026-06-22 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004869 | 2026-06-22 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004870 | 2026-06-22 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004871 | 2026-06-22 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004872 | 2026-06-22 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004873 | 2026-06-22 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004874 | 2026-06-22 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004875 | 2026-06-22 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004876 | 2026-06-22 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004877 | 2026-06-22 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004878 | 2026-06-22 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 55 | 385 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004879 | 2026-06-22 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004880 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 0.5 | 65 | 32.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004881 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004882 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 0.5 | 65 | 32.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004883 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004884 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004885 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 0.5 | 65 | 32.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004886 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004887 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004888 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004889 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 0.5 | 65 | 32.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004890 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 65 | 520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004891 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004892 | 2026-06-22 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004893 | 2026-06-22 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 21 | 120 | 2520 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004894 | 2026-06-22 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 10.5 | 120 | 1260 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004895 | 2026-06-22 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 120 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004896 | 2026-06-22 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004897 | 2026-06-22 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 23 | 100 | 2300 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004898 | 2026-06-22 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004899 | 2026-06-22 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004900 | 2026-06-22 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004901 | 2026-06-22 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 25.5 | 100 | 2550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004902 | 2026-06-22 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 6.5 | 100 | 650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004903 | 2026-06-22 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004904 | 2026-06-22 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 20 | 75 | 1500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004905 | 2026-06-22 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 9.5 | 75 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004906 | 2026-06-22 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004907 | 2026-06-22 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004908 | 2026-06-22 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 13 | 67.5 | 877.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004909 | 2026-06-22 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 3 | 67.5 | 202.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004910 | 2026-06-22 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004911 | 2026-06-22 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004912 | 2026-06-22 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 23.5 | 67.5 | 1586.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004913 | 2026-06-22 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004914 | 2026-06-22 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004915 | 2026-06-22 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 102.5 | 2613.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004916 | 2026-06-22 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 102.5 | 666.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004917 | 2026-06-22 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004918 | 2026-06-22 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 77.5 | 2015 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004919 | 2026-06-22 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6 | 77.5 | 465 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004920 | 2026-06-22 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004921 | 2026-06-22 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 23 | 65 | 1495 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004922 | 2026-06-22 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 65 | 585 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004923 | 2026-06-22 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004924 | 2026-06-22 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 13.5 | 117.5 | 1586.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004925 | 2026-06-22 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12 | 117.5 | 1410 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004926 | 2026-06-22 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004927 | 2026-06-22 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004928 | 2026-06-22 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004929 | 2026-06-22 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 82.5 | 1031.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004930 | 2026-06-22 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 13 | 82.5 | 1072.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004931 | 2026-06-22 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6 | 82.5 | 495 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004932 | 2026-06-22 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004933 | 2026-06-22 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004934 | 2026-06-22 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 15.5 | 95 | 1472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004935 | 2026-06-22 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 10 | 95 | 950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004936 | 2026-06-22 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6 | 95 | 570 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004937 | 2026-06-22 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004938 | 2026-06-22 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004939 | 2026-06-22 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 17.5 | 60 | 1050 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004940 | 2026-06-22 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 13 | 60 | 780 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004941 | 2026-06-22 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004942 | 2026-06-22 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004943 | 2026-06-22 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15.5 | 90 | 1395 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004944 | 2026-06-22 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 90 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004945 | 2026-06-22 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 90 | 585 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004946 | 2026-06-22 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004947 | 2026-06-22 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 15.5 | 62.5 | 968.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004948 | 2026-06-22 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 10.5 | 62.5 | 656.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004949 | 2026-06-22 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 6.5 | 62.5 | 406.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004950 | 2026-06-22 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004951 | 2026-06-22 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 12.5 | 62.5 | 781.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004952 | 2026-06-22 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 62.5 | 593.75 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004953 | 2026-06-22 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 9.5 | 62.5 | 593.75 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004954 | 2026-06-22 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004955 | 2026-06-22 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004956 | 2026-06-22 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004957 | 2026-06-22 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004958 | 2026-06-22 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 13 | 105 | 1365 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004959 | 2026-06-22 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004960 | 2026-06-22 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004961 | 2026-06-22 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004962 | 2026-06-22 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004963 | 2026-06-22 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25.5 | 72.5 | 1848.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004964 | 2026-06-22 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004965 | 2026-06-22 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004966 | 2026-06-22 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004967 | 2026-06-22 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004968 | 2026-06-22 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004969 | 2026-06-22 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004970 | 2026-06-22 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004971 | 2026-06-22 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19.5 | 120 | 2340 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004972 | 2026-06-22 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 120 | 1020 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004973 | 2026-06-22 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004974 | 2026-06-22 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 120 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004975 | 2026-06-22 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004976 | 2026-06-22 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 5.5 | 100 | 550 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004977 | 2026-06-22 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 2.5 | 100 | 250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004978 | 2026-06-22 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004979 | 2026-06-22 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004980 | 2026-06-22 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 16.5 | 90 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004981 | 2026-06-22 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 15.5 | 90 | 1395 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004982 | 2026-06-22 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004983 | 2026-06-22 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 17 | 67.5 | 1147.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004984 | 2026-06-22 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 9 | 67.5 | 607.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004985 | 2026-06-22 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 6 | 67.5 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004986 | 2026-06-22 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004987 | 2026-06-22 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004988 | 2026-06-22 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004989 | 2026-06-22 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004990 | 2026-06-22 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004991 | 2026-06-22 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004992 | 2026-06-22 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 14 | 75 | 1050 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004993 | 2026-06-22 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 75 | 375 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004994 | 2026-06-22 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 5 | 75 | 375 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004995 | 2026-06-22 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004996 | 2026-06-22 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004997 | 2026-06-22 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 17 | 97.5 | 1657.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004998 | 2026-06-22 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 7 | 97.5 | 682.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-004999 | 2026-06-22 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005000 | 2026-06-22 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005001 | 2026-06-22 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 24.5 | 75 | 1837.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005002 | 2026-06-22 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6 | 75 | 450 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005003 | 2026-06-22 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005004 | 2026-06-22 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 67.5 | 978.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005005 | 2026-06-22 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 67.5 | 641.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005006 | 2026-06-22 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 67.5 | 405 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005007 | 2026-06-22 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005008 | 2026-06-22 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005009 | 2026-06-22 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16.5 | 115 | 1897.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005010 | 2026-06-22 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9.5 | 115 | 1092.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005011 | 2026-06-22 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 6 | 115 | 690 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005012 | 2026-06-22 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005013 | 2026-06-22 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16 | 87.5 | 1400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005014 | 2026-06-22 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 9 | 87.5 | 787.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005015 | 2026-06-22 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7 | 87.5 | 612.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005016 | 2026-06-22 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005017 | 2026-06-22 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16 | 90 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005018 | 2026-06-22 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005019 | 2026-06-22 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005020 | 2026-06-22 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005021 | 2026-06-22 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 60 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005022 | 2026-06-22 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 60 | 360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005023 | 2026-06-22 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP02 | Architecture, detailed design and backlog refinement | Yes | 9 | 60 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005024 | 2026-06-22 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 60 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005025 | 2026-06-22 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005026 | 2026-06-29 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005027 | 2026-06-29 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005028 | 2026-06-29 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005029 | 2026-06-29 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005030 | 2026-06-29 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005031 | 2026-06-29 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005032 | 2026-06-29 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005033 | 2026-06-29 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005034 | 2026-06-29 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005035 | 2026-06-29 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005036 | 2026-06-29 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005037 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005038 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005039 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005040 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005041 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005042 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005043 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005044 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005045 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005046 | 2026-06-29 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005047 | 2026-06-29 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 80 | 2480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005048 | 2026-06-29 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005049 | 2026-06-29 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005050 | 2026-06-29 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005051 | 2026-06-29 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005052 | 2026-06-29 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005053 | 2026-06-29 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005054 | 2026-06-29 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005055 | 2026-06-29 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005056 | 2026-06-29 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005057 | 2026-06-29 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005058 | 2026-06-29 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29.5 | 62.5 | 1843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005059 | 2026-06-29 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 57.5 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005060 | 2026-06-29 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005061 | 2026-06-29 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005062 | 2026-06-29 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005063 | 2026-06-29 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005064 | 2026-06-29 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005065 | 2026-06-29 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005066 | 2026-06-29 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005067 | 2026-06-29 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005068 | 2026-06-29 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005069 | 2026-06-29 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005070 | 2026-06-29 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005071 | 2026-06-29 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 55 | 1732.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005072 | 2026-06-29 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005073 | 2026-06-29 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005074 | 2026-06-29 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005075 | 2026-06-29 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005076 | 2026-06-29 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005077 | 2026-06-29 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005078 | 2026-06-29 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005079 | 2026-06-29 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005080 | 2026-06-29 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005081 | 2026-06-29 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005082 | 2026-06-29 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005083 | 2026-06-29 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005084 | 2026-06-29 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005085 | 2026-06-29 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005086 | 2026-06-29 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005087 | 2026-06-29 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31 | 157.5 | 4882.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005088 | 2026-06-29 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005089 | 2026-06-29 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005090 | 2026-06-29 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005091 | 2026-06-29 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005092 | 2026-06-29 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005093 | 2026-06-29 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005094 | 2026-06-29 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005095 | 2026-06-29 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005096 | 2026-06-29 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005097 | 2026-06-29 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005098 | 2026-06-29 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005099 | 2026-06-29 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005100 | 2026-06-29 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005101 | 2026-06-29 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005102 | 2026-06-29 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005103 | 2026-06-29 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005104 | 2026-06-29 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005105 | 2026-06-29 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005106 | 2026-06-29 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005107 | 2026-06-29 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005108 | 2026-06-29 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005109 | 2026-06-29 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005110 | 2026-06-29 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005111 | 2026-06-29 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005112 | 2026-06-29 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 14.5 | 85 | 1232.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005113 | 2026-06-29 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005114 | 2026-06-29 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20.5 | 82.5 | 1691.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005115 | 2026-06-29 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005116 | 2026-06-29 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2.5 | 82.5 | 206.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005117 | 2026-06-29 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005118 | 2026-06-29 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005119 | 2026-06-29 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005120 | 2026-06-29 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005121 | 2026-06-29 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005122 | 2026-06-29 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005123 | 2026-06-29 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005124 | 2026-06-29 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005125 | 2026-06-29 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005126 | 2026-06-29 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005127 | 2026-06-29 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005128 | 2026-06-29 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005129 | 2026-06-29 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005130 | 2026-06-29 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005131 | 2026-06-29 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005132 | 2026-06-29 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005133 | 2026-06-29 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005134 | 2026-06-29 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 55 | 385 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005135 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005136 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005137 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005138 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005139 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005140 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005141 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005142 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005143 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005144 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005145 | 2026-06-29 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16 | 65 | 1040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005146 | 2026-06-29 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 24.5 | 120 | 2940 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005147 | 2026-06-29 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005148 | 2026-06-29 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 120 | 540 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005149 | 2026-06-29 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 30.5 | 100 | 3050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005150 | 2026-06-29 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005151 | 2026-06-29 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005152 | 2026-06-29 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 29 | 100 | 2900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005153 | 2026-06-29 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005154 | 2026-06-29 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005155 | 2026-06-29 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 28 | 75 | 2100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005156 | 2026-06-29 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 75 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005157 | 2026-06-29 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 31 | 67.5 | 2092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005158 | 2026-06-29 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005159 | 2026-06-29 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005160 | 2026-06-29 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005161 | 2026-06-29 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005162 | 2026-06-29 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 67.5 | 270 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005163 | 2026-06-29 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 102.5 | 3331.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005164 | 2026-06-29 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005165 | 2026-06-29 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 77.5 | 2441.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005166 | 2026-06-29 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8.5 | 77.5 | 658.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005167 | 2026-06-29 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 65 | 1657.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005168 | 2026-06-29 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 65 | 845 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005169 | 2026-06-29 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 65 | 97.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005170 | 2026-06-29 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005171 | 2026-06-29 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005172 | 2026-06-29 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005173 | 2026-06-29 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 117.5 | 117.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005174 | 2026-06-29 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005175 | 2026-06-29 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005176 | 2026-06-29 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005177 | 2026-06-29 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005178 | 2026-06-29 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005179 | 2026-06-29 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005180 | 2026-06-29 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 5 | 95 | 475 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005181 | 2026-06-29 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005182 | 2026-06-29 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 23 | 60 | 1380 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005183 | 2026-06-29 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005184 | 2026-06-29 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005185 | 2026-06-29 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005186 | 2026-06-29 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005187 | 2026-06-29 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005188 | 2026-06-29 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005189 | 2026-06-29 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005190 | 2026-06-29 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 4.5 | 62.5 | 281.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005191 | 2026-06-29 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005192 | 2026-06-29 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005193 | 2026-06-29 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005194 | 2026-06-29 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005195 | 2026-06-29 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005196 | 2026-06-29 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005197 | 2026-06-29 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005198 | 2026-06-29 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005199 | 2026-06-29 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005200 | 2026-06-29 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005201 | 2026-06-29 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005202 | 2026-06-29 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005203 | 2026-06-29 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005204 | 2026-06-29 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005205 | 2026-06-29 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 22.5 | 120 | 2700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005206 | 2026-06-29 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005207 | 2026-06-29 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005208 | 2026-06-29 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005209 | 2026-06-29 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005210 | 2026-06-29 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005211 | 2026-06-29 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 100 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005212 | 2026-06-29 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 13 | 90 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005213 | 2026-06-29 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11 | 90 | 990 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005214 | 2026-06-29 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005215 | 2026-06-29 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005216 | 2026-06-29 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005217 | 2026-06-29 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 9 | 67.5 | 607.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005218 | 2026-06-29 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005219 | 2026-06-29 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005220 | 2026-06-29 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005221 | 2026-06-29 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005222 | 2026-06-29 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005223 | 2026-06-29 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005224 | 2026-06-29 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005225 | 2026-06-29 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005226 | 2026-06-29 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005227 | 2026-06-29 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005228 | 2026-06-29 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18 | 67.5 | 1215 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005229 | 2026-06-29 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005230 | 2026-06-29 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005231 | 2026-06-29 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005232 | 2026-06-29 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20.5 | 115 | 2357.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005233 | 2026-06-29 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005234 | 2026-06-29 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005235 | 2026-06-29 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005236 | 2026-06-29 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21 | 87.5 | 1837.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005237 | 2026-06-29 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005238 | 2026-06-29 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005239 | 2026-06-29 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005240 | 2026-06-29 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005241 | 2026-06-29 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005242 | 2026-06-29 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005243 | 2026-06-29 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 60 | 1230 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005244 | 2026-06-29 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005245 | 2026-06-29 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005246 | 2026-07-06 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 97.5 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005247 | 2026-07-06 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005248 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005249 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005250 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005251 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005252 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005253 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005254 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005255 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005256 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005257 | 2026-07-06 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005258 | 2026-07-06 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 7 | 80 | 560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005259 | 2026-07-06 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005260 | 2026-07-06 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005261 | 2026-07-06 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005262 | 2026-07-06 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005263 | 2026-07-06 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005264 | 2026-07-06 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005265 | 2026-07-06 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005266 | 2026-07-06 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005267 | 2026-07-06 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005268 | 2026-07-06 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005269 | 2026-07-06 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005270 | 2026-07-06 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005271 | 2026-07-06 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005272 | 2026-07-06 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005273 | 2026-07-06 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005274 | 2026-07-06 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005275 | 2026-07-06 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005276 | 2026-07-06 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005277 | 2026-07-06 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005278 | 2026-07-06 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005279 | 2026-07-06 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005280 | 2026-07-06 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005281 | 2026-07-06 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005282 | 2026-07-06 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 55 | 605 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005283 | 2026-07-06 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005284 | 2026-07-06 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005285 | 2026-07-06 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005286 | 2026-07-06 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005287 | 2026-07-06 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005288 | 2026-07-06 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005289 | 2026-07-06 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005290 | 2026-07-06 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005291 | 2026-07-06 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005292 | 2026-07-06 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005293 | 2026-07-06 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005294 | 2026-07-06 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005295 | 2026-07-06 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005296 | 2026-07-06 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005297 | 2026-07-06 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005298 | 2026-07-06 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005299 | 2026-07-06 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31 | 157.5 | 4882.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005300 | 2026-07-06 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005301 | 2026-07-06 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005302 | 2026-07-06 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005303 | 2026-07-06 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005304 | 2026-07-06 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005305 | 2026-07-06 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005306 | 2026-07-06 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005307 | 2026-07-06 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005308 | 2026-07-06 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005309 | 2026-07-06 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005310 | 2026-07-06 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005311 | 2026-07-06 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005312 | 2026-07-06 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005313 | 2026-07-06 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005314 | 2026-07-06 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005315 | 2026-07-06 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005316 | 2026-07-06 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005317 | 2026-07-06 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005318 | 2026-07-06 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005319 | 2026-07-06 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005320 | 2026-07-06 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005321 | 2026-07-06 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005322 | 2026-07-06 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005323 | 2026-07-06 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005324 | 2026-07-06 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005325 | 2026-07-06 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005326 | 2026-07-06 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005327 | 2026-07-06 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005328 | 2026-07-06 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005329 | 2026-07-06 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005330 | 2026-07-06 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005331 | 2026-07-06 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005332 | 2026-07-06 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005333 | 2026-07-06 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005334 | 2026-07-06 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005335 | 2026-07-06 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005336 | 2026-07-06 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005337 | 2026-07-06 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005338 | 2026-07-06 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005339 | 2026-07-06 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005340 | 2026-07-06 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005341 | 2026-07-06 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005342 | 2026-07-06 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005343 | 2026-07-06 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005344 | 2026-07-06 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8.5 | 55 | 467.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005345 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005346 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005347 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005348 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005349 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005350 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005351 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005352 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005353 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005354 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005355 | 2026-07-06 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005356 | 2026-07-06 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 15.5 | 120 | 1860 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005357 | 2026-07-06 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7 | 120 | 840 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005358 | 2026-07-06 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005359 | 2026-07-06 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005360 | 2026-07-06 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 26.5 | 100 | 2650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005361 | 2026-07-06 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005362 | 2026-07-06 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 100 | 550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005363 | 2026-07-06 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 29 | 100 | 2900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005364 | 2026-07-06 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005365 | 2026-07-06 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005366 | 2026-07-06 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 27 | 75 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005367 | 2026-07-06 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP04 | Data integration, migration and validation | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005368 | 2026-07-06 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005369 | 2026-07-06 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005370 | 2026-07-06 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005371 | 2026-07-06 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 17 | 67.5 | 1147.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005372 | 2026-07-06 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7 | 67.5 | 472.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005373 | 2026-07-06 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005374 | 2026-07-06 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 102.5 | 3280 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005375 | 2026-07-06 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005376 | 2026-07-06 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 17.5 | 77.5 | 1356.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005377 | 2026-07-06 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 5 | 77.5 | 387.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005378 | 2026-07-06 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 77.5 | 116.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005379 | 2026-07-06 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005380 | 2026-07-06 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005381 | 2026-07-06 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005382 | 2026-07-06 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005383 | 2026-07-06 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 17.5 | 117.5 | 2056.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005384 | 2026-07-06 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005385 | 2026-07-06 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005386 | 2026-07-06 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 82.5 | 1402.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005387 | 2026-07-06 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005388 | 2026-07-06 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8.5 | 82.5 | 701.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005389 | 2026-07-06 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005390 | 2026-07-06 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005391 | 2026-07-06 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 9 | 95 | 855 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005392 | 2026-07-06 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 25.5 | 60 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005393 | 2026-07-06 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 14.5 | 60 | 870 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005394 | 2026-07-06 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 18 | 90 | 1620 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005395 | 2026-07-06 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005396 | 2026-07-06 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005397 | 2026-07-06 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005398 | 2026-07-06 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 8 | 62.5 | 500 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005399 | 2026-07-06 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 62.5 | 312.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005400 | 2026-07-06 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 3 | 62.5 | 187.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005401 | 2026-07-06 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005402 | 2026-07-06 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005403 | 2026-07-06 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005404 | 2026-07-06 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005405 | 2026-07-06 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005406 | 2026-07-06 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005407 | 2026-07-06 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005408 | 2026-07-06 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005409 | 2026-07-06 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005410 | 2026-07-06 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005411 | 2026-07-06 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005412 | 2026-07-06 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 55 | 1980 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005413 | 2026-07-06 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005414 | 2026-07-06 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 22.5 | 120 | 2700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005415 | 2026-07-06 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 120 | 1380 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005416 | 2026-07-06 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 4.5 | 120 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005417 | 2026-07-06 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005418 | 2026-07-06 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 27.5 | 100 | 2750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005419 | 2026-07-06 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 12.5 | 100 | 1250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005420 | 2026-07-06 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 90 | 1035 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005421 | 2026-07-06 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 12.5 | 90 | 1125 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005422 | 2026-07-06 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005423 | 2026-07-06 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19 | 67.5 | 1282.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005424 | 2026-07-06 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005425 | 2026-07-06 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005426 | 2026-07-06 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005427 | 2026-07-06 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005428 | 2026-07-06 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005429 | 2026-07-06 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 75 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005430 | 2026-07-06 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 23 | 75 | 1725 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005431 | 2026-07-06 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005432 | 2026-07-06 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005433 | 2026-07-06 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005434 | 2026-07-06 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005435 | 2026-07-06 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005436 | 2026-07-06 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 97.5 | 1121.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005437 | 2026-07-06 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005438 | 2026-07-06 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 29 | 75 | 2175 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005439 | 2026-07-06 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005440 | 2026-07-06 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 75 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005441 | 2026-07-06 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005442 | 2026-07-06 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005443 | 2026-07-06 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005444 | 2026-07-06 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005445 | 2026-07-06 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 4.5 | 115 | 517.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005446 | 2026-07-06 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 3 | 115 | 345 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005447 | 2026-07-06 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 115 | 115 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005448 | 2026-07-06 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005449 | 2026-07-06 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18.5 | 87.5 | 1618.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005450 | 2026-07-06 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005451 | 2026-07-06 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005452 | 2026-07-06 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 87.5 | 262.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005453 | 2026-07-06 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005454 | 2026-07-06 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005455 | 2026-07-06 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005456 | 2026-07-06 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 60 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005457 | 2026-07-06 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005458 | 2026-07-06 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12.5 | 60 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005459 | 2026-07-13 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005460 | 2026-07-13 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005461 | 2026-07-13 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005462 | 2026-07-13 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005463 | 2026-07-13 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005464 | 2026-07-13 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005465 | 2026-07-13 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005466 | 2026-07-13 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005467 | 2026-07-13 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005468 | 2026-07-13 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005469 | 2026-07-13 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005470 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005471 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005472 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005473 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005474 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005475 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005476 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005477 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005478 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005479 | 2026-07-13 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005480 | 2026-07-13 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11 | 80 | 880 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005481 | 2026-07-13 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005482 | 2026-07-13 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005483 | 2026-07-13 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005484 | 2026-07-13 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005485 | 2026-07-13 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005486 | 2026-07-13 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005487 | 2026-07-13 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005488 | 2026-07-13 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005489 | 2026-07-13 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005490 | 2026-07-13 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005491 | 2026-07-13 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005492 | 2026-07-13 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28.5 | 62.5 | 1781.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005493 | 2026-07-13 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005494 | 2026-07-13 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005495 | 2026-07-13 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005496 | 2026-07-13 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005497 | 2026-07-13 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005498 | 2026-07-13 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005499 | 2026-07-13 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005500 | 2026-07-13 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005501 | 2026-07-13 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005502 | 2026-07-13 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005503 | 2026-07-13 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005504 | 2026-07-13 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005505 | 2026-07-13 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005506 | 2026-07-13 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005507 | 2026-07-13 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005508 | 2026-07-13 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005509 | 2026-07-13 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005510 | 2026-07-13 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005511 | 2026-07-13 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005512 | 2026-07-13 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005513 | 2026-07-13 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005514 | 2026-07-13 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005515 | 2026-07-13 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005516 | 2026-07-13 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005517 | 2026-07-13 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005518 | 2026-07-13 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005519 | 2026-07-13 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005520 | 2026-07-13 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27 | 157.5 | 4252.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005521 | 2026-07-13 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005522 | 2026-07-13 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005523 | 2026-07-13 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005524 | 2026-07-13 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005525 | 2026-07-13 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005526 | 2026-07-13 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005527 | 2026-07-13 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005528 | 2026-07-13 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005529 | 2026-07-13 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005530 | 2026-07-13 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005531 | 2026-07-13 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005532 | 2026-07-13 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005533 | 2026-07-13 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005534 | 2026-07-13 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005535 | 2026-07-13 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005536 | 2026-07-13 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005537 | 2026-07-13 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005538 | 2026-07-13 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005539 | 2026-07-13 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005540 | 2026-07-13 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005541 | 2026-07-13 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005542 | 2026-07-13 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005543 | 2026-07-13 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005544 | 2026-07-13 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005545 | 2026-07-13 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005546 | 2026-07-13 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005547 | 2026-07-13 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005548 | 2026-07-13 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 85 | 127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005549 | 2026-07-13 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005550 | 2026-07-13 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005551 | 2026-07-13 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005552 | 2026-07-13 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21.5 | 67.5 | 1451.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005553 | 2026-07-13 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005554 | 2026-07-13 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 13 | 67.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005555 | 2026-07-13 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005556 | 2026-07-13 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005557 | 2026-07-13 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005558 | 2026-07-13 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005559 | 2026-07-13 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005560 | 2026-07-13 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005561 | 2026-07-13 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005562 | 2026-07-13 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005563 | 2026-07-13 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005564 | 2026-07-13 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005565 | 2026-07-13 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005566 | 2026-07-13 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005567 | 2026-07-13 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7.5 | 55 | 412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005568 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005569 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005570 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005571 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005572 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005573 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005574 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005575 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005576 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005577 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005578 | 2026-07-13 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005579 | 2026-07-13 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 10 | 120 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005580 | 2026-07-13 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 5 | 120 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005581 | 2026-07-13 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005582 | 2026-07-13 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005583 | 2026-07-13 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 28 | 100 | 2800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005584 | 2026-07-13 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005585 | 2026-07-13 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 100 | 400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005586 | 2026-07-13 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 12.5 | 100 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005587 | 2026-07-13 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 3.5 | 100 | 350 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005588 | 2026-07-13 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005589 | 2026-07-13 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 27 | 75 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005590 | 2026-07-13 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 12.5 | 75 | 937.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005591 | 2026-07-13 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005592 | 2026-07-13 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 29.5 | 67.5 | 1991.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005593 | 2026-07-13 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 9 | 67.5 | 607.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005594 | 2026-07-13 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005595 | 2026-07-13 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005596 | 2026-07-13 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005597 | 2026-07-13 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 102.5 | 3075 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005598 | 2026-07-13 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005599 | 2026-07-13 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 102.5 | 256.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005600 | 2026-07-13 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 77.5 | 2518.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005601 | 2026-07-13 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 77.5 | 581.25 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005602 | 2026-07-13 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 65 | 1820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005603 | 2026-07-13 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 65 | 780 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005604 | 2026-07-13 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005605 | 2026-07-13 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005606 | 2026-07-13 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005607 | 2026-07-13 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005608 | 2026-07-13 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 17 | 82.5 | 1402.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005609 | 2026-07-13 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005610 | 2026-07-13 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005611 | 2026-07-13 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005612 | 2026-07-13 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005613 | 2026-07-13 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005614 | 2026-07-13 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 95 | 190 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005615 | 2026-07-13 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005616 | 2026-07-13 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005617 | 2026-07-13 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005618 | 2026-07-13 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005619 | 2026-07-13 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005620 | 2026-07-13 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 18.5 | 62.5 | 1156.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005621 | 2026-07-13 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005622 | 2026-07-13 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005623 | 2026-07-13 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 62.5 | 125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005624 | 2026-07-13 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15 | 62.5 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005625 | 2026-07-13 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005626 | 2026-07-13 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 13 | 62.5 | 812.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005627 | 2026-07-13 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005628 | 2026-07-13 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005629 | 2026-07-13 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005630 | 2026-07-13 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005631 | 2026-07-13 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005632 | 2026-07-13 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005633 | 2026-07-13 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005634 | 2026-07-13 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005635 | 2026-07-13 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005636 | 2026-07-13 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005637 | 2026-07-13 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15 | 120 | 1800 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005638 | 2026-07-13 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 7 | 120 | 840 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005639 | 2026-07-13 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 2 | 120 | 240 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005640 | 2026-07-13 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005641 | 2026-07-13 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005642 | 2026-07-13 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005643 | 2026-07-13 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 19 | 90 | 1710 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005644 | 2026-07-13 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 21 | 90 | 1890 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005645 | 2026-07-13 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 19.5 | 67.5 | 1316.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005646 | 2026-07-13 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005647 | 2026-07-13 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005648 | 2026-07-13 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005649 | 2026-07-13 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005650 | 2026-07-13 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005651 | 2026-07-13 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005652 | 2026-07-13 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005653 | 2026-07-13 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005654 | 2026-07-13 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP02 | Architecture, detailed design and backlog refinement | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005655 | 2026-07-13 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005656 | 2026-07-13 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 5 | 97.5 | 487.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005657 | 2026-07-13 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 97.5 | 682.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005658 | 2026-07-13 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005659 | 2026-07-13 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005660 | 2026-07-13 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005661 | 2026-07-13 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005662 | 2026-07-13 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005663 | 2026-07-13 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005664 | 2026-07-13 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005665 | 2026-07-13 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005666 | 2026-07-13 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005667 | 2026-07-13 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8.5 | 115 | 977.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005668 | 2026-07-13 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005669 | 2026-07-13 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005670 | 2026-07-13 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP03 | Build, configuration and implementation | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005671 | 2026-07-13 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 4.5 | 87.5 | 393.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005672 | 2026-07-13 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005673 | 2026-07-13 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005674 | 2026-07-13 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005675 | 2026-07-13 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005676 | 2026-07-13 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 90 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005677 | 2026-07-13 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005678 | 2026-07-13 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 60 | 960 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005679 | 2026-07-13 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 60 | 360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005680 | 2026-07-13 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 10 | 60 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005681 | 2026-07-13 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005682 | 2026-07-20 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005683 | 2026-07-20 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005684 | 2026-07-20 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005685 | 2026-07-20 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005686 | 2026-07-20 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005687 | 2026-07-20 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005688 | 2026-07-20 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005689 | 2026-07-20 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005690 | 2026-07-20 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005691 | 2026-07-20 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005692 | 2026-07-20 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005693 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005694 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005695 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005696 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005697 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005698 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005699 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005700 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005701 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005702 | 2026-07-20 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005703 | 2026-07-20 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 80 | 2440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005704 | 2026-07-20 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005705 | 2026-07-20 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005706 | 2026-07-20 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005707 | 2026-07-20 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005708 | 2026-07-20 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005709 | 2026-07-20 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005710 | 2026-07-20 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005711 | 2026-07-20 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005712 | 2026-07-20 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005713 | 2026-07-20 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005714 | 2026-07-20 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005715 | 2026-07-20 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005716 | 2026-07-20 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005717 | 2026-07-20 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005718 | 2026-07-20 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005719 | 2026-07-20 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005720 | 2026-07-20 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005721 | 2026-07-20 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005722 | 2026-07-20 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005723 | 2026-07-20 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005724 | 2026-07-20 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005725 | 2026-07-20 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005726 | 2026-07-20 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005727 | 2026-07-20 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005728 | 2026-07-20 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005729 | 2026-07-20 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005730 | 2026-07-20 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005731 | 2026-07-20 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005732 | 2026-07-20 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005733 | 2026-07-20 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005734 | 2026-07-20 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005735 | 2026-07-20 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005736 | 2026-07-20 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005737 | 2026-07-20 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005738 | 2026-07-20 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005739 | 2026-07-20 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005740 | 2026-07-20 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005741 | 2026-07-20 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005742 | 2026-07-20 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30.5 | 157.5 | 4803.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005743 | 2026-07-20 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005744 | 2026-07-20 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005745 | 2026-07-20 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005746 | 2026-07-20 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005747 | 2026-07-20 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005748 | 2026-07-20 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005749 | 2026-07-20 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005750 | 2026-07-20 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005751 | 2026-07-20 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005752 | 2026-07-20 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005753 | 2026-07-20 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005754 | 2026-07-20 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005755 | 2026-07-20 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005756 | 2026-07-20 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005757 | 2026-07-20 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 0.5 | 105 | 52.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005758 | 2026-07-20 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005759 | 2026-07-20 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 0.5 | 105 | 52.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005760 | 2026-07-20 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 0.5 | 105 | 52.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005761 | 2026-07-20 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005762 | 2026-07-20 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005763 | 2026-07-20 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005764 | 2026-07-20 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005765 | 2026-07-20 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7.5 | 105 | 787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005766 | 2026-07-20 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005767 | 2026-07-20 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005768 | 2026-07-20 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 17 | 85 | 1445 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005769 | 2026-07-20 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005770 | 2026-07-20 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22 | 82.5 | 1815 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005771 | 2026-07-20 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18 | 82.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005772 | 2026-07-20 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005773 | 2026-07-20 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005774 | 2026-07-20 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005775 | 2026-07-20 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005776 | 2026-07-20 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005777 | 2026-07-20 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 9 | 67.5 | 607.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005778 | 2026-07-20 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005779 | 2026-07-20 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005780 | 2026-07-20 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005781 | 2026-07-20 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005782 | 2026-07-20 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005783 | 2026-07-20 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005784 | 2026-07-20 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005785 | 2026-07-20 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005786 | 2026-07-20 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005787 | 2026-07-20 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005788 | 2026-07-20 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 55 | 440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005789 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005790 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005791 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005792 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005793 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005794 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005795 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005796 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005797 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005798 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005799 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 65 | 1105 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005800 | 2026-07-20 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005801 | 2026-07-20 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 23 | 120 | 2760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005802 | 2026-07-20 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005803 | 2026-07-20 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 120 | 600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005804 | 2026-07-20 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 26.5 | 100 | 2650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005805 | 2026-07-20 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005806 | 2026-07-20 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 100 | 550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005807 | 2026-07-20 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005808 | 2026-07-20 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005809 | 2026-07-20 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 27 | 75 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005810 | 2026-07-20 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005811 | 2026-07-20 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005812 | 2026-07-20 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 31.5 | 67.5 | 2126.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005813 | 2026-07-20 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005814 | 2026-07-20 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005815 | 2026-07-20 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 28.5 | 67.5 | 1923.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005816 | 2026-07-20 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005817 | 2026-07-20 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 102.5 | 2972.5 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005818 | 2026-07-20 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 102.5 | 820 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005819 | 2026-07-20 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 102.5 | 307.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005820 | 2026-07-20 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 77.5 | 891.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005821 | 2026-07-20 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 3 | 77.5 | 232.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005822 | 2026-07-20 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 77.5 | 116.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005823 | 2026-07-20 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005824 | 2026-07-20 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005825 | 2026-07-20 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 65 | 747.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005826 | 2026-07-20 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005827 | 2026-07-20 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005828 | 2026-07-20 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005829 | 2026-07-20 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 117.5 | 117.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005830 | 2026-07-20 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 82.5 | 742.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005831 | 2026-07-20 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 9 | 82.5 | 742.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005832 | 2026-07-20 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 4.5 | 82.5 | 371.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005833 | 2026-07-20 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005834 | 2026-07-20 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005835 | 2026-07-20 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005836 | 2026-07-20 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005837 | 2026-07-20 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005838 | 2026-07-20 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 24.5 | 60 | 1470 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005839 | 2026-07-20 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005840 | 2026-07-20 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005841 | 2026-07-20 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005842 | 2026-07-20 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005843 | 2026-07-20 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005844 | 2026-07-20 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005845 | 2026-07-20 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 62.5 | 718.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005846 | 2026-07-20 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005847 | 2026-07-20 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 62.5 | 62.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005848 | 2026-07-20 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 9 | 62.5 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005849 | 2026-07-20 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005850 | 2026-07-20 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 7 | 62.5 | 437.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005851 | 2026-07-20 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005852 | 2026-07-20 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005853 | 2026-07-20 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005854 | 2026-07-20 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005855 | 2026-07-20 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005856 | 2026-07-20 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005857 | 2026-07-20 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005858 | 2026-07-20 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005859 | 2026-07-20 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005860 | 2026-07-20 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005861 | 2026-07-20 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005862 | 2026-07-20 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005863 | 2026-07-20 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 13 | 120 | 1560 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005864 | 2026-07-20 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005865 | 2026-07-20 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005866 | 2026-07-20 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005867 | 2026-07-20 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 100 | 50 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005868 | 2026-07-20 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005869 | 2026-07-20 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 21.5 | 90 | 1935 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005870 | 2026-07-20 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP04 | Data integration, migration and validation | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005871 | 2026-07-20 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 6.5 | 67.5 | 438.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005872 | 2026-07-20 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 4.5 | 67.5 | 303.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005873 | 2026-07-20 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005874 | 2026-07-20 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005875 | 2026-07-20 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005876 | 2026-07-20 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005877 | 2026-07-20 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005878 | 2026-07-20 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 24 | 75 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005879 | 2026-07-20 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005880 | 2026-07-20 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005881 | 2026-07-20 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005882 | 2026-07-20 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18.5 | 97.5 | 1803.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005883 | 2026-07-20 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005884 | 2026-07-20 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 97.5 | 1267.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005885 | 2026-07-20 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005886 | 2026-07-20 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 29.5 | 75 | 2212.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005887 | 2026-07-20 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005888 | 2026-07-20 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005889 | 2026-07-20 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005890 | 2026-07-20 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005891 | 2026-07-20 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005892 | 2026-07-20 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 21 | 115 | 2415 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005893 | 2026-07-20 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 10.5 | 115 | 1207.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005894 | 2026-07-20 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005895 | 2026-07-20 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005896 | 2026-07-20 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005897 | 2026-07-20 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005898 | 2026-07-20 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005899 | 2026-07-20 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 87.5 | 87.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005900 | 2026-07-20 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP03 | Build, configuration and implementation | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005901 | 2026-07-20 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005902 | 2026-07-20 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005903 | 2026-07-20 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 60 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005904 | 2026-07-20 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005905 | 2026-07-20 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005906 | 2026-07-20 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005907 | 2026-07-27 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005908 | 2026-07-27 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005909 | 2026-07-27 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005910 | 2026-07-27 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005911 | 2026-07-27 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005912 | 2026-07-27 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005913 | 2026-07-27 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005914 | 2026-07-27 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005915 | 2026-07-27 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005916 | 2026-07-27 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005917 | 2026-07-27 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005918 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005919 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005920 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005921 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005922 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005923 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005924 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005925 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005926 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005927 | 2026-07-27 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005928 | 2026-07-27 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 80 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005929 | 2026-07-27 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005930 | 2026-07-27 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005931 | 2026-07-27 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005932 | 2026-07-27 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005933 | 2026-07-27 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005934 | 2026-07-27 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005935 | 2026-07-27 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005936 | 2026-07-27 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005937 | 2026-07-27 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005938 | 2026-07-27 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005939 | 2026-07-27 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005940 | 2026-07-27 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 62.5 | 1875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005941 | 2026-07-27 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005942 | 2026-07-27 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005943 | 2026-07-27 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005944 | 2026-07-27 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005945 | 2026-07-27 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005946 | 2026-07-27 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005947 | 2026-07-27 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005948 | 2026-07-27 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005949 | 2026-07-27 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005950 | 2026-07-27 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005951 | 2026-07-27 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005952 | 2026-07-27 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 55 | 1677.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005953 | 2026-07-27 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005954 | 2026-07-27 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005955 | 2026-07-27 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005956 | 2026-07-27 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005957 | 2026-07-27 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005958 | 2026-07-27 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005959 | 2026-07-27 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005960 | 2026-07-27 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005961 | 2026-07-27 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005962 | 2026-07-27 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005963 | 2026-07-27 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005964 | 2026-07-27 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005965 | 2026-07-27 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005966 | 2026-07-27 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005967 | 2026-07-27 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005968 | 2026-07-27 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31.5 | 157.5 | 4961.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005969 | 2026-07-27 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005970 | 2026-07-27 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005971 | 2026-07-27 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005972 | 2026-07-27 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005973 | 2026-07-27 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005974 | 2026-07-27 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005975 | 2026-07-27 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005976 | 2026-07-27 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005977 | 2026-07-27 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005978 | 2026-07-27 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 2 | 150 | 300 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005979 | 2026-07-27 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005980 | 2026-07-27 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 150 | 4800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005981 | 2026-07-27 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005982 | 2026-07-27 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005983 | 2026-07-27 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005984 | 2026-07-27 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005985 | 2026-07-27 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005986 | 2026-07-27 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005987 | 2026-07-27 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005988 | 2026-07-27 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005989 | 2026-07-27 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005990 | 2026-07-27 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005991 | 2026-07-27 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 12.5 | 105 | 1312.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005992 | 2026-07-27 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005993 | 2026-07-27 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 10 | 85 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005994 | 2026-07-27 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 9 | 85 | 765 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005995 | 2026-07-27 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4 | 85 | 340 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005996 | 2026-07-27 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 85 | 85 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005997 | 2026-07-27 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005998 | 2026-07-27 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21.5 | 82.5 | 1773.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-005999 | 2026-07-27 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18.5 | 82.5 | 1526.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006000 | 2026-07-27 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006001 | 2026-07-27 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Pending | Sara Khan | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006002 | 2026-07-27 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006003 | 2026-07-27 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006004 | 2026-07-27 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006005 | 2026-07-27 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006006 | 2026-07-27 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6.5 | 67.5 | 438.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006007 | 2026-07-27 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006008 | 2026-07-27 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006009 | 2026-07-27 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006010 | 2026-07-27 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006011 | 2026-07-27 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006012 | 2026-07-27 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006013 | 2026-07-27 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006014 | 2026-07-27 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006015 | 2026-07-27 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006016 | 2026-07-27 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006017 | 2026-07-27 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8.5 | 55 | 467.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006018 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006019 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006020 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006021 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006022 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006023 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006024 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006025 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006026 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006027 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006028 | 2026-07-27 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006029 | 2026-07-27 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 24.5 | 120 | 2940 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006030 | 2026-07-27 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006031 | 2026-07-27 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006032 | 2026-07-27 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006033 | 2026-07-27 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006034 | 2026-07-27 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006035 | 2026-07-27 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 30 | 100 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006036 | 2026-07-27 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006037 | 2026-07-27 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 100 | 200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006038 | 2026-07-27 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 28 | 75 | 2100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006039 | 2026-07-27 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006040 | 2026-07-27 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006041 | 2026-07-27 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 19 | 67.5 | 1282.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006042 | 2026-07-27 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 5 | 67.5 | 337.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006043 | 2026-07-27 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006044 | 2026-07-27 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 25.5 | 67.5 | 1721.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006045 | 2026-07-27 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006046 | 2026-07-27 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006047 | 2026-07-27 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 102.5 | 3280 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006048 | 2026-07-27 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7 | 102.5 | 717.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006049 | 2026-07-27 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 102.5 | 102.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006050 | 2026-07-27 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 77.5 | 2363.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006051 | 2026-07-27 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006052 | 2026-07-27 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 77.5 | 155 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006053 | 2026-07-27 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 65 | 1105 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006054 | 2026-07-27 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 65 | 455 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006055 | 2026-07-27 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006056 | 2026-07-27 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 17.5 | 117.5 | 2056.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006057 | 2026-07-27 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006058 | 2026-07-27 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006059 | 2026-07-27 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006060 | 2026-07-27 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15 | 82.5 | 1237.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006061 | 2026-07-27 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006062 | 2026-07-27 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006063 | 2026-07-27 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006064 | 2026-07-27 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006065 | 2026-07-27 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006066 | 2026-07-27 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 95 | 95 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006067 | 2026-07-27 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 21.5 | 60 | 1290 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006068 | 2026-07-27 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006069 | 2026-07-27 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 60 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006070 | 2026-07-27 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 90 | 1710 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006071 | 2026-07-27 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006072 | 2026-07-27 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP04 | Data integration, migration and validation | Yes | 8.5 | 90 | 765 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006073 | 2026-07-27 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP03 | Build, configuration and implementation | Yes | 18.5 | 62.5 | 1156.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006074 | 2026-07-27 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006075 | 2026-07-27 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006076 | 2026-07-27 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 62.5 | 93.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006077 | 2026-07-27 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006078 | 2026-07-27 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006079 | 2026-07-27 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006080 | 2026-07-27 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006081 | 2026-07-27 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006082 | 2026-07-27 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006083 | 2026-07-27 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006084 | 2026-07-27 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006085 | 2026-07-27 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006086 | 2026-07-27 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006087 | 2026-07-27 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006088 | 2026-07-27 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006089 | 2026-07-27 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 120 | 2880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006090 | 2026-07-27 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 12 | 120 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006091 | 2026-07-27 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006092 | 2026-07-27 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 27 | 100 | 2700 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006093 | 2026-07-27 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 12.5 | 100 | 1250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006094 | 2026-07-27 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 100 | 50 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006095 | 2026-07-27 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006096 | 2026-07-27 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006097 | 2026-07-27 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 67.5 | 1451.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006098 | 2026-07-27 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006099 | 2026-07-27 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006100 | 2026-07-27 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 21 | 75 | 1575 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006101 | 2026-07-27 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006102 | 2026-07-27 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 15 | 75 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006103 | 2026-07-27 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 4.5 | 75 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006104 | 2026-07-27 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 5 | 75 | 375 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006105 | 2026-07-27 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006106 | 2026-07-27 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006107 | 2026-07-27 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006108 | 2026-07-27 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 97.5 | 1121.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006109 | 2026-07-27 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 97.5 | 97.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006110 | 2026-07-27 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 30.5 | 75 | 2287.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006111 | 2026-07-27 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006112 | 2026-07-27 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006113 | 2026-07-27 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006114 | 2026-07-27 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006115 | 2026-07-27 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006116 | 2026-07-27 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18.5 | 115 | 2127.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006117 | 2026-07-27 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006118 | 2026-07-27 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006119 | 2026-07-27 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 115 | 230 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006120 | 2026-07-27 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006121 | 2026-07-27 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006122 | 2026-07-27 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006123 | 2026-07-27 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 87.5 | 87.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006124 | 2026-07-27 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006125 | 2026-07-27 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006126 | 2026-07-27 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006127 | 2026-07-27 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 60 | 1080 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006128 | 2026-07-27 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006129 | 2026-07-27 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006130 | 2026-07-27 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 60 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006131 | 2026-08-03 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006132 | 2026-08-03 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006133 | 2026-08-03 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006134 | 2026-08-03 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006135 | 2026-08-03 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006136 | 2026-08-03 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006137 | 2026-08-03 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006138 | 2026-08-03 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006139 | 2026-08-03 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006140 | 2026-08-03 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006141 | 2026-08-03 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006142 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006143 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006144 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006145 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006146 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006147 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006148 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006149 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006150 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006151 | 2026-08-03 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006152 | 2026-08-03 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 80 | 2440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006153 | 2026-08-03 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006154 | 2026-08-03 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006155 | 2026-08-03 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006156 | 2026-08-03 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006157 | 2026-08-03 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006158 | 2026-08-03 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006159 | 2026-08-03 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006160 | 2026-08-03 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006161 | 2026-08-03 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006162 | 2026-08-03 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006163 | 2026-08-03 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006164 | 2026-08-03 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006165 | 2026-08-03 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006166 | 2026-08-03 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006167 | 2026-08-03 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006168 | 2026-08-03 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006169 | 2026-08-03 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006170 | 2026-08-03 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006171 | 2026-08-03 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006172 | 2026-08-03 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006173 | 2026-08-03 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006174 | 2026-08-03 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006175 | 2026-08-03 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 55 | 1677.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006176 | 2026-08-03 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006177 | 2026-08-03 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006178 | 2026-08-03 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006179 | 2026-08-03 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006180 | 2026-08-03 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006181 | 2026-08-03 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006182 | 2026-08-03 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006183 | 2026-08-03 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006184 | 2026-08-03 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006185 | 2026-08-03 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006186 | 2026-08-03 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006187 | 2026-08-03 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006188 | 2026-08-03 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006189 | 2026-08-03 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006190 | 2026-08-03 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006191 | 2026-08-03 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31 | 157.5 | 4882.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006192 | 2026-08-03 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006193 | 2026-08-03 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006194 | 2026-08-03 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006195 | 2026-08-03 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006196 | 2026-08-03 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006197 | 2026-08-03 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006198 | 2026-08-03 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006199 | 2026-08-03 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006200 | 2026-08-03 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006201 | 2026-08-03 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 2 | 150 | 300 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006202 | 2026-08-03 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006203 | 2026-08-03 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32 | 150 | 4800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006204 | 2026-08-03 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006205 | 2026-08-03 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006206 | 2026-08-03 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006207 | 2026-08-03 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006208 | 2026-08-03 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006209 | 2026-08-03 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006210 | 2026-08-03 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006211 | 2026-08-03 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006212 | 2026-08-03 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006213 | 2026-08-03 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006214 | 2026-08-03 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006215 | 2026-08-03 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006216 | 2026-08-03 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006217 | 2026-08-03 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006218 | 2026-08-03 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006219 | 2026-08-03 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18.5 | 82.5 | 1526.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006220 | 2026-08-03 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006221 | 2026-08-03 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006222 | 2026-08-03 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006223 | 2026-08-03 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006224 | 2026-08-03 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006225 | 2026-08-03 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 4.5 | 67.5 | 303.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006226 | 2026-08-03 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 3 | 67.5 | 202.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006227 | 2026-08-03 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006228 | 2026-08-03 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006229 | 2026-08-03 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006230 | 2026-08-03 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006231 | 2026-08-03 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006232 | 2026-08-03 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006233 | 2026-08-03 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006234 | 2026-08-03 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006235 | 2026-08-03 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006236 | 2026-08-03 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006237 | 2026-08-03 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006238 | 2026-08-03 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 9 | 55 | 495 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006239 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006240 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006241 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006242 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006243 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006244 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006245 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006246 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006247 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006248 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006249 | 2026-08-03 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006250 | 2026-08-03 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006251 | 2026-08-03 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 12.5 | 120 | 1500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006252 | 2026-08-03 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006253 | 2026-08-03 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 27.5 | 100 | 2750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006254 | 2026-08-03 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006255 | 2026-08-03 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 100 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006256 | 2026-08-03 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 31.5 | 100 | 3150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006257 | 2026-08-03 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006258 | 2026-08-03 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006259 | 2026-08-03 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 75 | 337.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006260 | 2026-08-03 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006261 | 2026-08-03 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 12.5 | 67.5 | 843.75 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006262 | 2026-08-03 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 3 | 67.5 | 202.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006263 | 2026-08-03 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006264 | 2026-08-03 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 26.5 | 67.5 | 1788.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006265 | 2026-08-03 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006266 | 2026-08-03 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006267 | 2026-08-03 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 31.5 | 102.5 | 3228.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006268 | 2026-08-03 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 102.5 | 871.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006269 | 2026-08-03 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 77.5 | 1007.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006270 | 2026-08-03 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 3 | 77.5 | 232.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006271 | 2026-08-03 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006272 | 2026-08-03 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 65 | 1657.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006273 | 2026-08-03 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006274 | 2026-08-03 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 65 | 130 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006275 | 2026-08-03 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 17.5 | 117.5 | 2056.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006276 | 2026-08-03 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006277 | 2026-08-03 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006278 | 2026-08-03 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006279 | 2026-08-03 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 15.5 | 82.5 | 1278.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006280 | 2026-08-03 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 8 | 82.5 | 660 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006281 | 2026-08-03 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 95 | 1710 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006282 | 2026-08-03 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006283 | 2026-08-03 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006284 | 2026-08-03 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 95 | 237.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006285 | 2026-08-03 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 21.5 | 60 | 1290 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006286 | 2026-08-03 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 60 | 1020 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006287 | 2026-08-03 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006288 | 2026-08-03 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006289 | 2026-08-03 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006290 | 2026-08-03 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006291 | 2026-08-03 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006292 | 2026-08-03 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006293 | 2026-08-03 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 62.5 | 812.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006294 | 2026-08-03 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006295 | 2026-08-03 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006296 | 2026-08-03 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006297 | 2026-08-03 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006298 | 2026-08-03 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 62.5 | 62.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006299 | 2026-08-03 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006300 | 2026-08-03 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006301 | 2026-08-03 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006302 | 2026-08-03 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006303 | 2026-08-03 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006304 | 2026-08-03 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006305 | 2026-08-03 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006306 | 2026-08-03 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006307 | 2026-08-03 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006308 | 2026-08-03 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006309 | 2026-08-03 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 13 | 120 | 1560 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006310 | 2026-08-03 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006311 | 2026-08-03 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 100 | 2550 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006312 | 2026-08-03 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006313 | 2026-08-03 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006314 | 2026-08-03 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006315 | 2026-08-03 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006316 | 2026-08-03 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006317 | 2026-08-03 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006318 | 2026-08-03 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006319 | 2026-08-03 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8 | 67.5 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006320 | 2026-08-03 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006321 | 2026-08-03 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 21 | 75 | 1575 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006322 | 2026-08-03 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006323 | 2026-08-03 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 24.5 | 75 | 1837.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006324 | 2026-08-03 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006325 | 2026-08-03 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006326 | 2026-08-03 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006327 | 2026-08-03 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006328 | 2026-08-03 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 97.5 | 1218.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006329 | 2026-08-03 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006330 | 2026-08-03 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006331 | 2026-08-03 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006332 | 2026-08-03 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006333 | 2026-08-03 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006334 | 2026-08-03 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 18.5 | 115 | 2127.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006335 | 2026-08-03 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006336 | 2026-08-03 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006337 | 2026-08-03 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 115 | 230 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006338 | 2026-08-03 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006339 | 2026-08-03 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006340 | 2026-08-03 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006341 | 2026-08-03 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 87.5 | 218.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006342 | 2026-08-03 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006343 | 2026-08-03 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP03 | Build, configuration and implementation | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006344 | 2026-08-03 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006345 | 2026-08-03 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 60 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006346 | 2026-08-03 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 60 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006347 | 2026-08-03 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 60 | 690 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006348 | 2026-08-10 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006349 | 2026-08-10 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006350 | 2026-08-10 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006351 | 2026-08-10 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006352 | 2026-08-10 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006353 | 2026-08-10 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006354 | 2026-08-10 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006355 | 2026-08-10 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006356 | 2026-08-10 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006357 | 2026-08-10 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006358 | 2026-08-10 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 97.5 | 2632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006359 | 2026-08-10 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006360 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006361 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006362 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006363 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006364 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006365 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006366 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006367 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006368 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006369 | 2026-08-10 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006370 | 2026-08-10 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 80 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006371 | 2026-08-10 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006372 | 2026-08-10 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006373 | 2026-08-10 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006374 | 2026-08-10 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006375 | 2026-08-10 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006376 | 2026-08-10 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006377 | 2026-08-10 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006378 | 2026-08-10 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006379 | 2026-08-10 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006380 | 2026-08-10 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006381 | 2026-08-10 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006382 | 2026-08-10 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 22 | 62.5 | 1375 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006383 | 2026-08-10 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006384 | 2026-08-10 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006385 | 2026-08-10 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006386 | 2026-08-10 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006387 | 2026-08-10 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006388 | 2026-08-10 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006389 | 2026-08-10 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006390 | 2026-08-10 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006391 | 2026-08-10 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006392 | 2026-08-10 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006393 | 2026-08-10 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006394 | 2026-08-10 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006395 | 2026-08-10 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006396 | 2026-08-10 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 55 | 1485 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006397 | 2026-08-10 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006398 | 2026-08-10 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006399 | 2026-08-10 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006400 | 2026-08-10 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006401 | 2026-08-10 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006402 | 2026-08-10 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 28 | 187.5 | 5250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006403 | 2026-08-10 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006404 | 2026-08-10 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006405 | 2026-08-10 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006406 | 2026-08-10 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006407 | 2026-08-10 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006408 | 2026-08-10 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006409 | 2026-08-10 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006410 | 2026-08-10 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006411 | 2026-08-10 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006412 | 2026-08-10 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006413 | 2026-08-10 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006414 | 2026-08-10 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 27 | 157.5 | 4252.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006415 | 2026-08-10 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006416 | 2026-08-10 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006417 | 2026-08-10 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006418 | 2026-08-10 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006419 | 2026-08-10 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006420 | 2026-08-10 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006421 | 2026-08-10 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 11 | 162.5 | 1787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006422 | 2026-08-10 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006423 | 2026-08-10 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006424 | 2026-08-10 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006425 | 2026-08-10 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006426 | 2026-08-10 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006427 | 2026-08-10 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006428 | 2026-08-10 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 150 | 75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006429 | 2026-08-10 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 13.5 | 150 | 2025 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006430 | 2026-08-10 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006431 | 2026-08-10 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006432 | 2026-08-10 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006433 | 2026-08-10 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006434 | 2026-08-10 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006435 | 2026-08-10 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006436 | 2026-08-10 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006437 | 2026-08-10 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006438 | 2026-08-10 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006439 | 2026-08-10 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006440 | 2026-08-10 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006441 | 2026-08-10 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006442 | 2026-08-10 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 105 | 1785 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006443 | 2026-08-10 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006444 | 2026-08-10 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 13.5 | 85 | 1147.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006445 | 2026-08-10 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 13.5 | 85 | 1147.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006446 | 2026-08-10 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5 | 85 | 425 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006447 | 2026-08-10 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006448 | 2026-08-10 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 16 | 82.5 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006449 | 2026-08-10 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 14.5 | 82.5 | 1196.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006450 | 2026-08-10 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006451 | 2026-08-10 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006452 | 2026-08-10 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 16.5 | 67.5 | 1113.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006453 | 2026-08-10 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 15.5 | 67.5 | 1046.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006454 | 2026-08-10 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006455 | 2026-08-10 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 15 | 67.5 | 1012.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006456 | 2026-08-10 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 10.5 | 67.5 | 708.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006457 | 2026-08-10 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 6 | 67.5 | 405 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006458 | 2026-08-10 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006459 | 2026-08-10 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006460 | 2026-08-10 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006461 | 2026-08-10 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006462 | 2026-08-10 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006463 | 2026-08-10 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006464 | 2026-08-10 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006465 | 2026-08-10 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006466 | 2026-08-10 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006467 | 2026-08-10 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006468 | 2026-08-10 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006469 | 2026-08-10 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006470 | 2026-08-10 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 7 | 55 | 385 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006471 | 2026-08-10 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006472 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006473 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006474 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006475 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006476 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006477 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006478 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006479 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006480 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006481 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006482 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 65 | 1105 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006483 | 2026-08-10 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006484 | 2026-08-10 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 120 | 2520 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006485 | 2026-08-10 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP04 | Data integration, migration and validation | Yes | 9 | 120 | 1080 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006486 | 2026-08-10 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 120 | 240 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006487 | 2026-08-10 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006488 | 2026-08-10 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 22.5 | 100 | 2250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006489 | 2026-08-10 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 100 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006490 | 2026-08-10 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006491 | 2026-08-10 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006492 | 2026-08-10 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 25 | 100 | 2500 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006493 | 2026-08-10 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 7 | 100 | 700 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006494 | 2026-08-10 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006495 | 2026-08-10 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 75 | 1612.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006496 | 2026-08-10 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 75 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006497 | 2026-08-10 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006498 | 2026-08-10 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006499 | 2026-08-10 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 24 | 67.5 | 1620 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006500 | 2026-08-10 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 6 | 67.5 | 405 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006501 | 2026-08-10 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006502 | 2026-08-10 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006503 | 2026-08-10 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 22.5 | 67.5 | 1518.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006504 | 2026-08-10 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 9.5 | 67.5 | 641.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006505 | 2026-08-10 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006506 | 2026-08-10 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 102.5 | 2613.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006507 | 2026-08-10 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 102.5 | 666.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006508 | 2026-08-10 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006509 | 2026-08-10 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 77.5 | 930 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006510 | 2026-08-10 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 3.5 | 77.5 | 271.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006511 | 2026-08-10 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 77.5 | 38.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006512 | 2026-08-10 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006513 | 2026-08-10 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006514 | 2026-08-10 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 22.5 | 65 | 1462.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006515 | 2026-08-10 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 65 | 617.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006516 | 2026-08-10 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006517 | 2026-08-10 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 117.5 | 1468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006518 | 2026-08-10 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 117.5 | 1468.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006519 | 2026-08-10 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 117.5 | 822.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006520 | 2026-08-10 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006521 | 2026-08-10 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 82.5 | 536.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006522 | 2026-08-10 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 82.5 | 536.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006523 | 2026-08-10 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 3.5 | 82.5 | 288.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006524 | 2026-08-10 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006525 | 2026-08-10 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006526 | 2026-08-10 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006527 | 2026-08-10 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 95 | 475 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006528 | 2026-08-10 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 3 | 95 | 285 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006529 | 2026-08-10 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006530 | 2026-08-10 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006531 | 2026-08-10 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 19.5 | 60 | 1170 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006532 | 2026-08-10 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 60 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006533 | 2026-08-10 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006534 | 2026-08-10 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 90 | 1395 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006535 | 2026-08-10 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 90 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006536 | 2026-08-10 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 90 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006537 | 2026-08-10 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006538 | 2026-08-10 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006539 | 2026-08-10 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 62.5 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006540 | 2026-08-10 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006541 | 2026-08-10 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 6 | 62.5 | 375 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006542 | 2026-08-10 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006543 | 2026-08-10 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 13.5 | 62.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006544 | 2026-08-10 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 62.5 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006545 | 2026-08-10 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 10 | 62.5 | 625 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006546 | 2026-08-10 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006547 | 2026-08-10 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006548 | 2026-08-10 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006549 | 2026-08-10 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006550 | 2026-08-10 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006551 | 2026-08-10 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 72.5 | 108.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006552 | 2026-08-10 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 72.5 | 108.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006553 | 2026-08-10 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 13 | 72.5 | 942.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006554 | 2026-08-10 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006555 | 2026-08-10 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006556 | 2026-08-10 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006557 | 2026-08-10 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006558 | 2026-08-10 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006559 | 2026-08-10 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006560 | 2026-08-10 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006561 | 2026-08-10 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006562 | 2026-08-10 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 120 | 2160 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006563 | 2026-08-10 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 9 | 120 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006564 | 2026-08-10 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006565 | 2026-08-10 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006566 | 2026-08-10 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006567 | 2026-08-10 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 22.5 | 100 | 2250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006568 | 2026-08-10 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 9.5 | 100 | 950 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006569 | 2026-08-10 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006570 | 2026-08-10 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 15.5 | 90 | 1395 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006571 | 2026-08-10 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 16.5 | 90 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006572 | 2026-08-10 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006573 | 2026-08-10 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 67.5 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006574 | 2026-08-10 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 9.5 | 67.5 | 641.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006575 | 2026-08-10 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 6.5 | 67.5 | 438.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006576 | 2026-08-10 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006577 | 2026-08-10 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 15.5 | 75 | 1162.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006578 | 2026-08-10 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 16.5 | 75 | 1237.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006579 | 2026-08-10 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006580 | 2026-08-10 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 17.5 | 75 | 1312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006581 | 2026-08-10 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 6 | 75 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006582 | 2026-08-10 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 6 | 75 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006583 | 2026-08-10 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006584 | 2026-08-10 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006585 | 2026-08-10 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 97.5 | 1608.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006586 | 2026-08-10 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 6.5 | 97.5 | 633.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006587 | 2026-08-10 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006588 | 2026-08-10 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006589 | 2026-08-10 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006590 | 2026-08-10 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 75 | 1912.5 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006591 | 2026-08-10 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 6.5 | 75 | 487.5 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006592 | 2026-08-10 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006593 | 2026-08-10 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 67.5 | 270 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006594 | 2026-08-10 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 2.5 | 67.5 | 168.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006595 | 2026-08-10 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 1.5 | 67.5 | 101.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006596 | 2026-08-10 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006597 | 2026-08-10 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006598 | 2026-08-10 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 115 | 1782.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006599 | 2026-08-10 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 115 | 1150 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006600 | 2026-08-10 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006601 | 2026-08-10 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006602 | 2026-08-10 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 87.5 | 1400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006603 | 2026-08-10 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 87.5 | 875 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006604 | 2026-08-10 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP03 | Build, configuration and implementation | Yes | 5.5 | 87.5 | 481.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006605 | 2026-08-10 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006606 | 2026-08-10 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006607 | 2026-08-10 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 90 | 1305 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006608 | 2026-08-10 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 90 | 585 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006609 | 2026-08-10 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 90 | 900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006610 | 2026-08-10 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006611 | 2026-08-10 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006612 | 2026-08-10 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 60 | 990 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006613 | 2026-08-10 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 60 | 360 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006614 | 2026-08-10 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 9.5 | 60 | 570 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006615 | 2026-08-10 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006616 | 2026-08-17 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006617 | 2026-08-17 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006618 | 2026-08-17 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006619 | 2026-08-17 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006620 | 2026-08-17 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006621 | 2026-08-17 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006622 | 2026-08-17 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006623 | 2026-08-17 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006624 | 2026-08-17 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006625 | 2026-08-17 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006626 | 2026-08-17 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006627 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006628 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006629 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006630 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006631 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006632 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006633 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006634 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006635 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006636 | 2026-08-17 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006637 | 2026-08-17 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 80 | 2440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006638 | 2026-08-17 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006639 | 2026-08-17 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006640 | 2026-08-17 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006641 | 2026-08-17 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006642 | 2026-08-17 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006643 | 2026-08-17 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006644 | 2026-08-17 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006645 | 2026-08-17 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006646 | 2026-08-17 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006647 | 2026-08-17 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006648 | 2026-08-17 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 18 | 62.5 | 1125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006649 | 2026-08-17 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006650 | 2026-08-17 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 57.5 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006651 | 2026-08-17 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006652 | 2026-08-17 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006653 | 2026-08-17 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006654 | 2026-08-17 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006655 | 2026-08-17 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006656 | 2026-08-17 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006657 | 2026-08-17 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006658 | 2026-08-17 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006659 | 2026-08-17 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006660 | 2026-08-17 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006661 | 2026-08-17 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006662 | 2026-08-17 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006663 | 2026-08-17 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006664 | 2026-08-17 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006665 | 2026-08-17 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006666 | 2026-08-17 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006667 | 2026-08-17 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006668 | 2026-08-17 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006669 | 2026-08-17 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006670 | 2026-08-17 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006671 | 2026-08-17 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006672 | 2026-08-17 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006673 | 2026-08-17 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006674 | 2026-08-17 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006675 | 2026-08-17 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006676 | 2026-08-17 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006677 | 2026-08-17 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006678 | 2026-08-17 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30.5 | 157.5 | 4803.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006679 | 2026-08-17 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006680 | 2026-08-17 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006681 | 2026-08-17 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006682 | 2026-08-17 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006683 | 2026-08-17 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 162.5 | 162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006684 | 2026-08-17 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 17.5 | 162.5 | 2843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006685 | 2026-08-17 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006686 | 2026-08-17 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006687 | 2026-08-17 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006688 | 2026-08-17 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006689 | 2026-08-17 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006690 | 2026-08-17 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006691 | 2026-08-17 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006692 | 2026-08-17 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006693 | 2026-08-17 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006694 | 2026-08-17 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006695 | 2026-08-17 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006696 | 2026-08-17 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006697 | 2026-08-17 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006698 | 2026-08-17 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006699 | 2026-08-17 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006700 | 2026-08-17 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006701 | 2026-08-17 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006702 | 2026-08-17 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006703 | 2026-08-17 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006704 | 2026-08-17 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006705 | 2026-08-17 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006706 | 2026-08-17 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006707 | 2026-08-17 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006708 | 2026-08-17 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006709 | 2026-08-17 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 16 | 67.5 | 1080 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006710 | 2026-08-17 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 16 | 67.5 | 1080 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006711 | 2026-08-17 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006712 | 2026-08-17 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006713 | 2026-08-17 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006714 | 2026-08-17 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006715 | 2026-08-17 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006716 | 2026-08-17 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006717 | 2026-08-17 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006718 | 2026-08-17 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006719 | 2026-08-17 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006720 | 2026-08-17 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006721 | 2026-08-17 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006722 | 2026-08-17 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006723 | 2026-08-17 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006724 | 2026-08-17 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006725 | 2026-08-17 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006726 | 2026-08-17 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4 | 55 | 220 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006727 | 2026-08-17 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006728 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006729 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006730 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006731 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006732 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006733 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006734 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006735 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006736 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006737 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006738 | 2026-08-17 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006739 | 2026-08-17 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 120 | 3120 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006740 | 2026-08-17 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006741 | 2026-08-17 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 120 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006742 | 2026-08-17 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006743 | 2026-08-17 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006744 | 2026-08-17 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006745 | 2026-08-17 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 100 | 3250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006746 | 2026-08-17 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006747 | 2026-08-17 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 29.5 | 75 | 2212.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006748 | 2026-08-17 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 10.5 | 75 | 787.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006749 | 2026-08-17 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 67.5 | 1316.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006750 | 2026-08-17 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 4.5 | 67.5 | 303.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006751 | 2026-08-17 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006752 | 2026-08-17 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 29 | 67.5 | 1957.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006753 | 2026-08-17 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006754 | 2026-08-17 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 102.5 | 3331.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006755 | 2026-08-17 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006756 | 2026-08-17 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 77.5 | 2480 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006757 | 2026-08-17 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 77.5 | 542.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006758 | 2026-08-17 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 77.5 | 77.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006759 | 2026-08-17 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 28.5 | 65 | 1852.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006760 | 2026-08-17 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 65 | 715 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006761 | 2026-08-17 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 65 | 32.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006762 | 2026-08-17 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006763 | 2026-08-17 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006764 | 2026-08-17 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 117.5 | 822.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006765 | 2026-08-17 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 117.5 | 293.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006766 | 2026-08-17 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 82.5 | 1361.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006767 | 2026-08-17 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 82.5 | 1320 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006768 | 2026-08-17 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 82.5 | 618.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006769 | 2026-08-17 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006770 | 2026-08-17 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006771 | 2026-08-17 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006772 | 2026-08-17 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 24.5 | 60 | 1470 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006773 | 2026-08-17 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 60 | 930 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006774 | 2026-08-17 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006775 | 2026-08-17 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006776 | 2026-08-17 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006777 | 2026-08-17 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006778 | 2026-08-17 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 62.5 | 781.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006779 | 2026-08-17 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006780 | 2026-08-17 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 62.5 | 406.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006781 | 2026-08-17 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 62.5 | 312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006782 | 2026-08-17 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 5 | 62.5 | 312.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006783 | 2026-08-17 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006784 | 2026-08-17 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006785 | 2026-08-17 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006786 | 2026-08-17 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006787 | 2026-08-17 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006788 | 2026-08-17 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006789 | 2026-08-17 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006790 | 2026-08-17 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006791 | 2026-08-17 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006792 | 2026-08-17 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006793 | 2026-08-17 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 120 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006794 | 2026-08-17 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 4.5 | 120 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006795 | 2026-08-17 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 1.5 | 120 | 180 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006796 | 2026-08-17 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006797 | 2026-08-17 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006798 | 2026-08-17 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006799 | 2026-08-17 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 20 | 90 | 1800 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006800 | 2026-08-17 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 18 | 90 | 1620 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006801 | 2026-08-17 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006802 | 2026-08-17 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 67.5 | 1417.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006803 | 2026-08-17 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006804 | 2026-08-17 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006805 | 2026-08-17 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006806 | 2026-08-17 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006807 | 2026-08-17 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006808 | 2026-08-17 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP04 | Data integration, migration and validation | Yes | 22 | 75 | 1650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006809 | 2026-08-17 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006810 | 2026-08-17 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006811 | 2026-08-17 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006812 | 2026-08-17 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 97.5 | 2047.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006813 | 2026-08-17 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP03 | Build, configuration and implementation | Yes | 7 | 97.5 | 682.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006814 | 2026-08-17 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 97.5 | 1121.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006815 | 2026-08-17 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 97.5 | 48.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006816 | 2026-08-17 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006817 | 2026-08-17 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006818 | 2026-08-17 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006819 | 2026-08-17 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006820 | 2026-08-17 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 67.5 | 337.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006821 | 2026-08-17 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006822 | 2026-08-17 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006823 | 2026-08-17 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006824 | 2026-08-17 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006825 | 2026-08-17 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 87.5 | 1487.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006826 | 2026-08-17 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006827 | 2026-08-17 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 87.5 | 525 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006828 | 2026-08-17 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006829 | 2026-08-17 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006830 | 2026-08-17 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006831 | 2026-08-17 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006832 | 2026-08-17 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006833 | 2026-08-17 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 60 | 1230 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006834 | 2026-08-17 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006835 | 2026-08-17 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006836 | 2026-08-24 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006837 | 2026-08-24 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006838 | 2026-08-24 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006839 | 2026-08-24 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006840 | 2026-08-24 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006841 | 2026-08-24 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006842 | 2026-08-24 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006843 | 2026-08-24 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006844 | 2026-08-24 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006845 | 2026-08-24 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006846 | 2026-08-24 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 27 | 97.5 | 2632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006847 | 2026-08-24 | E001 | Sophie Lambert | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006848 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006849 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006850 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006851 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006852 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006853 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006854 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006855 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006856 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006857 | 2026-08-24 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006858 | 2026-08-24 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006859 | 2026-08-24 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006860 | 2026-08-24 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006861 | 2026-08-24 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006862 | 2026-08-24 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006863 | 2026-08-24 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006864 | 2026-08-24 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006865 | 2026-08-24 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006866 | 2026-08-24 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006867 | 2026-08-24 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006868 | 2026-08-24 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006869 | 2026-08-24 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29 | 62.5 | 1812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006870 | 2026-08-24 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006871 | 2026-08-24 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006872 | 2026-08-24 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006873 | 2026-08-24 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006874 | 2026-08-24 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006875 | 2026-08-24 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006876 | 2026-08-24 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006877 | 2026-08-24 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006878 | 2026-08-24 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006879 | 2026-08-24 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006880 | 2026-08-24 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006881 | 2026-08-24 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 55 | 1732.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006882 | 2026-08-24 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006883 | 2026-08-24 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006884 | 2026-08-24 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006885 | 2026-08-24 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006886 | 2026-08-24 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006887 | 2026-08-24 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006888 | 2026-08-24 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006889 | 2026-08-24 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006890 | 2026-08-24 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006891 | 2026-08-24 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006892 | 2026-08-24 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006893 | 2026-08-24 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006894 | 2026-08-24 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006895 | 2026-08-24 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006896 | 2026-08-24 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006897 | 2026-08-24 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31 | 157.5 | 4882.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006898 | 2026-08-24 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006899 | 2026-08-24 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006900 | 2026-08-24 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006901 | 2026-08-24 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006902 | 2026-08-24 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006903 | 2026-08-24 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006904 | 2026-08-24 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006905 | 2026-08-24 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006906 | 2026-08-24 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006907 | 2026-08-24 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006908 | 2026-08-24 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006909 | 2026-08-24 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006910 | 2026-08-24 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006911 | 2026-08-24 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006912 | 2026-08-24 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006913 | 2026-08-24 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006914 | 2026-08-24 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006915 | 2026-08-24 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006916 | 2026-08-24 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 0.5 | 105 | 52.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006917 | 2026-08-24 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006918 | 2026-08-24 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006919 | 2026-08-24 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006920 | 2026-08-24 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6.5 | 105 | 682.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006921 | 2026-08-24 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006922 | 2026-08-24 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006923 | 2026-08-24 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006924 | 2026-08-24 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006925 | 2026-08-24 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 23 | 82.5 | 1897.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006926 | 2026-08-24 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006927 | 2026-08-24 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006928 | 2026-08-24 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006929 | 2026-08-24 | E013 | Sara Khan | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006930 | 2026-08-24 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006931 | 2026-08-24 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006932 | 2026-08-24 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006933 | 2026-08-24 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006934 | 2026-08-24 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006935 | 2026-08-24 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006936 | 2026-08-24 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006937 | 2026-08-24 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006938 | 2026-08-24 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006939 | 2026-08-24 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006940 | 2026-08-24 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006941 | 2026-08-24 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006942 | 2026-08-24 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006943 | 2026-08-24 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 5.5 | 55 | 302.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006944 | 2026-08-24 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006945 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006946 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006947 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006948 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006949 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006950 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006951 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006952 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006953 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006954 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006955 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 13.5 | 65 | 877.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006956 | 2026-08-24 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006957 | 2026-08-24 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 23 | 120 | 2760 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006958 | 2026-08-24 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 120 | 1380 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006959 | 2026-08-24 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 100 | 2900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006960 | 2026-08-24 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006961 | 2026-08-24 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006962 | 2026-08-24 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006963 | 2026-08-24 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006964 | 2026-08-24 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006965 | 2026-08-24 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 75 | 1162.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006966 | 2026-08-24 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 75 | 487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006967 | 2026-08-24 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006968 | 2026-08-24 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006969 | 2026-08-24 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006970 | 2026-08-24 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006971 | 2026-08-24 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 29.5 | 67.5 | 1991.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006972 | 2026-08-24 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 10.5 | 67.5 | 708.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006973 | 2026-08-24 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 29.5 | 102.5 | 3023.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006974 | 2026-08-24 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 102.5 | 820 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006975 | 2026-08-24 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 102.5 | 256.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006976 | 2026-08-24 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 77.5 | 2363.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006977 | 2026-08-24 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 77.5 | 658.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006978 | 2026-08-24 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 77.5 | 77.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006979 | 2026-08-24 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 65 | 1007.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006980 | 2026-08-24 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 65 | 422.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006981 | 2026-08-24 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 65 | 130 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006982 | 2026-08-24 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006983 | 2026-08-24 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 117.5 | 1057.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006984 | 2026-08-24 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 10 | 117.5 | 1175 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006985 | 2026-08-24 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 117.5 | 587.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006986 | 2026-08-24 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006987 | 2026-08-24 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 9.5 | 82.5 | 783.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006988 | 2026-08-24 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 82.5 | 783.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006989 | 2026-08-24 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 82.5 | 371.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006990 | 2026-08-24 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006991 | 2026-08-24 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006992 | 2026-08-24 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006993 | 2026-08-24 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006994 | 2026-08-24 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006995 | 2026-08-24 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 60 | 1470 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006996 | 2026-08-24 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006997 | 2026-08-24 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006998 | 2026-08-24 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-006999 | 2026-08-24 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 90 | 315 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007000 | 2026-08-24 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007001 | 2026-08-24 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 62.5 | 906.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007002 | 2026-08-24 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007003 | 2026-08-24 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 62.5 | 406.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007004 | 2026-08-24 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 62.5 | 125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007005 | 2026-08-24 | E031 | Lucie Pereira | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007006 | 2026-08-24 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 62.5 | 968.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007007 | 2026-08-24 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007008 | 2026-08-24 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007009 | 2026-08-24 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007010 | 2026-08-24 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007011 | 2026-08-24 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007012 | 2026-08-24 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007013 | 2026-08-24 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007014 | 2026-08-24 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007015 | 2026-08-24 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007016 | 2026-08-24 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007017 | 2026-08-24 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007018 | 2026-08-24 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007019 | 2026-08-24 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 11 | 120 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007020 | 2026-08-24 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007021 | 2026-08-24 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 120 | 240 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007022 | 2026-08-24 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 27.5 | 100 | 2750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007023 | 2026-08-24 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12.5 | 100 | 1250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007024 | 2026-08-24 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007025 | 2026-08-24 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007026 | 2026-08-24 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007027 | 2026-08-24 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 67.5 | 1417.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007028 | 2026-08-24 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 10.5 | 67.5 | 708.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007029 | 2026-08-24 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007030 | 2026-08-24 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007031 | 2026-08-24 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007032 | 2026-08-24 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007033 | 2026-08-24 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 75 | 1837.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007034 | 2026-08-24 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007035 | 2026-08-24 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007036 | 2026-08-24 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 97.5 | 1170 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007037 | 2026-08-24 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 97.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007038 | 2026-08-24 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007039 | 2026-08-24 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 97.5 | 390 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007040 | 2026-08-24 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007041 | 2026-08-24 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007042 | 2026-08-24 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007043 | 2026-08-24 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007044 | 2026-08-24 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007045 | 2026-08-24 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007046 | 2026-08-24 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007047 | 2026-08-24 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007048 | 2026-08-24 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 115 | 2357.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007049 | 2026-08-24 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007050 | 2026-08-24 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007051 | 2026-08-24 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007052 | 2026-08-24 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 87.5 | 1706.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007053 | 2026-08-24 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 87.5 | 1093.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007054 | 2026-08-24 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007055 | 2026-08-24 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007056 | 2026-08-24 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007057 | 2026-08-24 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007058 | 2026-08-24 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007059 | 2026-08-24 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 60 | 1140 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007060 | 2026-08-24 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 60 | 450 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007061 | 2026-08-24 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12.5 | 60 | 750 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007062 | 2026-08-24 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007063 | 2026-08-31 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007064 | 2026-08-31 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007065 | 2026-08-31 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007066 | 2026-08-31 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007067 | 2026-08-31 | E001 | Sophie Lambert | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007068 | 2026-08-31 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007069 | 2026-08-31 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007070 | 2026-08-31 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007071 | 2026-08-31 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007072 | 2026-08-31 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007073 | 2026-08-31 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35 | 97.5 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007074 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007075 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007076 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007077 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007078 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007079 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007080 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007081 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007082 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007083 | 2026-08-31 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007084 | 2026-08-31 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 80 | 2480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007085 | 2026-08-31 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007086 | 2026-08-31 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007087 | 2026-08-31 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007088 | 2026-08-31 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007089 | 2026-08-31 | E003 | Elena Rossi | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007090 | 2026-08-31 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007091 | 2026-08-31 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007092 | 2026-08-31 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007093 | 2026-08-31 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007094 | 2026-08-31 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007095 | 2026-08-31 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28 | 62.5 | 1750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007096 | 2026-08-31 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007097 | 2026-08-31 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007098 | 2026-08-31 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007099 | 2026-08-31 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007100 | 2026-08-31 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007101 | 2026-08-31 | E005 | Nadia Benali | Finance | P005 | Cloud Landing Zone | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007102 | 2026-08-31 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007103 | 2026-08-31 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007104 | 2026-08-31 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007105 | 2026-08-31 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007106 | 2026-08-31 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007107 | 2026-08-31 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007108 | 2026-08-31 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007109 | 2026-08-31 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007110 | 2026-08-31 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007111 | 2026-08-31 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007112 | 2026-08-31 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007113 | 2026-08-31 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007114 | 2026-08-31 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007115 | 2026-08-31 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007116 | 2026-08-31 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007117 | 2026-08-31 | E007 | Claire Muller | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007118 | 2026-08-31 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007119 | 2026-08-31 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007120 | 2026-08-31 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007121 | 2026-08-31 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007122 | 2026-08-31 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007123 | 2026-08-31 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 19 | 157.5 | 2992.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007124 | 2026-08-31 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007125 | 2026-08-31 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007126 | 2026-08-31 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007127 | 2026-08-31 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007128 | 2026-08-31 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007129 | 2026-08-31 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007130 | 2026-08-31 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24.5 | 162.5 | 3981.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007131 | 2026-08-31 | E008 | Luca Conti | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007132 | 2026-08-31 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007133 | 2026-08-31 | E009 | Amélie Dubois | Executive | P005 | Cloud Landing Zone | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007134 | 2026-08-31 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007135 | 2026-08-31 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007136 | 2026-08-31 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007137 | 2026-08-31 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 150 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007138 | 2026-08-31 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007139 | 2026-08-31 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007140 | 2026-08-31 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007141 | 2026-08-31 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007142 | 2026-08-31 | E010 | David Martin | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007143 | 2026-08-31 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007144 | 2026-08-31 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007145 | 2026-08-31 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007146 | 2026-08-31 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007147 | 2026-08-31 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007148 | 2026-08-31 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 105 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007149 | 2026-08-31 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007150 | 2026-08-31 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007151 | 2026-08-31 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 5.5 | 85 | 467.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007152 | 2026-08-31 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 85 | 42.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007153 | 2026-08-31 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20 | 82.5 | 1650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007154 | 2026-08-31 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 19 | 82.5 | 1567.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007155 | 2026-08-31 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007156 | 2026-08-31 | E013 | Sara Khan | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007157 | 2026-08-31 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007158 | 2026-08-31 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007159 | 2026-08-31 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 13 | 67.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007160 | 2026-08-31 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007161 | 2026-08-31 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007162 | 2026-08-31 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007163 | 2026-08-31 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007164 | 2026-08-31 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007165 | 2026-08-31 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007166 | 2026-08-31 | E015 | Inès Petit | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007167 | 2026-08-31 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007168 | 2026-08-31 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007169 | 2026-08-31 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007170 | 2026-08-31 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007171 | 2026-08-31 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007172 | 2026-08-31 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6 | 55 | 330 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007173 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007174 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007175 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007176 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007177 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P005 | Cloud Landing Zone | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007178 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007179 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007180 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007181 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007182 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007183 | 2026-08-31 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 65 | 1300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007184 | 2026-08-31 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 22.5 | 120 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007185 | 2026-08-31 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007186 | 2026-08-31 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 120 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007187 | 2026-08-31 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 100 | 1600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007188 | 2026-08-31 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007189 | 2026-08-31 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 100 | 700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007190 | 2026-08-31 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007191 | 2026-08-31 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007192 | 2026-08-31 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007193 | 2026-08-31 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 75 | 2175 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007194 | 2026-08-31 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007195 | 2026-08-31 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 67.5 | 2126.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007196 | 2026-08-31 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 8.5 | 67.5 | 573.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007197 | 2026-08-31 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 27.5 | 67.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007198 | 2026-08-31 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007199 | 2026-08-31 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007200 | 2026-08-31 | E023 | Mila Costa | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 31 | 102.5 | 3177.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007201 | 2026-08-31 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 102.5 | 768.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007202 | 2026-08-31 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 102.5 | 563.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007203 | 2026-08-31 | E024 | Louis Fontaine | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 77.5 | 2518.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007204 | 2026-08-31 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 77.5 | 581.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007205 | 2026-08-31 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 77.5 | 310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007206 | 2026-08-31 | E025 | Camille Garcia | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 27.5 | 65 | 1787.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007207 | 2026-08-31 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 65 | 812.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007208 | 2026-08-31 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007209 | 2026-08-31 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007210 | 2026-08-31 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 117.5 | 822.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007211 | 2026-08-31 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 117.5 | 176.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007212 | 2026-08-31 | E027 | Emma Lopez | Cybersecurity | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 82.5 | 495 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007213 | 2026-08-31 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 82.5 | 495 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007214 | 2026-08-31 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 82.5 | 288.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007215 | 2026-08-31 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007216 | 2026-08-31 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007217 | 2026-08-31 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007218 | 2026-08-31 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 95 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007219 | 2026-08-31 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 95 | 665 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007220 | 2026-08-31 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 60 | 870 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007221 | 2026-08-31 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 60 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007222 | 2026-08-31 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007223 | 2026-08-31 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007224 | 2026-08-31 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007225 | 2026-08-31 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007226 | 2026-08-31 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 90 | 315 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007227 | 2026-08-31 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007228 | 2026-08-31 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 62.5 | 1312.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007229 | 2026-08-31 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 62.5 | 687.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007230 | 2026-08-31 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007231 | 2026-08-31 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007232 | 2026-08-31 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 62.5 | 1000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007233 | 2026-08-31 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 62.5 | 687.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007234 | 2026-08-31 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007235 | 2026-08-31 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 62.5 | 62.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007236 | 2026-08-31 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007237 | 2026-08-31 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007238 | 2026-08-31 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007239 | 2026-08-31 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007240 | 2026-08-31 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007241 | 2026-08-31 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007242 | 2026-08-31 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007243 | 2026-08-31 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007244 | 2026-08-31 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007245 | 2026-08-31 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 120 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007246 | 2026-08-31 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 7 | 120 | 840 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007247 | 2026-08-31 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 2 | 120 | 240 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007248 | 2026-08-31 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007249 | 2026-08-31 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 100 | 2850 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007250 | 2026-08-31 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 11.5 | 100 | 1150 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007251 | 2026-08-31 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP04 | Data integration, migration and validation | Yes | 15.5 | 90 | 1395 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007252 | 2026-08-31 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 15 | 90 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007253 | 2026-08-31 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007254 | 2026-08-31 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007255 | 2026-08-31 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007256 | 2026-08-31 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007257 | 2026-08-31 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007258 | 2026-08-31 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007259 | 2026-08-31 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007260 | 2026-08-31 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007261 | 2026-08-31 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007262 | 2026-08-31 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007263 | 2026-08-31 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007264 | 2026-08-31 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 97.5 | 1803.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007265 | 2026-08-31 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007266 | 2026-08-31 | E044 | Yanis Vidal | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 97.5 | 1218.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007267 | 2026-08-31 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 97.5 | 146.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007268 | 2026-08-31 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 75 | 2250 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007269 | 2026-08-31 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 75 | 637.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007270 | 2026-08-31 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007271 | 2026-08-31 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007272 | 2026-08-31 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007273 | 2026-08-31 | E046 | Alexandre Blanc | Cloud & Platform | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007274 | 2026-08-31 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 115 | 2357.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007275 | 2026-08-31 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007276 | 2026-08-31 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007277 | 2026-08-31 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007278 | 2026-08-31 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 87.5 | 1837.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007279 | 2026-08-31 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007280 | 2026-08-31 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007281 | 2026-08-31 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007282 | 2026-08-31 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 90 | 315 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007283 | 2026-08-31 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007284 | 2026-08-31 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007285 | 2026-08-31 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 60 | 1200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007286 | 2026-08-31 | E050 | Mathis Girard | Consulting | P005 | Cloud Landing Zone | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 60 | 450 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007287 | 2026-08-31 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP03 | Build, configuration and implementation | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007288 | 2026-08-31 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007289 | 2026-09-07 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007290 | 2026-09-07 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007291 | 2026-09-07 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007292 | 2026-09-07 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007293 | 2026-09-07 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007294 | 2026-09-07 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007295 | 2026-09-07 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007296 | 2026-09-07 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007297 | 2026-09-07 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007298 | 2026-09-07 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007299 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007300 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007301 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007302 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007303 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007304 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007305 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007306 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007307 | 2026-09-07 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007308 | 2026-09-07 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 80 | 2560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007309 | 2026-09-07 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007310 | 2026-09-07 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007311 | 2026-09-07 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007312 | 2026-09-07 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007313 | 2026-09-07 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007314 | 2026-09-07 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007315 | 2026-09-07 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007316 | 2026-09-07 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007317 | 2026-09-07 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007318 | 2026-09-07 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 62.5 | 1875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007319 | 2026-09-07 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007320 | 2026-09-07 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007321 | 2026-09-07 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007322 | 2026-09-07 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007323 | 2026-09-07 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007324 | 2026-09-07 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007325 | 2026-09-07 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007326 | 2026-09-07 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007327 | 2026-09-07 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007328 | 2026-09-07 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007329 | 2026-09-07 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007330 | 2026-09-07 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007331 | 2026-09-07 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007332 | 2026-09-07 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007333 | 2026-09-07 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007334 | 2026-09-07 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007335 | 2026-09-07 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007336 | 2026-09-07 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007337 | 2026-09-07 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007338 | 2026-09-07 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007339 | 2026-09-07 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007340 | 2026-09-07 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007341 | 2026-09-07 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007342 | 2026-09-07 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007343 | 2026-09-07 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007344 | 2026-09-07 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 31.5 | 157.5 | 4961.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007345 | 2026-09-07 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007346 | 2026-09-07 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007347 | 2026-09-07 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007348 | 2026-09-07 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007349 | 2026-09-07 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007350 | 2026-09-07 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007351 | 2026-09-07 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007352 | 2026-09-07 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007353 | 2026-09-07 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007354 | 2026-09-07 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007355 | 2026-09-07 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007356 | 2026-09-07 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007357 | 2026-09-07 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007358 | 2026-09-07 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007359 | 2026-09-07 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007360 | 2026-09-07 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007361 | 2026-09-07 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007362 | 2026-09-07 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007363 | 2026-09-07 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007364 | 2026-09-07 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007365 | 2026-09-07 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 105 | 2310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007366 | 2026-09-07 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007367 | 2026-09-07 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007368 | 2026-09-07 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007369 | 2026-09-07 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 14 | 82.5 | 1155 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007370 | 2026-09-07 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 10 | 82.5 | 825 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007371 | 2026-09-07 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007372 | 2026-09-07 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21 | 67.5 | 1417.5 | Rejected | Sara Khan | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007373 | 2026-09-07 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 13 | 67.5 | 877.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007374 | 2026-09-07 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007375 | 2026-09-07 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007376 | 2026-09-07 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007377 | 2026-09-07 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007378 | 2026-09-07 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007379 | 2026-09-07 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007380 | 2026-09-07 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007381 | 2026-09-07 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007382 | 2026-09-07 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007383 | 2026-09-07 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007384 | 2026-09-07 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1.5 | 55 | 82.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007385 | 2026-09-07 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007386 | 2026-09-07 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4.5 | 55 | 247.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007387 | 2026-09-07 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007388 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007389 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007390 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007391 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007392 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007393 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007394 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007395 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007396 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007397 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 65 | 910 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007398 | 2026-09-07 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007399 | 2026-09-07 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 23 | 120 | 2760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007400 | 2026-09-07 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 120 | 1560 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007401 | 2026-09-07 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007402 | 2026-09-07 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007403 | 2026-09-07 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007404 | 2026-09-07 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007405 | 2026-09-07 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 100 | 3150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007406 | 2026-09-07 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007407 | 2026-09-07 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 75 | 2100 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007408 | 2026-09-07 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 75 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007409 | 2026-09-07 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 67.5 | 1755 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007410 | 2026-09-07 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 6 | 67.5 | 405 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007411 | 2026-09-07 | E021 | Lea Nguyen | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007412 | 2026-09-07 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007413 | 2026-09-07 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007414 | 2026-09-07 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 102.5 | 820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007415 | 2026-09-07 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 102.5 | 3280 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007416 | 2026-09-07 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 77.5 | 348.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007417 | 2026-09-07 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19.5 | 77.5 | 1511.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007418 | 2026-09-07 | E024 | Louis Fontaine | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007419 | 2026-09-07 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 65 | 845 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007420 | 2026-09-07 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27 | 65 | 1755 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007421 | 2026-09-07 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 117.5 | 1057.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007422 | 2026-09-07 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 10.5 | 117.5 | 1233.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007423 | 2026-09-07 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 117.5 | 587.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007424 | 2026-09-07 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007425 | 2026-09-07 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 82.5 | 536.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007426 | 2026-09-07 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 82.5 | 288.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007427 | 2026-09-07 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 82.5 | 495 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007428 | 2026-09-07 | E027 | Emma Lopez | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007429 | 2026-09-07 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 95 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007430 | 2026-09-07 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 95 | 665 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007431 | 2026-09-07 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 95 | 427.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007432 | 2026-09-07 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007433 | 2026-09-07 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007434 | 2026-09-07 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007435 | 2026-09-07 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 90 | 1035 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007436 | 2026-09-07 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007437 | 2026-09-07 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007438 | 2026-09-07 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007439 | 2026-09-07 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007440 | 2026-09-07 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007441 | 2026-09-07 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 62.5 | 781.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007442 | 2026-09-07 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007443 | 2026-09-07 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 62.5 | 968.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007444 | 2026-09-07 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007445 | 2026-09-07 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007446 | 2026-09-07 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007447 | 2026-09-07 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007448 | 2026-09-07 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007449 | 2026-09-07 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 72.5 | 181.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007450 | 2026-09-07 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 72.5 | 181.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007451 | 2026-09-07 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 19 | 72.5 | 1377.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007452 | 2026-09-07 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007453 | 2026-09-07 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007454 | 2026-09-07 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007455 | 2026-09-07 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 67.5 | 1080 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007456 | 2026-09-07 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007457 | 2026-09-07 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 120 | 2880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007458 | 2026-09-07 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 120 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007459 | 2026-09-07 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007460 | 2026-09-07 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007461 | 2026-09-07 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 100 | 2600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007462 | 2026-09-07 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 100 | 1250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007463 | 2026-09-07 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007464 | 2026-09-07 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 90 | 1890 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007465 | 2026-09-07 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007466 | 2026-09-07 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007467 | 2026-09-07 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007468 | 2026-09-07 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007469 | 2026-09-07 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007470 | 2026-09-07 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007471 | 2026-09-07 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007472 | 2026-09-07 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007473 | 2026-09-07 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007474 | 2026-09-07 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 75 | 712.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007475 | 2026-09-07 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 75 | 262.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007476 | 2026-09-07 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 3.5 | 75 | 262.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007477 | 2026-09-07 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007478 | 2026-09-07 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 97.5 | 1852.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007479 | 2026-09-07 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007480 | 2026-09-07 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 97.5 | 1218.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007481 | 2026-09-07 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007482 | 2026-09-07 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007483 | 2026-09-07 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 67.5 | 1383.75 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007484 | 2026-09-07 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007485 | 2026-09-07 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 115 | 1265 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007486 | 2026-09-07 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 115 | 747.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007487 | 2026-09-07 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 115 | 517.5 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007488 | 2026-09-07 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007489 | 2026-09-07 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007490 | 2026-09-07 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007491 | 2026-09-07 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007492 | 2026-09-07 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 87.5 | 656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007493 | 2026-09-07 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007494 | 2026-09-07 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007495 | 2026-09-07 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007496 | 2026-09-07 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007497 | 2026-09-07 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 60 | 690 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007498 | 2026-09-07 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 60 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007499 | 2026-09-07 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 60 | 330 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007500 | 2026-09-07 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007501 | 2026-09-14 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007502 | 2026-09-14 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007503 | 2026-09-14 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007504 | 2026-09-14 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007505 | 2026-09-14 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007506 | 2026-09-14 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007507 | 2026-09-14 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007508 | 2026-09-14 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007509 | 2026-09-14 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007510 | 2026-09-14 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007511 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007512 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007513 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007514 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007515 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007516 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007517 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007518 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007519 | 2026-09-14 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007520 | 2026-09-14 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 80 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007521 | 2026-09-14 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007522 | 2026-09-14 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007523 | 2026-09-14 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007524 | 2026-09-14 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007525 | 2026-09-14 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007526 | 2026-09-14 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007527 | 2026-09-14 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007528 | 2026-09-14 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007529 | 2026-09-14 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007530 | 2026-09-14 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29.5 | 62.5 | 1843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007531 | 2026-09-14 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007532 | 2026-09-14 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007533 | 2026-09-14 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007534 | 2026-09-14 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007535 | 2026-09-14 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007536 | 2026-09-14 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007537 | 2026-09-14 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007538 | 2026-09-14 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007539 | 2026-09-14 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007540 | 2026-09-14 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007541 | 2026-09-14 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 55 | 1705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007542 | 2026-09-14 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007543 | 2026-09-14 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007544 | 2026-09-14 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007545 | 2026-09-14 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007546 | 2026-09-14 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007547 | 2026-09-14 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007548 | 2026-09-14 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007549 | 2026-09-14 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007550 | 2026-09-14 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007551 | 2026-09-14 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007552 | 2026-09-14 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007553 | 2026-09-14 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007554 | 2026-09-14 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007555 | 2026-09-14 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007556 | 2026-09-14 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 157.5 | 5118.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007557 | 2026-09-14 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007558 | 2026-09-14 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007559 | 2026-09-14 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007560 | 2026-09-14 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007561 | 2026-09-14 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007562 | 2026-09-14 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007563 | 2026-09-14 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007564 | 2026-09-14 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007565 | 2026-09-14 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007566 | 2026-09-14 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007567 | 2026-09-14 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007568 | 2026-09-14 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007569 | 2026-09-14 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007570 | 2026-09-14 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007571 | 2026-09-14 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007572 | 2026-09-14 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007573 | 2026-09-14 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007574 | 2026-09-14 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007575 | 2026-09-14 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007576 | 2026-09-14 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007577 | 2026-09-14 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 105 | 2310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007578 | 2026-09-14 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007579 | 2026-09-14 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 12.5 | 85 | 1062.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007580 | 2026-09-14 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 4.5 | 85 | 382.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007581 | 2026-09-14 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007582 | 2026-09-14 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007583 | 2026-09-14 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007584 | 2026-09-14 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007585 | 2026-09-14 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19.5 | 67.5 | 1316.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007586 | 2026-09-14 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007587 | 2026-09-14 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007588 | 2026-09-14 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007589 | 2026-09-14 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007590 | 2026-09-14 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007591 | 2026-09-14 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007592 | 2026-09-14 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007593 | 2026-09-14 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007594 | 2026-09-14 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007595 | 2026-09-14 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007596 | 2026-09-14 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007597 | 2026-09-14 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007598 | 2026-09-14 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 10.5 | 55 | 577.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007599 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007600 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007601 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007602 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007603 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007604 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007605 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007606 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007607 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007608 | 2026-09-14 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 65 | 1430 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007609 | 2026-09-14 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 120 | 2940 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007610 | 2026-09-14 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007611 | 2026-09-14 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007612 | 2026-09-14 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 100 | 2550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007613 | 2026-09-14 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007614 | 2026-09-14 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 100 | 700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007615 | 2026-09-14 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 33 | 100 | 3300 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007616 | 2026-09-14 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 7 | 100 | 700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007617 | 2026-09-14 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007618 | 2026-09-14 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007619 | 2026-09-14 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 75 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007620 | 2026-09-14 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 67.5 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007621 | 2026-09-14 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007622 | 2026-09-14 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 27 | 67.5 | 1822.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007623 | 2026-09-14 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007624 | 2026-09-14 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007625 | 2026-09-14 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 102.5 | 820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007626 | 2026-09-14 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 102.5 | 3280 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007627 | 2026-09-14 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 77.5 | 581.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007628 | 2026-09-14 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 77.5 | 2518.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007629 | 2026-09-14 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 65 | 812.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007630 | 2026-09-14 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27.5 | 65 | 1787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007631 | 2026-09-14 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007632 | 2026-09-14 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007633 | 2026-09-14 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007634 | 2026-09-14 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 82.5 | 1361.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007635 | 2026-09-14 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 82.5 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007636 | 2026-09-14 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15.5 | 82.5 | 1278.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007637 | 2026-09-14 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007638 | 2026-09-14 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 95 | 427.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007639 | 2026-09-14 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 95 | 332.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007640 | 2026-09-14 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007641 | 2026-09-14 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 22.5 | 60 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007642 | 2026-09-14 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 60 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007643 | 2026-09-14 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 60 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007644 | 2026-09-14 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007645 | 2026-09-14 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 90 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007646 | 2026-09-14 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007647 | 2026-09-14 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007648 | 2026-09-14 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 62.5 | 1312.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007649 | 2026-09-14 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007650 | 2026-09-14 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 62.5 | 437.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007651 | 2026-09-14 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 62.5 | 1062.5 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007652 | 2026-09-14 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 62.5 | 718.75 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007653 | 2026-09-14 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 11.5 | 62.5 | 718.75 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007654 | 2026-09-14 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007655 | 2026-09-14 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007656 | 2026-09-14 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007657 | 2026-09-14 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007658 | 2026-09-14 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007659 | 2026-09-14 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007660 | 2026-09-14 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007661 | 2026-09-14 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007662 | 2026-09-14 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007663 | 2026-09-14 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007664 | 2026-09-14 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 120 | 2880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007665 | 2026-09-14 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007666 | 2026-09-14 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007667 | 2026-09-14 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 100 | 2550 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007668 | 2026-09-14 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007669 | 2026-09-14 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007670 | 2026-09-14 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 90 | 1935 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007671 | 2026-09-14 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007672 | 2026-09-14 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 67.5 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007673 | 2026-09-14 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007674 | 2026-09-14 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007675 | 2026-09-14 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 75 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007676 | 2026-09-14 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP03 | Build, configuration and implementation | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007677 | 2026-09-14 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007678 | 2026-09-14 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 75 | 1912.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007679 | 2026-09-14 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007680 | 2026-09-14 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP04 | Data integration, migration and validation | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007681 | 2026-09-14 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 97.5 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007682 | 2026-09-14 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 97.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007683 | 2026-09-14 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 97.5 | 1267.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007684 | 2026-09-14 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007685 | 2026-09-14 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007686 | 2026-09-14 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007687 | 2026-09-14 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007688 | 2026-09-14 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 67.5 | 506.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007689 | 2026-09-14 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 115 | 2070 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007690 | 2026-09-14 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007691 | 2026-09-14 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 115 | 805 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007692 | 2026-09-14 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 115 | 402.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007693 | 2026-09-14 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007694 | 2026-09-14 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007695 | 2026-09-14 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 87.5 | 437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007696 | 2026-09-14 | E048 | Raphaël Meyer | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007697 | 2026-09-14 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007698 | 2026-09-14 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007699 | 2026-09-14 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 90 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007700 | 2026-09-14 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 60 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007701 | 2026-09-14 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 60 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007702 | 2026-09-14 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 60 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007703 | 2026-09-21 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007704 | 2026-09-21 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007705 | 2026-09-21 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007706 | 2026-09-21 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007707 | 2026-09-21 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007708 | 2026-09-21 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007709 | 2026-09-21 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007710 | 2026-09-21 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007711 | 2026-09-21 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007712 | 2026-09-21 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007713 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007714 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007715 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007716 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007717 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007718 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007719 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007720 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007721 | 2026-09-21 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007722 | 2026-09-21 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 80 | 2480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007723 | 2026-09-21 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007724 | 2026-09-21 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007725 | 2026-09-21 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007726 | 2026-09-21 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007727 | 2026-09-21 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007728 | 2026-09-21 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007729 | 2026-09-21 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007730 | 2026-09-21 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007731 | 2026-09-21 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007732 | 2026-09-21 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 62.5 | 1875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007733 | 2026-09-21 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007734 | 2026-09-21 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007735 | 2026-09-21 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007736 | 2026-09-21 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007737 | 2026-09-21 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007738 | 2026-09-21 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007739 | 2026-09-21 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007740 | 2026-09-21 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007741 | 2026-09-21 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007742 | 2026-09-21 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007743 | 2026-09-21 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007744 | 2026-09-21 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007745 | 2026-09-21 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007746 | 2026-09-21 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007747 | 2026-09-21 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007748 | 2026-09-21 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007749 | 2026-09-21 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007750 | 2026-09-21 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007751 | 2026-09-21 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007752 | 2026-09-21 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007753 | 2026-09-21 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007754 | 2026-09-21 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007755 | 2026-09-21 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007756 | 2026-09-21 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007757 | 2026-09-21 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007758 | 2026-09-21 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007759 | 2026-09-21 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007760 | 2026-09-21 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007761 | 2026-09-21 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007762 | 2026-09-21 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007763 | 2026-09-21 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007764 | 2026-09-21 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007765 | 2026-09-21 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007766 | 2026-09-21 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007767 | 2026-09-21 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007768 | 2026-09-21 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007769 | 2026-09-21 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 2 | 150 | 300 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007770 | 2026-09-21 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 150 | 5025 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007771 | 2026-09-21 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007772 | 2026-09-21 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007773 | 2026-09-21 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007774 | 2026-09-21 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007775 | 2026-09-21 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007776 | 2026-09-21 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007777 | 2026-09-21 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007778 | 2026-09-21 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007779 | 2026-09-21 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007780 | 2026-09-21 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 105 | 2310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007781 | 2026-09-21 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007782 | 2026-09-21 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007783 | 2026-09-21 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007784 | 2026-09-21 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007785 | 2026-09-21 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007786 | 2026-09-21 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007787 | 2026-09-21 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007788 | 2026-09-21 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19.5 | 67.5 | 1316.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007789 | 2026-09-21 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007790 | 2026-09-21 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 7 | 67.5 | 472.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007791 | 2026-09-21 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 4.5 | 67.5 | 303.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007792 | 2026-09-21 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007793 | 2026-09-21 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007794 | 2026-09-21 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007795 | 2026-09-21 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007796 | 2026-09-21 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007797 | 2026-09-21 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007798 | 2026-09-21 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007799 | 2026-09-21 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007800 | 2026-09-21 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007801 | 2026-09-21 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007802 | 2026-09-21 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 11.5 | 55 | 632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007803 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007804 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007805 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007806 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007807 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007808 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007809 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007810 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007811 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007812 | 2026-09-21 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 65 | 1430 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007813 | 2026-09-21 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007814 | 2026-09-21 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007815 | 2026-09-21 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 120 | 540 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007816 | 2026-09-21 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 100 | 2800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007817 | 2026-09-21 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007818 | 2026-09-21 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 100 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007819 | 2026-09-21 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 100 | 3200 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007820 | 2026-09-21 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007821 | 2026-09-21 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 75 | 862.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007822 | 2026-09-21 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 75 | 337.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007823 | 2026-09-21 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007824 | 2026-09-21 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007825 | 2026-09-21 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 67.5 | 607.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007826 | 2026-09-21 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007827 | 2026-09-21 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 67.5 | 1721.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007828 | 2026-09-21 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007829 | 2026-09-21 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 67.5 | 236.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007830 | 2026-09-21 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 102.5 | 871.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007831 | 2026-09-21 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 102.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007832 | 2026-09-21 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 77.5 | 620 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007833 | 2026-09-21 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 77.5 | 2480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007834 | 2026-09-21 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 65 | 715 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007835 | 2026-09-21 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 29 | 65 | 1885 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007836 | 2026-09-21 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007837 | 2026-09-21 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007838 | 2026-09-21 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 117.5 | 1057.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007839 | 2026-09-21 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 82.5 | 1237.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007840 | 2026-09-21 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 82.5 | 577.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007841 | 2026-09-21 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 82.5 | 1485 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007842 | 2026-09-21 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007843 | 2026-09-21 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 95 | 1092.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007844 | 2026-09-21 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007845 | 2026-09-21 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007846 | 2026-09-21 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 60 | 870 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007847 | 2026-09-21 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 60 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007848 | 2026-09-21 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007849 | 2026-09-21 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007850 | 2026-09-21 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 90 | 405 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007851 | 2026-09-21 | E030 | Rayan Fischer | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007852 | 2026-09-21 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007853 | 2026-09-21 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 62.5 | 687.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007854 | 2026-09-21 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007855 | 2026-09-21 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 62.5 | 125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007856 | 2026-09-21 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 62.5 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007857 | 2026-09-21 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007858 | 2026-09-21 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007859 | 2026-09-21 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 62.5 | 93.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007860 | 2026-09-21 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007861 | 2026-09-21 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007862 | 2026-09-21 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007863 | 2026-09-21 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007864 | 2026-09-21 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007865 | 2026-09-21 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007866 | 2026-09-21 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007867 | 2026-09-21 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007868 | 2026-09-21 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007869 | 2026-09-21 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007870 | 2026-09-21 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 120 | 2880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007871 | 2026-09-21 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 120 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007872 | 2026-09-21 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007873 | 2026-09-21 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007874 | 2026-09-21 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007875 | 2026-09-21 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007876 | 2026-09-21 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007877 | 2026-09-21 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 90 | 1620 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007878 | 2026-09-21 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007879 | 2026-09-21 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007880 | 2026-09-21 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007881 | 2026-09-21 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007882 | 2026-09-21 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007883 | 2026-09-21 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 75 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007884 | 2026-09-21 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 75 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007885 | 2026-09-21 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007886 | 2026-09-21 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 75 | 1087.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007887 | 2026-09-21 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 75 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007888 | 2026-09-21 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 75 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007889 | 2026-09-21 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007890 | 2026-09-21 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007891 | 2026-09-21 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007892 | 2026-09-21 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007893 | 2026-09-21 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 97.5 | 1121.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007894 | 2026-09-21 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 75 | 2250 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007895 | 2026-09-21 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007896 | 2026-09-21 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007897 | 2026-09-21 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007898 | 2026-09-21 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007899 | 2026-09-21 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 67.5 | 506.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007900 | 2026-09-21 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 115 | 2127.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007901 | 2026-09-21 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 115 | 1495 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007902 | 2026-09-21 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007903 | 2026-09-21 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007904 | 2026-09-21 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 87.5 | 1793.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007905 | 2026-09-21 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 87.5 | 962.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007906 | 2026-09-21 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007907 | 2026-09-21 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 90 | 1935 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007908 | 2026-09-21 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007909 | 2026-09-21 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 10.5 | 90 | 945 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007910 | 2026-09-21 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 21.5 | 60 | 1290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007911 | 2026-09-21 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 60 | 690 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007912 | 2026-09-21 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7 | 60 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007913 | 2026-09-28 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007914 | 2026-09-28 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007915 | 2026-09-28 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007916 | 2026-09-28 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007917 | 2026-09-28 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007918 | 2026-09-28 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007919 | 2026-09-28 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007920 | 2026-09-28 | E001 | Sophie Lambert | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007921 | 2026-09-28 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007922 | 2026-09-28 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 97.5 | 3461.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007923 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007924 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007925 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007926 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007927 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007928 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007929 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007930 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007931 | 2026-09-28 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007932 | 2026-09-28 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 11.5 | 80 | 920 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007933 | 2026-09-28 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007934 | 2026-09-28 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007935 | 2026-09-28 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007936 | 2026-09-28 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007937 | 2026-09-28 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007938 | 2026-09-28 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007939 | 2026-09-28 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007940 | 2026-09-28 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007941 | 2026-09-28 | E003 | Elena Rossi | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007942 | 2026-09-28 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007943 | 2026-09-28 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30 | 62.5 | 1875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007944 | 2026-09-28 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007945 | 2026-09-28 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007946 | 2026-09-28 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007947 | 2026-09-28 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007948 | 2026-09-28 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007949 | 2026-09-28 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007950 | 2026-09-28 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007951 | 2026-09-28 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007952 | 2026-09-28 | E005 | Nadia Benali | Finance | P009 | ERP Integration | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007953 | 2026-09-28 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007954 | 2026-09-28 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 26.5 | 55 | 1457.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007955 | 2026-09-28 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007956 | 2026-09-28 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007957 | 2026-09-28 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007958 | 2026-09-28 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007959 | 2026-09-28 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007960 | 2026-09-28 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007961 | 2026-09-28 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007962 | 2026-09-28 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007963 | 2026-09-28 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007964 | 2026-09-28 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007965 | 2026-09-28 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007966 | 2026-09-28 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007967 | 2026-09-28 | E007 | Claire Muller | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007968 | 2026-09-28 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007969 | 2026-09-28 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 32.5 | 157.5 | 5118.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007970 | 2026-09-28 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007971 | 2026-09-28 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007972 | 2026-09-28 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007973 | 2026-09-28 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007974 | 2026-09-28 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007975 | 2026-09-28 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007976 | 2026-09-28 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007977 | 2026-09-28 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007978 | 2026-09-28 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007979 | 2026-09-28 | E009 | Amélie Dubois | Executive | P009 | ERP Integration | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007980 | 2026-09-28 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 150 | 5100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007981 | 2026-09-28 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007982 | 2026-09-28 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007983 | 2026-09-28 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007984 | 2026-09-28 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007985 | 2026-09-28 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007986 | 2026-09-28 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007987 | 2026-09-28 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007988 | 2026-09-28 | E010 | David Martin | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007989 | 2026-09-28 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007990 | 2026-09-28 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 105 | 2310 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007991 | 2026-09-28 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007992 | 2026-09-28 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007993 | 2026-09-28 | E011 | Maya Fernandes | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | Yes | 6 | 85 | 510 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007994 | 2026-09-28 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 85 | 127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007995 | 2026-09-28 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20 | 82.5 | 1650 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007996 | 2026-09-28 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 19 | 82.5 | 1567.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007997 | 2026-09-28 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007998 | 2026-09-28 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-007999 | 2026-09-28 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008000 | 2026-09-28 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008001 | 2026-09-28 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11 | 67.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008002 | 2026-09-28 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008003 | 2026-09-28 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008004 | 2026-09-28 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008005 | 2026-09-28 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008006 | 2026-09-28 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008007 | 2026-09-28 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008008 | 2026-09-28 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008009 | 2026-09-28 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008010 | 2026-09-28 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008011 | 2026-09-28 | E015 | Inès Petit | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008012 | 2026-09-28 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008013 | 2026-09-28 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 11.5 | 55 | 632.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008014 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008015 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008016 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008017 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008018 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008019 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008020 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008021 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P009 | ERP Integration | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008022 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008023 | 2026-09-28 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 22 | 65 | 1430 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008024 | 2026-09-28 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 120 | 2940 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008025 | 2026-09-28 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008026 | 2026-09-28 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008027 | 2026-09-28 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008028 | 2026-09-28 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008029 | 2026-09-28 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 100 | 400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008030 | 2026-09-28 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008031 | 2026-09-28 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008032 | 2026-09-28 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008033 | 2026-09-28 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 75 | 975 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008034 | 2026-09-28 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008035 | 2026-09-28 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008036 | 2026-09-28 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008037 | 2026-09-28 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 67.5 | 1113.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008038 | 2026-09-28 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008039 | 2026-09-28 | E022 | Hugo Laurent | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008040 | 2026-09-28 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 102.5 | 871.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008041 | 2026-09-28 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 102.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008042 | 2026-09-28 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 77.5 | 658.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008043 | 2026-09-28 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 77.5 | 2441.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008044 | 2026-09-28 | E025 | Camille Garcia | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 65 | 845 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008045 | 2026-09-28 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27 | 65 | 1755 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008046 | 2026-09-28 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008047 | 2026-09-28 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008048 | 2026-09-28 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008049 | 2026-09-28 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 117.5 | 176.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008050 | 2026-09-28 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 82.5 | 1361.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008051 | 2026-09-28 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 82.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008052 | 2026-09-28 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 82.5 | 1196.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008053 | 2026-09-28 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008054 | 2026-09-28 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 95 | 1235 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008055 | 2026-09-28 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008056 | 2026-09-28 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 14 | 60 | 840 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008057 | 2026-09-28 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 10 | 60 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008058 | 2026-09-28 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008059 | 2026-09-28 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008060 | 2026-09-28 | E030 | Rayan Fischer | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008061 | 2026-09-28 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008062 | 2026-09-28 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 90 | 45 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008063 | 2026-09-28 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008064 | 2026-09-28 | E031 | Lucie Pereira | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 62.5 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008065 | 2026-09-28 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008066 | 2026-09-28 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 62.5 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008067 | 2026-09-28 | E032 | Maxime Richard | Applications | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 62.5 | 781.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008068 | 2026-09-28 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008069 | 2026-09-28 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 62.5 | 31.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008070 | 2026-09-28 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008071 | 2026-09-28 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008072 | 2026-09-28 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008073 | 2026-09-28 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008074 | 2026-09-28 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008075 | 2026-09-28 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008076 | 2026-09-28 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008077 | 2026-09-28 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008078 | 2026-09-28 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008079 | 2026-09-28 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 120 | 2880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008080 | 2026-09-28 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008081 | 2026-09-28 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008082 | 2026-09-28 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008083 | 2026-09-28 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008084 | 2026-09-28 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008085 | 2026-09-28 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 90 | 1620 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008086 | 2026-09-28 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 90 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008087 | 2026-09-28 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 67.5 | 1282.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008088 | 2026-09-28 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008089 | 2026-09-28 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008090 | 2026-09-28 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008091 | 2026-09-28 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008092 | 2026-09-28 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 75 | 1575 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008093 | 2026-09-28 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008094 | 2026-09-28 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 75 | 525 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008095 | 2026-09-28 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008096 | 2026-09-28 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 97.5 | 2096.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008097 | 2026-09-28 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 97.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008098 | 2026-09-28 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 97.5 | 926.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008099 | 2026-09-28 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 75 | 2175 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008100 | 2026-09-28 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 75 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008101 | 2026-09-28 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008102 | 2026-09-28 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008103 | 2026-09-28 | E046 | Alexandre Blanc | Cloud & Platform | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008104 | 2026-09-28 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 67.5 | 573.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008105 | 2026-09-28 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 115 | 2415 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008106 | 2026-09-28 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 115 | 1322.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008107 | 2026-09-28 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008108 | 2026-09-28 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008109 | 2026-09-28 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008110 | 2026-09-28 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008111 | 2026-09-28 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008112 | 2026-09-28 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008113 | 2026-09-28 | E049 | Nora Aydin | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 90 | 990 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008114 | 2026-09-28 | E050 | Mathis Girard | Consulting | P009 | ERP Integration | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 60 | 1230 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008115 | 2026-09-28 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 60 | 780 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008116 | 2026-09-28 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 60 | 390 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008117 | 2026-10-05 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008118 | 2026-10-05 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008119 | 2026-10-05 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008120 | 2026-10-05 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008121 | 2026-10-05 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008122 | 2026-10-05 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008123 | 2026-10-05 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008124 | 2026-10-05 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008125 | 2026-10-05 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008126 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008127 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008128 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008129 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008130 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008131 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008132 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008133 | 2026-10-05 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008134 | 2026-10-05 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 80 | 2720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008135 | 2026-10-05 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008136 | 2026-10-05 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008137 | 2026-10-05 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008138 | 2026-10-05 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008139 | 2026-10-05 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008140 | 2026-10-05 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008141 | 2026-10-05 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008142 | 2026-10-05 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008143 | 2026-10-05 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 62.5 | 2000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008144 | 2026-10-05 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008145 | 2026-10-05 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008146 | 2026-10-05 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008147 | 2026-10-05 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008148 | 2026-10-05 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008149 | 2026-10-05 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008150 | 2026-10-05 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008151 | 2026-10-05 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008152 | 2026-10-05 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008153 | 2026-10-05 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 55 | 1787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008154 | 2026-10-05 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008155 | 2026-10-05 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008156 | 2026-10-05 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008157 | 2026-10-05 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008158 | 2026-10-05 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 14 | 187.5 | 2625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008159 | 2026-10-05 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008160 | 2026-10-05 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008161 | 2026-10-05 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008162 | 2026-10-05 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008163 | 2026-10-05 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008164 | 2026-10-05 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008165 | 2026-10-05 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008166 | 2026-10-05 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008167 | 2026-10-05 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008168 | 2026-10-05 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 157.5 | 5355 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008169 | 2026-10-05 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008170 | 2026-10-05 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008171 | 2026-10-05 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008172 | 2026-10-05 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008173 | 2026-10-05 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008174 | 2026-10-05 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008175 | 2026-10-05 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008176 | 2026-10-05 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008177 | 2026-10-05 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008178 | 2026-10-05 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 150 | 5325 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008179 | 2026-10-05 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008180 | 2026-10-05 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008181 | 2026-10-05 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008182 | 2026-10-05 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008183 | 2026-10-05 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008184 | 2026-10-05 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008185 | 2026-10-05 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 105 | 105 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008186 | 2026-10-05 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008187 | 2026-10-05 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 105 | 1470 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008188 | 2026-10-05 | E010 | David Martin | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008189 | 2026-10-05 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19.5 | 85 | 1657.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008190 | 2026-10-05 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15.5 | 85 | 1317.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008191 | 2026-10-05 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 5 | 85 | 425 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008192 | 2026-10-05 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008193 | 2026-10-05 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 19 | 82.5 | 1567.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008194 | 2026-10-05 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 21.5 | 67.5 | 1451.25 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008195 | 2026-10-05 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18.5 | 67.5 | 1248.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008196 | 2026-10-05 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 16 | 67.5 | 1080 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008197 | 2026-10-05 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 10 | 67.5 | 675 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008198 | 2026-10-05 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 6.5 | 67.5 | 438.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008199 | 2026-10-05 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008200 | 2026-10-05 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008201 | 2026-10-05 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008202 | 2026-10-05 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008203 | 2026-10-05 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008204 | 2026-10-05 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008205 | 2026-10-05 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008206 | 2026-10-05 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008207 | 2026-10-05 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008208 | 2026-10-05 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 55 | 770 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008209 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008210 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008211 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008212 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008213 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008214 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008215 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008216 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008217 | 2026-10-05 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008218 | 2026-10-05 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 13.5 | 120 | 1620 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008219 | 2026-10-05 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 120 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008220 | 2026-10-05 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 120 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008221 | 2026-10-05 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008222 | 2026-10-05 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 100 | 1850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008223 | 2026-10-05 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008224 | 2026-10-05 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 100 | 50 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008225 | 2026-10-05 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008226 | 2026-10-05 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008227 | 2026-10-05 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008228 | 2026-10-05 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008229 | 2026-10-05 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 75 | 937.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008230 | 2026-10-05 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008231 | 2026-10-05 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 30.5 | 67.5 | 2058.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008232 | 2026-10-05 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008233 | 2026-10-05 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008234 | 2026-10-05 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 67.5 | 1957.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008235 | 2026-10-05 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008236 | 2026-10-05 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 102.5 | 512.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008237 | 2026-10-05 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 102.5 | 1947.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008238 | 2026-10-05 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008239 | 2026-10-05 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 77.5 | 581.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008240 | 2026-10-05 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 77.5 | 2518.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008241 | 2026-10-05 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008242 | 2026-10-05 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008243 | 2026-10-05 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008244 | 2026-10-05 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008245 | 2026-10-05 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008246 | 2026-10-05 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 82.5 | 1320 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008247 | 2026-10-05 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 82.5 | 618.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008248 | 2026-10-05 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 82.5 | 1361.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008249 | 2026-10-05 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 95 | 1900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008250 | 2026-10-05 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008251 | 2026-10-05 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008252 | 2026-10-05 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24 | 60 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008253 | 2026-10-05 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 60 | 960 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008254 | 2026-10-05 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 22 | 90 | 1980 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008255 | 2026-10-05 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008256 | 2026-10-05 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 90 | 900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008257 | 2026-10-05 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008258 | 2026-10-05 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008259 | 2026-10-05 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 62.5 | 812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008260 | 2026-10-05 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 17.5 | 62.5 | 1093.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008261 | 2026-10-05 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 62.5 | 812.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008262 | 2026-10-05 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 62.5 | 593.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008263 | 2026-10-05 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008264 | 2026-10-05 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008265 | 2026-10-05 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008266 | 2026-10-05 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008267 | 2026-10-05 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008268 | 2026-10-05 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008269 | 2026-10-05 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008270 | 2026-10-05 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008271 | 2026-10-05 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008272 | 2026-10-05 | E036 | Nathan Cohen | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008273 | 2026-10-05 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008274 | 2026-10-05 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 25 | 120 | 3000 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008275 | 2026-10-05 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 120 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008276 | 2026-10-05 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008277 | 2026-10-05 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 26 | 100 | 2600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008278 | 2026-10-05 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008279 | 2026-10-05 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 100 | 200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008280 | 2026-10-05 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 90 | 1080 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008281 | 2026-10-05 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 90 | 990 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008282 | 2026-10-05 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 90 | 270 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008283 | 2026-10-05 | E040 | Adam Klein | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008284 | 2026-10-05 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 67.5 | 1417.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008285 | 2026-10-05 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008286 | 2026-10-05 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 67.5 | 472.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008287 | 2026-10-05 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008288 | 2026-10-05 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008289 | 2026-10-05 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008290 | 2026-10-05 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 75 | 1837.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008291 | 2026-10-05 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008292 | 2026-10-05 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008293 | 2026-10-05 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 97.5 | 1901.25 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008294 | 2026-10-05 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 97.5 | 828.75 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008295 | 2026-10-05 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 97.5 | 1170 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008296 | 2026-10-05 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008297 | 2026-10-05 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008298 | 2026-10-05 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008299 | 2026-10-05 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 23.5 | 67.5 | 1586.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008300 | 2026-10-05 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 115 | 1897.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008301 | 2026-10-05 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 115 | 1035 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008302 | 2026-10-05 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008303 | 2026-10-05 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008304 | 2026-10-05 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008305 | 2026-10-05 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 87.5 | 1137.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008306 | 2026-10-05 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008307 | 2026-10-05 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 90 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008308 | 2026-10-05 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008309 | 2026-10-05 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 90 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008310 | 2026-10-05 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 60 | 720 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008311 | 2026-10-05 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 28 | 60 | 1680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008312 | 2026-10-12 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008313 | 2026-10-12 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008314 | 2026-10-12 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008315 | 2026-10-12 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008316 | 2026-10-12 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008317 | 2026-10-12 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008318 | 2026-10-12 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008319 | 2026-10-12 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008320 | 2026-10-12 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008321 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008322 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008323 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008324 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008325 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008326 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008327 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008328 | 2026-10-12 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008329 | 2026-10-12 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 20 | 80 | 1600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008330 | 2026-10-12 | E002 | Marc Hoffmann | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008331 | 2026-10-12 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008332 | 2026-10-12 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008333 | 2026-10-12 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008334 | 2026-10-12 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008335 | 2026-10-12 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008336 | 2026-10-12 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008337 | 2026-10-12 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008338 | 2026-10-12 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008339 | 2026-10-12 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 29.5 | 62.5 | 1843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008340 | 2026-10-12 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008341 | 2026-10-12 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008342 | 2026-10-12 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008343 | 2026-10-12 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008344 | 2026-10-12 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008345 | 2026-10-12 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008346 | 2026-10-12 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008347 | 2026-10-12 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008348 | 2026-10-12 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008349 | 2026-10-12 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008350 | 2026-10-12 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008351 | 2026-10-12 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008352 | 2026-10-12 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008353 | 2026-10-12 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008354 | 2026-10-12 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008355 | 2026-10-12 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008356 | 2026-10-12 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008357 | 2026-10-12 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008358 | 2026-10-12 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008359 | 2026-10-12 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008360 | 2026-10-12 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008361 | 2026-10-12 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008362 | 2026-10-12 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008363 | 2026-10-12 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008364 | 2026-10-12 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008365 | 2026-10-12 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008366 | 2026-10-12 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008367 | 2026-10-12 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008368 | 2026-10-12 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008369 | 2026-10-12 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008370 | 2026-10-12 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008371 | 2026-10-12 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008372 | 2026-10-12 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008373 | 2026-10-12 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 21 | 150 | 3150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008374 | 2026-10-12 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008375 | 2026-10-12 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008376 | 2026-10-12 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008377 | 2026-10-12 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008378 | 2026-10-12 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008379 | 2026-10-12 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008380 | 2026-10-12 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008381 | 2026-10-12 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008382 | 2026-10-12 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008383 | 2026-10-12 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008384 | 2026-10-12 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008385 | 2026-10-12 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 17 | 85 | 1445 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008386 | 2026-10-12 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4 | 85 | 340 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008387 | 2026-10-12 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22 | 82.5 | 1815 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008388 | 2026-10-12 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18 | 82.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008389 | 2026-10-12 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008390 | 2026-10-12 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21 | 67.5 | 1417.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008391 | 2026-10-12 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008392 | 2026-10-12 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 13 | 67.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008393 | 2026-10-12 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008394 | 2026-10-12 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008395 | 2026-10-12 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008396 | 2026-10-12 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008397 | 2026-10-12 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008398 | 2026-10-12 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008399 | 2026-10-12 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008400 | 2026-10-12 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008401 | 2026-10-12 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008402 | 2026-10-12 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 13.5 | 55 | 742.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008403 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008404 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008405 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008406 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008407 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008408 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008409 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008410 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008411 | 2026-10-12 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008412 | 2026-10-12 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 14 | 120 | 1680 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008413 | 2026-10-12 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 120 | 900 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008414 | 2026-10-12 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 120 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008415 | 2026-10-12 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008416 | 2026-10-12 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 22 | 100 | 2200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008417 | 2026-10-12 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 100 | 700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008418 | 2026-10-12 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 100 | 300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008419 | 2026-10-12 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008420 | 2026-10-12 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 100 | 1800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008421 | 2026-10-12 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008422 | 2026-10-12 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008423 | 2026-10-12 | E019 | Eva Moreau | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008424 | 2026-10-12 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 75 | 1237.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008425 | 2026-10-12 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 75 | 487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008426 | 2026-10-12 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008427 | 2026-10-12 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008428 | 2026-10-12 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 67.5 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008429 | 2026-10-12 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008430 | 2026-10-12 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008431 | 2026-10-12 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 27.5 | 67.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008432 | 2026-10-12 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 67.5 | 843.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008433 | 2026-10-12 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 102.5 | 768.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008434 | 2026-10-12 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 102.5 | 3331.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008435 | 2026-10-12 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 77.5 | 658.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008436 | 2026-10-12 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 77.5 | 2441.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008437 | 2026-10-12 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008438 | 2026-10-12 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 117.5 | 1938.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008439 | 2026-10-12 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008440 | 2026-10-12 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 117.5 | 940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008441 | 2026-10-12 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 82.5 | 1237.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008442 | 2026-10-12 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 82.5 | 701.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008443 | 2026-10-12 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 82.5 | 1361.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008444 | 2026-10-12 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 95 | 1710 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008445 | 2026-10-12 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 95 | 1235 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008446 | 2026-10-12 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 95 | 760 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008447 | 2026-10-12 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 95 | 95 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008448 | 2026-10-12 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 14 | 60 | 840 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008449 | 2026-10-12 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 9.5 | 60 | 570 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008450 | 2026-10-12 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 60 | 30 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008451 | 2026-10-12 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008452 | 2026-10-12 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 90 | 1845 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008453 | 2026-10-12 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008454 | 2026-10-12 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 90 | 1035 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008455 | 2026-10-12 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 62.5 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008456 | 2026-10-12 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008457 | 2026-10-12 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 62.5 | 812.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008458 | 2026-10-12 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 62.5 | 1062.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008459 | 2026-10-12 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 62.5 | 781.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008460 | 2026-10-12 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 62.5 | 656.25 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008461 | 2026-10-12 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 105 | 262.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008462 | 2026-10-12 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 105 | 262.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008463 | 2026-10-12 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 19 | 105 | 1995 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008464 | 2026-10-12 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008465 | 2026-10-12 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008466 | 2026-10-12 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008467 | 2026-10-12 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008468 | 2026-10-12 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008469 | 2026-10-12 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008470 | 2026-10-12 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008471 | 2026-10-12 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 23 | 120 | 2760 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008472 | 2026-10-12 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008473 | 2026-10-12 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 120 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008474 | 2026-10-12 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 120 | 720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008475 | 2026-10-12 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008476 | 2026-10-12 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008477 | 2026-10-12 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 90 | 1710 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008478 | 2026-10-12 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 90 | 1890 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008479 | 2026-10-12 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008480 | 2026-10-12 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008481 | 2026-10-12 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008482 | 2026-10-12 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008483 | 2026-10-12 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008484 | 2026-10-12 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 21.5 | 75 | 1612.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008485 | 2026-10-12 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008486 | 2026-10-12 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008487 | 2026-10-12 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 75 | 525 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008488 | 2026-10-12 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008489 | 2026-10-12 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008490 | 2026-10-12 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 97.5 | 1803.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008491 | 2026-10-12 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008492 | 2026-10-12 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 97.5 | 1365 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008493 | 2026-10-12 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 75 | 2250 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008494 | 2026-10-12 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008495 | 2026-10-12 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008496 | 2026-10-12 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 22 | 67.5 | 1485 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008497 | 2026-10-12 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 67.5 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008498 | 2026-10-12 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 115 | 2415 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008499 | 2026-10-12 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 10.5 | 115 | 1207.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008500 | 2026-10-12 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008501 | 2026-10-12 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008502 | 2026-10-12 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 87.5 | 1837.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008503 | 2026-10-12 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 87.5 | 1006.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008504 | 2026-10-12 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008505 | 2026-10-12 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008506 | 2026-10-12 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008507 | 2026-10-12 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 90 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008508 | 2026-10-12 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 60 | 750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008509 | 2026-10-12 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27.5 | 60 | 1650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008510 | 2026-10-19 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008511 | 2026-10-19 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008512 | 2026-10-19 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008513 | 2026-10-19 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008514 | 2026-10-19 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008515 | 2026-10-19 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008516 | 2026-10-19 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008517 | 2026-10-19 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008518 | 2026-10-19 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008519 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008520 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008521 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008522 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008523 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008524 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008525 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008526 | 2026-10-19 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008527 | 2026-10-19 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 80 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008528 | 2026-10-19 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008529 | 2026-10-19 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008530 | 2026-10-19 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008531 | 2026-10-19 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008532 | 2026-10-19 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008533 | 2026-10-19 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008534 | 2026-10-19 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 62.5 | 31.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008535 | 2026-10-19 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008536 | 2026-10-19 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 19 | 62.5 | 1187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008537 | 2026-10-19 | E003 | Elena Rossi | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008538 | 2026-10-19 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008539 | 2026-10-19 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008540 | 2026-10-19 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008541 | 2026-10-19 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008542 | 2026-10-19 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008543 | 2026-10-19 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008544 | 2026-10-19 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008545 | 2026-10-19 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008546 | 2026-10-19 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008547 | 2026-10-19 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 12 | 55 | 660 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008548 | 2026-10-19 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008549 | 2026-10-19 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008550 | 2026-10-19 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008551 | 2026-10-19 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008552 | 2026-10-19 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008553 | 2026-10-19 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008554 | 2026-10-19 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008555 | 2026-10-19 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008556 | 2026-10-19 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008557 | 2026-10-19 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008558 | 2026-10-19 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008559 | 2026-10-19 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008560 | 2026-10-19 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008561 | 2026-10-19 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008562 | 2026-10-19 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008563 | 2026-10-19 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008564 | 2026-10-19 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008565 | 2026-10-19 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008566 | 2026-10-19 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008567 | 2026-10-19 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008568 | 2026-10-19 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008569 | 2026-10-19 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008570 | 2026-10-19 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008571 | 2026-10-19 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008572 | 2026-10-19 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35.5 | 150 | 5325 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008573 | 2026-10-19 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008574 | 2026-10-19 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008575 | 2026-10-19 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008576 | 2026-10-19 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008577 | 2026-10-19 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008578 | 2026-10-19 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008579 | 2026-10-19 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008580 | 2026-10-19 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008581 | 2026-10-19 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008582 | 2026-10-19 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17.5 | 85 | 1487.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008583 | 2026-10-19 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008584 | 2026-10-19 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6.5 | 85 | 552.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008585 | 2026-10-19 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 20.5 | 82.5 | 1691.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008586 | 2026-10-19 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18 | 82.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008587 | 2026-10-19 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008588 | 2026-10-19 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008589 | 2026-10-19 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 67.5 | 1350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008590 | 2026-10-19 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008591 | 2026-10-19 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008592 | 2026-10-19 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008593 | 2026-10-19 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008594 | 2026-10-19 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008595 | 2026-10-19 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008596 | 2026-10-19 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008597 | 2026-10-19 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008598 | 2026-10-19 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008599 | 2026-10-19 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008600 | 2026-10-19 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008601 | 2026-10-19 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14 | 55 | 770 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008602 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008603 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008604 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008605 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008606 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008607 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008608 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008609 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008610 | 2026-10-19 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008611 | 2026-10-19 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 22.5 | 120 | 2700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008612 | 2026-10-19 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008613 | 2026-10-19 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 120 | 720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008614 | 2026-10-19 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 28.5 | 100 | 2850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008615 | 2026-10-19 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008616 | 2026-10-19 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008617 | 2026-10-19 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008618 | 2026-10-19 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 75 | 2175 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008619 | 2026-10-19 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008620 | 2026-10-19 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 30 | 67.5 | 2025 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008621 | 2026-10-19 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008622 | 2026-10-19 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008623 | 2026-10-19 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 67.5 | 1957.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008624 | 2026-10-19 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008625 | 2026-10-19 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 102.5 | 768.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008626 | 2026-10-19 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 102.5 | 3331.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008627 | 2026-10-19 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 77.5 | 581.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008628 | 2026-10-19 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 77.5 | 2518.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008629 | 2026-10-19 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008630 | 2026-10-19 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008631 | 2026-10-19 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008632 | 2026-10-19 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008633 | 2026-10-19 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008634 | 2026-10-19 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 16.5 | 82.5 | 1361.25 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008635 | 2026-10-19 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 82.5 | 660 | Rejected | Nicolas Wagner | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008636 | 2026-10-19 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 82.5 | 783.75 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008637 | 2026-10-19 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 19 | 95 | 1805 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008638 | 2026-10-19 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 95 | 1045 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008639 | 2026-10-19 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008640 | 2026-10-19 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 95 | 142.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008641 | 2026-10-19 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 24.5 | 60 | 1470 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008642 | 2026-10-19 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 60 | 930 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008643 | 2026-10-19 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008644 | 2026-10-19 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008645 | 2026-10-19 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 90 | 945 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008646 | 2026-10-19 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 21 | 62.5 | 1312.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008647 | 2026-10-19 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008648 | 2026-10-19 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008649 | 2026-10-19 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 62.5 | 968.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008650 | 2026-10-19 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 13 | 62.5 | 812.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008651 | 2026-10-19 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008652 | 2026-10-19 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008653 | 2026-10-19 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008654 | 2026-10-19 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008655 | 2026-10-19 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008656 | 2026-10-19 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008657 | 2026-10-19 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008658 | 2026-10-19 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008659 | 2026-10-19 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008660 | 2026-10-19 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008661 | 2026-10-19 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008662 | 2026-10-19 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 23.5 | 120 | 2820 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008663 | 2026-10-19 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 120 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008664 | 2026-10-19 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 120 | 420 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008665 | 2026-10-19 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 120 | 240 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008666 | 2026-10-19 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 100 | 2550 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008667 | 2026-10-19 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008668 | 2026-10-19 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 100 | 250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008669 | 2026-10-19 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 18 | 90 | 1620 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008670 | 2026-10-19 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008671 | 2026-10-19 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 90 | 225 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008672 | 2026-10-19 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008673 | 2026-10-19 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 5 | 67.5 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008674 | 2026-10-19 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 3.5 | 67.5 | 236.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008675 | 2026-10-19 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008676 | 2026-10-19 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008677 | 2026-10-19 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008678 | 2026-10-19 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008679 | 2026-10-19 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 23 | 75 | 1725 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008680 | 2026-10-19 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008681 | 2026-10-19 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008682 | 2026-10-19 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008683 | 2026-10-19 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008684 | 2026-10-19 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008685 | 2026-10-19 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 97.5 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008686 | 2026-10-19 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008687 | 2026-10-19 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008688 | 2026-10-19 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008689 | 2026-10-19 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 67.5 | 1451.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008690 | 2026-10-19 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 115 | 2127.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008691 | 2026-10-19 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 115 | 1265 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008692 | 2026-10-19 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 115 | 862.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008693 | 2026-10-19 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 115 | 345 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008694 | 2026-10-19 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 18.5 | 87.5 | 1618.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008695 | 2026-10-19 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008696 | 2026-10-19 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 87.5 | 787.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008697 | 2026-10-19 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 87.5 | 43.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008698 | 2026-10-19 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 90 | 1980 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008699 | 2026-10-19 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008700 | 2026-10-19 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 90 | 945 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008701 | 2026-10-19 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12.5 | 60 | 750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008702 | 2026-10-19 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27.5 | 60 | 1650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008703 | 2026-10-26 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008704 | 2026-10-26 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008705 | 2026-10-26 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008706 | 2026-10-26 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008707 | 2026-10-26 | E001 | Sophie Lambert | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008708 | 2026-10-26 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008709 | 2026-10-26 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008710 | 2026-10-26 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008711 | 2026-10-26 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36 | 97.5 | 3510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008712 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008713 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008714 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008715 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008716 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008717 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008718 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008719 | 2026-10-26 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008720 | 2026-10-26 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 80 | 2640 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008721 | 2026-10-26 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008722 | 2026-10-26 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008723 | 2026-10-26 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008724 | 2026-10-26 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008725 | 2026-10-26 | E003 | Elena Rossi | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008726 | 2026-10-26 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008727 | 2026-10-26 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008728 | 2026-10-26 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008729 | 2026-10-26 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 30.5 | 62.5 | 1906.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008730 | 2026-10-26 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 57.5 | 920 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008731 | 2026-10-26 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008732 | 2026-10-26 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008733 | 2026-10-26 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008734 | 2026-10-26 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008735 | 2026-10-26 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008736 | 2026-10-26 | E005 | Nadia Benali | Finance | P006 | AML Data Quality | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008737 | 2026-10-26 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008738 | 2026-10-26 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008739 | 2026-10-26 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008740 | 2026-10-26 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 55 | 1787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008741 | 2026-10-26 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008742 | 2026-10-26 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008743 | 2026-10-26 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008744 | 2026-10-26 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008745 | 2026-10-26 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 187.5 | 6375 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008746 | 2026-10-26 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008747 | 2026-10-26 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008748 | 2026-10-26 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008749 | 2026-10-26 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008750 | 2026-10-26 | E007 | Claire Muller | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008751 | 2026-10-26 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008752 | 2026-10-26 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008753 | 2026-10-26 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008754 | 2026-10-26 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008755 | 2026-10-26 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008756 | 2026-10-26 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008757 | 2026-10-26 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008758 | 2026-10-26 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008759 | 2026-10-26 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008760 | 2026-10-26 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008761 | 2026-10-26 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008762 | 2026-10-26 | E009 | Amélie Dubois | Executive | P006 | AML Data Quality | WP07 | Steering committee and executive decision support | No | 2 | 150 | 300 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008763 | 2026-10-26 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008764 | 2026-10-26 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 35 | 150 | 5250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008765 | 2026-10-26 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008766 | 2026-10-26 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008767 | 2026-10-26 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008768 | 2026-10-26 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008769 | 2026-10-26 | E010 | David Martin | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008770 | 2026-10-26 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008771 | 2026-10-26 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008772 | 2026-10-26 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008773 | 2026-10-26 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008774 | 2026-10-26 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 17 | 85 | 1445 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008775 | 2026-10-26 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 15 | 85 | 1275 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008776 | 2026-10-26 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 85 | 680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008777 | 2026-10-26 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22 | 82.5 | 1815 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008778 | 2026-10-26 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 18 | 82.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008779 | 2026-10-26 | E013 | Sara Khan | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | Yes | 20.5 | 67.5 | 1383.75 | Approved | Sara Khan | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008780 | 2026-10-26 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 19.5 | 67.5 | 1316.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008781 | 2026-10-26 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008782 | 2026-10-26 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008783 | 2026-10-26 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008784 | 2026-10-26 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008785 | 2026-10-26 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008786 | 2026-10-26 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008787 | 2026-10-26 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008788 | 2026-10-26 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008789 | 2026-10-26 | E015 | Inès Petit | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008790 | 2026-10-26 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008791 | 2026-10-26 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008792 | 2026-10-26 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008793 | 2026-10-26 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 14.5 | 55 | 797.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008794 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008795 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008796 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008797 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008798 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P006 | AML Data Quality | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008799 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008800 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008801 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1 | 65 | 65 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008802 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 8 | 65 | 520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008803 | 2026-10-26 | E016 | Olivier Lefevre | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008804 | 2026-10-26 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 120 | 1860 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008805 | 2026-10-26 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 120 | 840 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008806 | 2026-10-26 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008807 | 2026-10-26 | E017 | Amina Amar | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008808 | 2026-10-26 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 100 | 1550 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008809 | 2026-10-26 | E018 | Gabriel Simon | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 100 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008810 | 2026-10-26 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 100 | 350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008811 | 2026-10-26 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008812 | 2026-10-26 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 30.5 | 100 | 3050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008813 | 2026-10-26 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008814 | 2026-10-26 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008815 | 2026-10-26 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 75 | 1912.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008816 | 2026-10-26 | E020 | Antoine Robert | Data & AI | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 75 | 825 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008817 | 2026-10-26 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 75 | 262.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008818 | 2026-10-26 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 31.5 | 67.5 | 2126.25 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008819 | 2026-10-26 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008820 | 2026-10-26 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008821 | 2026-10-26 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 29 | 67.5 | 1957.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008822 | 2026-10-26 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008823 | 2026-10-26 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 102.5 | 768.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008824 | 2026-10-26 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 102.5 | 3331.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008825 | 2026-10-26 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7 | 77.5 | 542.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008826 | 2026-10-26 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 33 | 77.5 | 2557.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008827 | 2026-10-26 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008828 | 2026-10-26 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008829 | 2026-10-26 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 117.5 | 1703.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008830 | 2026-10-26 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008831 | 2026-10-26 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 117.5 | 822.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008832 | 2026-10-26 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 117.5 | 352.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008833 | 2026-10-26 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 82.5 | 1237.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008834 | 2026-10-26 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 82.5 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008835 | 2026-10-26 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 82.5 | 1402.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008836 | 2026-10-26 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 95 | 1947.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008837 | 2026-10-26 | E028 | Arthur Mercier | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 95 | 1187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008838 | 2026-10-26 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 95 | 617.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008839 | 2026-10-26 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 95 | 47.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008840 | 2026-10-26 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 22 | 60 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008841 | 2026-10-26 | E029 | Chloé Diallo | Consulting | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 60 | 870 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008842 | 2026-10-26 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 60 | 210 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008843 | 2026-10-26 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 90 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008844 | 2026-10-26 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008845 | 2026-10-26 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 90 | 990 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008846 | 2026-10-26 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 62.5 | 1312.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008847 | 2026-10-26 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 62.5 | 531.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008848 | 2026-10-26 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 62.5 | 656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008849 | 2026-10-26 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 62.5 | 1062.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008850 | 2026-10-26 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008851 | 2026-10-26 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008852 | 2026-10-26 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008853 | 2026-10-26 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008854 | 2026-10-26 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008855 | 2026-10-26 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008856 | 2026-10-26 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008857 | 2026-10-26 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008858 | 2026-10-26 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008859 | 2026-10-26 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008860 | 2026-10-26 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008861 | 2026-10-26 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008862 | 2026-10-26 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 120 | 1440 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008863 | 2026-10-26 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 120 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008864 | 2026-10-26 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008865 | 2026-10-26 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 28.5 | 100 | 2850 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008866 | 2026-10-26 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 100 | 1150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008867 | 2026-10-26 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008868 | 2026-10-26 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 20 | 90 | 1800 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008869 | 2026-10-26 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008870 | 2026-10-26 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008871 | 2026-10-26 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 67.5 | 607.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008872 | 2026-10-26 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008873 | 2026-10-26 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008874 | 2026-10-26 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008875 | 2026-10-26 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 23.5 | 75 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008876 | 2026-10-26 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008877 | 2026-10-26 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008878 | 2026-10-26 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008879 | 2026-10-26 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008880 | 2026-10-26 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008881 | 2026-10-26 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 97.5 | 1121.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008882 | 2026-10-26 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 30 | 75 | 2250 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008883 | 2026-10-26 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008884 | 2026-10-26 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 75 | 187.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008885 | 2026-10-26 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008886 | 2026-10-26 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 67.5 | 776.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008887 | 2026-10-26 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008888 | 2026-10-26 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 115 | 2242.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008889 | 2026-10-26 | E047 | Mia Nowak | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 115 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008890 | 2026-10-26 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008891 | 2026-10-26 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 115 | 57.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008892 | 2026-10-26 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 18 | 87.5 | 1575 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008893 | 2026-10-26 | E048 | Raphaël Meyer | Cybersecurity | P006 | AML Data Quality | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 87.5 | 1050 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008894 | 2026-10-26 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP05 | Testing, defect resolution and acceptance support | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008895 | 2026-10-26 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 87.5 | 131.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008896 | 2026-10-26 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 90 | 1125 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008897 | 2026-10-26 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 90 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008898 | 2026-10-26 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 90 | 585 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008899 | 2026-10-26 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008900 | 2026-10-26 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 60 | 720 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008901 | 2026-10-26 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 28 | 60 | 1680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008902 | 2026-11-02 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008903 | 2026-11-02 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008904 | 2026-11-02 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008905 | 2026-11-02 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008906 | 2026-11-02 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008907 | 2026-11-02 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008908 | 2026-11-02 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008909 | 2026-11-02 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28.5 | 97.5 | 2778.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008910 | 2026-11-02 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008911 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008912 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008913 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008914 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008915 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008916 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008917 | 2026-11-02 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008918 | 2026-11-02 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 28.5 | 80 | 2280 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008919 | 2026-11-02 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008920 | 2026-11-02 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008921 | 2026-11-02 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008922 | 2026-11-02 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008923 | 2026-11-02 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008924 | 2026-11-02 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008925 | 2026-11-02 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008926 | 2026-11-02 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008927 | 2026-11-02 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 25 | 62.5 | 1562.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008928 | 2026-11-02 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008929 | 2026-11-02 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 57.5 | 1840 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008930 | 2026-11-02 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008931 | 2026-11-02 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008932 | 2026-11-02 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008933 | 2026-11-02 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008934 | 2026-11-02 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008935 | 2026-11-02 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008936 | 2026-11-02 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008937 | 2026-11-02 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008938 | 2026-11-02 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 20.5 | 55 | 1127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008939 | 2026-11-02 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008940 | 2026-11-02 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008941 | 2026-11-02 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008942 | 2026-11-02 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008943 | 2026-11-02 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008944 | 2026-11-02 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008945 | 2026-11-02 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 29 | 187.5 | 5437.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008946 | 2026-11-02 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008947 | 2026-11-02 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008948 | 2026-11-02 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008949 | 2026-11-02 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008950 | 2026-11-02 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008951 | 2026-11-02 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008952 | 2026-11-02 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008953 | 2026-11-02 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008954 | 2026-11-02 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 28.5 | 157.5 | 4488.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008955 | 2026-11-02 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008956 | 2026-11-02 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008957 | 2026-11-02 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008958 | 2026-11-02 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008959 | 2026-11-02 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008960 | 2026-11-02 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1.5 | 162.5 | 243.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008961 | 2026-11-02 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24 | 162.5 | 3900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008962 | 2026-11-02 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008963 | 2026-11-02 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008964 | 2026-11-02 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008965 | 2026-11-02 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 29 | 150 | 4350 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008966 | 2026-11-02 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008967 | 2026-11-02 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008968 | 2026-11-02 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008969 | 2026-11-02 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008970 | 2026-11-02 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008971 | 2026-11-02 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008972 | 2026-11-02 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008973 | 2026-11-02 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008974 | 2026-11-02 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21.5 | 105 | 2257.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008975 | 2026-11-02 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008976 | 2026-11-02 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 7.5 | 85 | 637.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008977 | 2026-11-02 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 6.5 | 85 | 552.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008978 | 2026-11-02 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 2 | 85 | 170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008979 | 2026-11-02 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008980 | 2026-11-02 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008981 | 2026-11-02 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 16 | 82.5 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008982 | 2026-11-02 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 14.5 | 82.5 | 1196.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008983 | 2026-11-02 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 5.5 | 82.5 | 453.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008984 | 2026-11-02 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008985 | 2026-11-02 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008986 | 2026-11-02 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008987 | 2026-11-02 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008988 | 2026-11-02 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 4.5 | 67.5 | 303.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008989 | 2026-11-02 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 3 | 67.5 | 202.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008990 | 2026-11-02 | E014 | Nicolas Wagner | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008991 | 2026-11-02 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008992 | 2026-11-02 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008993 | 2026-11-02 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008994 | 2026-11-02 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008995 | 2026-11-02 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008996 | 2026-11-02 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008997 | 2026-11-02 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008998 | 2026-11-02 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2.5 | 55 | 137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-008999 | 2026-11-02 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 13.5 | 55 | 742.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009000 | 2026-11-02 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009001 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009002 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009003 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009004 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009005 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009006 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009007 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 1.5 | 65 | 97.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009008 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 21.5 | 65 | 1397.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009009 | 2026-11-02 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009010 | 2026-11-02 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 120 | 2400 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009011 | 2026-11-02 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 120 | 1080 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009012 | 2026-11-02 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 120 | 360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009013 | 2026-11-02 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009014 | 2026-11-02 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 24 | 100 | 2400 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009015 | 2026-11-02 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8 | 100 | 800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009016 | 2026-11-02 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009017 | 2026-11-02 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 26 | 100 | 2600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009018 | 2026-11-02 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 100 | 600 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009019 | 2026-11-02 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009020 | 2026-11-02 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 75 | 1650 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009021 | 2026-11-02 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 75 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009022 | 2026-11-02 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009023 | 2026-11-02 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 26.5 | 67.5 | 1788.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009024 | 2026-11-02 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 5.5 | 67.5 | 371.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009025 | 2026-11-02 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009026 | 2026-11-02 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 67.5 | 1485 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009027 | 2026-11-02 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 67.5 | 607.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009028 | 2026-11-02 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009029 | 2026-11-02 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009030 | 2026-11-02 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 102.5 | 666.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009031 | 2026-11-02 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 25.5 | 102.5 | 2613.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009032 | 2026-11-02 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009033 | 2026-11-02 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 77.5 | 465 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009034 | 2026-11-02 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 26 | 77.5 | 2015 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009035 | 2026-11-02 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009036 | 2026-11-02 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16 | 65 | 1040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009037 | 2026-11-02 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009038 | 2026-11-02 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009039 | 2026-11-02 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 117.5 | 1351.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009040 | 2026-11-02 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 117.5 | 1351.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009041 | 2026-11-02 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 117.5 | 705 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009042 | 2026-11-02 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 117.5 | 352.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009043 | 2026-11-02 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009044 | 2026-11-02 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 82.5 | 1072.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009045 | 2026-11-02 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 82.5 | 495 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009046 | 2026-11-02 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 82.5 | 1072.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009047 | 2026-11-02 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009048 | 2026-11-02 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 95 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009049 | 2026-11-02 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 95 | 570 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009050 | 2026-11-02 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 95 | 855 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009051 | 2026-11-02 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009052 | 2026-11-02 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 60 | 1260 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009053 | 2026-11-02 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 60 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009054 | 2026-11-02 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009055 | 2026-11-02 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 90 | 1305 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009056 | 2026-11-02 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 90 | 630 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009057 | 2026-11-02 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 90 | 945 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009058 | 2026-11-02 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009059 | 2026-11-02 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 62.5 | 906.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009060 | 2026-11-02 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 62.5 | 437.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009061 | 2026-11-02 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 62.5 | 656.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009062 | 2026-11-02 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009063 | 2026-11-02 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009064 | 2026-11-02 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 9 | 62.5 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009065 | 2026-11-02 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 62.5 | 687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009066 | 2026-11-02 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009067 | 2026-11-02 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009068 | 2026-11-02 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3 | 105 | 315 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009069 | 2026-11-02 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009070 | 2026-11-02 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009071 | 2026-11-02 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009072 | 2026-11-02 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009073 | 2026-11-02 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 26 | 72.5 | 1885 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009074 | 2026-11-02 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009075 | 2026-11-02 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009076 | 2026-11-02 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009077 | 2026-11-02 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 55 | 1760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009078 | 2026-11-02 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009079 | 2026-11-02 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 67.5 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009080 | 2026-11-02 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009081 | 2026-11-02 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 120 | 2280 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009082 | 2026-11-02 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 9.5 | 120 | 1140 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009083 | 2026-11-02 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 3 | 120 | 360 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009084 | 2026-11-02 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 120 | 60 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009085 | 2026-11-02 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009086 | 2026-11-02 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009087 | 2026-11-02 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 100 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009088 | 2026-11-02 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 100 | 50 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009089 | 2026-11-02 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009090 | 2026-11-02 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009091 | 2026-11-02 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 17 | 90 | 1530 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009092 | 2026-11-02 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 15 | 90 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009093 | 2026-11-02 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009094 | 2026-11-02 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 67.5 | 1046.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009095 | 2026-11-02 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 67.5 | 607.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009096 | 2026-11-02 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 67.5 | 438.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009097 | 2026-11-02 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 67.5 | 67.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009098 | 2026-11-02 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009099 | 2026-11-02 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 75 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009100 | 2026-11-02 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 16 | 75 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009101 | 2026-11-02 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009102 | 2026-11-02 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 75 | 1425 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009103 | 2026-11-02 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 6.5 | 75 | 487.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009104 | 2026-11-02 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 6 | 75 | 450 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009105 | 2026-11-02 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009106 | 2026-11-02 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009107 | 2026-11-02 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 97.5 | 1462.5 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009108 | 2026-11-02 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 97.5 | 682.5 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009109 | 2026-11-02 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 97.5 | 975 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009110 | 2026-11-02 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009111 | 2026-11-02 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 75 | 975 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009112 | 2026-11-02 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 3 | 75 | 225 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009113 | 2026-11-02 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009114 | 2026-11-02 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009115 | 2026-11-02 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 67.5 | 1147.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009116 | 2026-11-02 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15 | 67.5 | 1012.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009117 | 2026-11-02 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009118 | 2026-11-02 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 115 | 1955 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009119 | 2026-11-02 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 115 | 747.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009120 | 2026-11-02 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 8.5 | 115 | 977.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009121 | 2026-11-02 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009122 | 2026-11-02 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 87.5 | 1443.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009123 | 2026-11-02 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 87.5 | 568.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009124 | 2026-11-02 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9 | 87.5 | 787.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009125 | 2026-11-02 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009126 | 2026-11-02 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 90 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009127 | 2026-11-02 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 90 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009128 | 2026-11-02 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 90 | 990 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009129 | 2026-11-02 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009130 | 2026-11-02 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP05 | Testing, defect resolution and acceptance support | Yes | 2.5 | 60 | 150 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009131 | 2026-11-02 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 60 | 330 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009132 | 2026-11-02 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009133 | 2026-11-02 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 8 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009134 | 2026-11-09 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009135 | 2026-11-09 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009136 | 2026-11-09 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009137 | 2026-11-09 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009138 | 2026-11-09 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009139 | 2026-11-09 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009140 | 2026-11-09 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009141 | 2026-11-09 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009142 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009143 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009144 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009145 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009146 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009147 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009148 | 2026-11-09 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009149 | 2026-11-09 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 80 | 2640 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009150 | 2026-11-09 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009151 | 2026-11-09 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009152 | 2026-11-09 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009153 | 2026-11-09 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009154 | 2026-11-09 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009155 | 2026-11-09 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009156 | 2026-11-09 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009157 | 2026-11-09 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 62.5 | 2062.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009158 | 2026-11-09 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009159 | 2026-11-09 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009160 | 2026-11-09 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009161 | 2026-11-09 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009162 | 2026-11-09 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009163 | 2026-11-09 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009164 | 2026-11-09 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009165 | 2026-11-09 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009166 | 2026-11-09 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 55 | 1870 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009167 | 2026-11-09 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009168 | 2026-11-09 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009169 | 2026-11-09 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009170 | 2026-11-09 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009171 | 2026-11-09 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009172 | 2026-11-09 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009173 | 2026-11-09 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009174 | 2026-11-09 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009175 | 2026-11-09 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009176 | 2026-11-09 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009177 | 2026-11-09 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009178 | 2026-11-09 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009179 | 2026-11-09 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33.5 | 157.5 | 5276.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009180 | 2026-11-09 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009181 | 2026-11-09 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009182 | 2026-11-09 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009183 | 2026-11-09 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009184 | 2026-11-09 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009185 | 2026-11-09 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009186 | 2026-11-09 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009187 | 2026-11-09 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009188 | 2026-11-09 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 150 | 5550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009189 | 2026-11-09 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009190 | 2026-11-09 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009191 | 2026-11-09 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009192 | 2026-11-09 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009193 | 2026-11-09 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009194 | 2026-11-09 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009195 | 2026-11-09 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009196 | 2026-11-09 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009197 | 2026-11-09 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18 | 85 | 1530 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009198 | 2026-11-09 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009199 | 2026-11-09 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 6 | 85 | 510 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009200 | 2026-11-09 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 13.5 | 82.5 | 1113.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009201 | 2026-11-09 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 10.5 | 82.5 | 866.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009202 | 2026-11-09 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009203 | 2026-11-09 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009204 | 2026-11-09 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 20 | 67.5 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009205 | 2026-11-09 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009206 | 2026-11-09 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009207 | 2026-11-09 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009208 | 2026-11-09 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009209 | 2026-11-09 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009210 | 2026-11-09 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009211 | 2026-11-09 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009212 | 2026-11-09 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009213 | 2026-11-09 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 55 | 110 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009214 | 2026-11-09 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 10 | 55 | 550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009215 | 2026-11-09 | E015 | Inès Petit | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009216 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009217 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009218 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009219 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009220 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009221 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009222 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009223 | 2026-11-09 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009224 | 2026-11-09 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009225 | 2026-11-09 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 120 | 1440 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009226 | 2026-11-09 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 120 | 540 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009227 | 2026-11-09 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 29.5 | 100 | 2950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009228 | 2026-11-09 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10.5 | 100 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009229 | 2026-11-09 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009230 | 2026-11-09 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009231 | 2026-11-09 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 75 | 1387.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009232 | 2026-11-09 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 75 | 712.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009233 | 2026-11-09 | E020 | Antoine Robert | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009234 | 2026-11-09 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009235 | 2026-11-09 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009236 | 2026-11-09 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009237 | 2026-11-09 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009238 | 2026-11-09 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 102.5 | 871.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009239 | 2026-11-09 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 102.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009240 | 2026-11-09 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 77.5 | 658.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009241 | 2026-11-09 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 77.5 | 2441.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009242 | 2026-11-09 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009243 | 2026-11-09 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009244 | 2026-11-09 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 117.5 | 1821.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009245 | 2026-11-09 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009246 | 2026-11-09 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 82.5 | 1361.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009247 | 2026-11-09 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 82.5 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009248 | 2026-11-09 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15.5 | 82.5 | 1278.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009249 | 2026-11-09 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 95 | 1757.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009250 | 2026-11-09 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009251 | 2026-11-09 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 95 | 1235 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009252 | 2026-11-09 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 60 | 1320 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009253 | 2026-11-09 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 60 | 1080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009254 | 2026-11-09 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009255 | 2026-11-09 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009256 | 2026-11-09 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 90 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009257 | 2026-11-09 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009258 | 2026-11-09 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 62.5 | 562.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009259 | 2026-11-09 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009260 | 2026-11-09 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 62.5 | 906.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009261 | 2026-11-09 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009262 | 2026-11-09 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 62.5 | 875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009263 | 2026-11-09 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009264 | 2026-11-09 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009265 | 2026-11-09 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25 | 105 | 2625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009266 | 2026-11-09 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009267 | 2026-11-09 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009268 | 2026-11-09 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3 | 72.5 | 217.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009269 | 2026-11-09 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 25.5 | 72.5 | 1848.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009270 | 2026-11-09 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009271 | 2026-11-09 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009272 | 2026-11-09 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009273 | 2026-11-09 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 67.5 | 1080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009274 | 2026-11-09 | E037 | Lina Gomes | Operations | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009275 | 2026-11-09 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 24.5 | 120 | 2940 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009276 | 2026-11-09 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 120 | 1380 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009277 | 2026-11-09 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009278 | 2026-11-09 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 120 | 240 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009279 | 2026-11-09 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 28 | 100 | 2800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009280 | 2026-11-09 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 100 | 1200 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009281 | 2026-11-09 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009282 | 2026-11-09 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009283 | 2026-11-09 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 90 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009284 | 2026-11-09 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 67.5 | 1248.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009285 | 2026-11-09 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009286 | 2026-11-09 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009287 | 2026-11-09 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 67.5 | 135 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009288 | 2026-11-09 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009289 | 2026-11-09 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009290 | 2026-11-09 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 75 | 975 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009291 | 2026-11-09 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 75 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009292 | 2026-11-09 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP05 | Testing, defect resolution and acceptance support | Yes | 4.5 | 75 | 337.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009293 | 2026-11-09 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009294 | 2026-11-09 | E043 | Manon Franco | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009295 | 2026-11-09 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009296 | 2026-11-09 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009297 | 2026-11-09 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 97.5 | 1218.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009298 | 2026-11-09 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 75 | 2400 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009299 | 2026-11-09 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009300 | 2026-11-09 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 67.5 | 1417.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009301 | 2026-11-09 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 67.5 | 1282.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009302 | 2026-11-09 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009303 | 2026-11-09 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009304 | 2026-11-09 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 115 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009305 | 2026-11-09 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009306 | 2026-11-09 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009307 | 2026-11-09 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 87.5 | 1181.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009308 | 2026-11-09 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18 | 90 | 1620 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009309 | 2026-11-09 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009310 | 2026-11-09 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 90 | 1260 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009311 | 2026-11-09 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 60 | 420 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009312 | 2026-11-09 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17 | 60 | 1020 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009313 | 2026-11-09 | E050 | Mathis Girard | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009314 | 2026-11-16 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009315 | 2026-11-16 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009316 | 2026-11-16 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009317 | 2026-11-16 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009318 | 2026-11-16 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009319 | 2026-11-16 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009320 | 2026-11-16 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009321 | 2026-11-16 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009322 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009323 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009324 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009325 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009326 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009327 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009328 | 2026-11-16 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009329 | 2026-11-16 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 80 | 2720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009330 | 2026-11-16 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009331 | 2026-11-16 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009332 | 2026-11-16 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009333 | 2026-11-16 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009334 | 2026-11-16 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009335 | 2026-11-16 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009336 | 2026-11-16 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009337 | 2026-11-16 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 62.5 | 2031.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009338 | 2026-11-16 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009339 | 2026-11-16 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009340 | 2026-11-16 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009341 | 2026-11-16 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009342 | 2026-11-16 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009343 | 2026-11-16 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009344 | 2026-11-16 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009345 | 2026-11-16 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009346 | 2026-11-16 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 20.5 | 55 | 1127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009347 | 2026-11-16 | E005 | Nadia Benali | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009348 | 2026-11-16 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009349 | 2026-11-16 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009350 | 2026-11-16 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009351 | 2026-11-16 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 187.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009352 | 2026-11-16 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 14 | 187.5 | 2625 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009353 | 2026-11-16 | E006 | Jean Schmit | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009354 | 2026-11-16 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009355 | 2026-11-16 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009356 | 2026-11-16 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009357 | 2026-11-16 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009358 | 2026-11-16 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009359 | 2026-11-16 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009360 | 2026-11-16 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009361 | 2026-11-16 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 33 | 157.5 | 5197.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009362 | 2026-11-16 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009363 | 2026-11-16 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009364 | 2026-11-16 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009365 | 2026-11-16 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009366 | 2026-11-16 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009367 | 2026-11-16 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009368 | 2026-11-16 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009369 | 2026-11-16 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009370 | 2026-11-16 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 150 | 5550 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009371 | 2026-11-16 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009372 | 2026-11-16 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009373 | 2026-11-16 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009374 | 2026-11-16 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009375 | 2026-11-16 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009376 | 2026-11-16 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009377 | 2026-11-16 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009378 | 2026-11-16 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009379 | 2026-11-16 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 7.5 | 85 | 637.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009380 | 2026-11-16 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 7 | 85 | 595 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009381 | 2026-11-16 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 85 | 127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009382 | 2026-11-16 | E011 | Maya Fernandes | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009383 | 2026-11-16 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 22.5 | 82.5 | 1856.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009384 | 2026-11-16 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 16.5 | 82.5 | 1361.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009385 | 2026-11-16 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1 | 82.5 | 82.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009386 | 2026-11-16 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009387 | 2026-11-16 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009388 | 2026-11-16 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009389 | 2026-11-16 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009390 | 2026-11-16 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009391 | 2026-11-16 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009392 | 2026-11-16 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009393 | 2026-11-16 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009394 | 2026-11-16 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009395 | 2026-11-16 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009396 | 2026-11-16 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009397 | 2026-11-16 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009398 | 2026-11-16 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17.5 | 55 | 962.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009399 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009400 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009401 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009402 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009403 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009404 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009405 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009406 | 2026-11-16 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009407 | 2026-11-16 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009408 | 2026-11-16 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 120 | 1560 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009409 | 2026-11-16 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009410 | 2026-11-16 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 100 | 1150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009411 | 2026-11-16 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 100 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009412 | 2026-11-16 | E018 | Gabriel Simon | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009413 | 2026-11-16 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 31.5 | 100 | 3150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009414 | 2026-11-16 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 100 | 700 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009415 | 2026-11-16 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009416 | 2026-11-16 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 75 | 2287.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009417 | 2026-11-16 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 75 | 712.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009418 | 2026-11-16 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009419 | 2026-11-16 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009420 | 2026-11-16 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 26 | 67.5 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009421 | 2026-11-16 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009422 | 2026-11-16 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009423 | 2026-11-16 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 102.5 | 512.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009424 | 2026-11-16 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 102.5 | 1947.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009425 | 2026-11-16 | E023 | Mila Costa | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009426 | 2026-11-16 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 77.5 | 658.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009427 | 2026-11-16 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 77.5 | 2441.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009428 | 2026-11-16 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009429 | 2026-11-16 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009430 | 2026-11-16 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 117.5 | 1880 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009431 | 2026-11-16 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 117.5 | 881.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009432 | 2026-11-16 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009433 | 2026-11-16 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 82.5 | 1361.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009434 | 2026-11-16 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 82.5 | 742.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009435 | 2026-11-16 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 82.5 | 1196.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009436 | 2026-11-16 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 95 | 1995 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009437 | 2026-11-16 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 95 | 712.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009438 | 2026-11-16 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 95 | 1092.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009439 | 2026-11-16 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 22.5 | 60 | 1350 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009440 | 2026-11-16 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 60 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009441 | 2026-11-16 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009442 | 2026-11-16 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009443 | 2026-11-16 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 90 | 1125 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009444 | 2026-11-16 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 62.5 | 1250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009445 | 2026-11-16 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 62.5 | 500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009446 | 2026-11-16 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 62.5 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009447 | 2026-11-16 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 62.5 | 1031.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009448 | 2026-11-16 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 62.5 | 750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009449 | 2026-11-16 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 62.5 | 718.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009450 | 2026-11-16 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 105 | 367.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009451 | 2026-11-16 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009452 | 2026-11-16 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 105 | 3412.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009453 | 2026-11-16 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009454 | 2026-11-16 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009455 | 2026-11-16 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32.5 | 72.5 | 2356.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009456 | 2026-11-16 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009457 | 2026-11-16 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009458 | 2026-11-16 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009459 | 2026-11-16 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009460 | 2026-11-16 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 120 | 1560 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009461 | 2026-11-16 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009462 | 2026-11-16 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 120 | 120 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009463 | 2026-11-16 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 26 | 100 | 2600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009464 | 2026-11-16 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 100 | 1250 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009465 | 2026-11-16 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009466 | 2026-11-16 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009467 | 2026-11-16 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009468 | 2026-11-16 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009469 | 2026-11-16 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 67.5 | 1383.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009470 | 2026-11-16 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009471 | 2026-11-16 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 67.5 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009472 | 2026-11-16 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 75 | 1387.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009473 | 2026-11-16 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009474 | 2026-11-16 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009475 | 2026-11-16 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 24 | 75 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009476 | 2026-11-16 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009477 | 2026-11-16 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009478 | 2026-11-16 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 97.5 | 1560 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009479 | 2026-11-16 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 6 | 97.5 | 585 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009480 | 2026-11-16 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 97.5 | 975 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009481 | 2026-11-16 | E044 | Yanis Vidal | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009482 | 2026-11-16 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 75 | 2437.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009483 | 2026-11-16 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 75 | 562.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009484 | 2026-11-16 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 67.5 | 1248.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009485 | 2026-11-16 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 67.5 | 1451.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009486 | 2026-11-16 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 115 | 1265 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009487 | 2026-11-16 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 115 | 517.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009488 | 2026-11-16 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 115 | 517.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009489 | 2026-11-16 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009490 | 2026-11-16 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009491 | 2026-11-16 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009492 | 2026-11-16 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 87.5 | 1006.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009493 | 2026-11-16 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009494 | 2026-11-16 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 90 | 765 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009495 | 2026-11-16 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 90 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009496 | 2026-11-16 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 60 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009497 | 2026-11-16 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27 | 60 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009498 | 2026-11-23 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009499 | 2026-11-23 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009500 | 2026-11-23 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009501 | 2026-11-23 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009502 | 2026-11-23 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009503 | 2026-11-23 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009504 | 2026-11-23 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009505 | 2026-11-23 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009506 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009507 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009508 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009509 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009510 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009511 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009512 | 2026-11-23 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009513 | 2026-11-23 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 80 | 2720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009514 | 2026-11-23 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009515 | 2026-11-23 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009516 | 2026-11-23 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009517 | 2026-11-23 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009518 | 2026-11-23 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009519 | 2026-11-23 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009520 | 2026-11-23 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009521 | 2026-11-23 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31.5 | 62.5 | 1968.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009522 | 2026-11-23 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009523 | 2026-11-23 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009524 | 2026-11-23 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009525 | 2026-11-23 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009526 | 2026-11-23 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009527 | 2026-11-23 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009528 | 2026-11-23 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009529 | 2026-11-23 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009530 | 2026-11-23 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 55 | 1897.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009531 | 2026-11-23 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009532 | 2026-11-23 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009533 | 2026-11-23 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009534 | 2026-11-23 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Pending | Maya Fernandes | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009535 | 2026-11-23 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009536 | 2026-11-23 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009537 | 2026-11-23 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009538 | 2026-11-23 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009539 | 2026-11-23 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009540 | 2026-11-23 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009541 | 2026-11-23 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009542 | 2026-11-23 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009543 | 2026-11-23 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34 | 157.5 | 5355 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009544 | 2026-11-23 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009545 | 2026-11-23 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009546 | 2026-11-23 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009547 | 2026-11-23 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009548 | 2026-11-23 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009549 | 2026-11-23 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009550 | 2026-11-23 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 150 | 150 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009551 | 2026-11-23 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009552 | 2026-11-23 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 29.5 | 150 | 4425 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009553 | 2026-11-23 | E009 | Amélie Dubois | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009554 | 2026-11-23 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009555 | 2026-11-23 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009556 | 2026-11-23 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009557 | 2026-11-23 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009558 | 2026-11-23 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009559 | 2026-11-23 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009560 | 2026-11-23 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009561 | 2026-11-23 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009562 | 2026-11-23 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 18.5 | 85 | 1572.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009563 | 2026-11-23 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 17 | 85 | 1445 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009564 | 2026-11-23 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4.5 | 85 | 382.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009565 | 2026-11-23 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 21 | 82.5 | 1732.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009566 | 2026-11-23 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17.5 | 82.5 | 1443.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009567 | 2026-11-23 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 82.5 | 123.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009568 | 2026-11-23 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009569 | 2026-11-23 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 18 | 67.5 | 1215 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009570 | 2026-11-23 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12.5 | 67.5 | 843.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009571 | 2026-11-23 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009572 | 2026-11-23 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009573 | 2026-11-23 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009574 | 2026-11-23 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009575 | 2026-11-23 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009576 | 2026-11-23 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009577 | 2026-11-23 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009578 | 2026-11-23 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009579 | 2026-11-23 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009580 | 2026-11-23 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 17 | 55 | 935 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009581 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009582 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009583 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009584 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009585 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009586 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009587 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009588 | 2026-11-23 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009589 | 2026-11-23 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009590 | 2026-11-23 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 120 | 1500 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009591 | 2026-11-23 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009592 | 2026-11-23 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 27.5 | 100 | 2750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009593 | 2026-11-23 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 100 | 1250 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009594 | 2026-11-23 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 100 | 3250 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009595 | 2026-11-23 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 100 | 750 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009596 | 2026-11-23 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 28.5 | 75 | 2137.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009597 | 2026-11-23 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 75 | 862.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009598 | 2026-11-23 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 67.5 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009599 | 2026-11-23 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009600 | 2026-11-23 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 28.5 | 67.5 | 1923.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009601 | 2026-11-23 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009602 | 2026-11-23 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 102.5 | 768.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009603 | 2026-11-23 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 102.5 | 3331.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009604 | 2026-11-23 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 77.5 | 542.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009605 | 2026-11-23 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 33 | 77.5 | 2557.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009606 | 2026-11-23 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009607 | 2026-11-23 | E025 | Camille Garcia | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009608 | 2026-11-23 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 117.5 | 1821.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009609 | 2026-11-23 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16.5 | 117.5 | 1938.75 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009610 | 2026-11-23 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 117.5 | 881.25 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009611 | 2026-11-23 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 117.5 | 58.75 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009612 | 2026-11-23 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 16 | 82.5 | 1320 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009613 | 2026-11-23 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 82.5 | 701.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009614 | 2026-11-23 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15.5 | 82.5 | 1278.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009615 | 2026-11-23 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 95 | 1140 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009616 | 2026-11-23 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 95 | 427.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009617 | 2026-11-23 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 7.5 | 95 | 712.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009618 | 2026-11-23 | E028 | Arthur Mercier | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009619 | 2026-11-23 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 60 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009620 | 2026-11-23 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 60 | 870 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009621 | 2026-11-23 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009622 | 2026-11-23 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009623 | 2026-11-23 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 90 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009624 | 2026-11-23 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 62.5 | 1156.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009625 | 2026-11-23 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 62.5 | 468.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009626 | 2026-11-23 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 62.5 | 875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009627 | 2026-11-23 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 10.5 | 62.5 | 656.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009628 | 2026-11-23 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 62.5 | 437.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009629 | 2026-11-23 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 62.5 | 406.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009630 | 2026-11-23 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009631 | 2026-11-23 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009632 | 2026-11-23 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009633 | 2026-11-23 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 105 | 3360 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009634 | 2026-11-23 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 3.5 | 72.5 | 253.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009635 | 2026-11-23 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009636 | 2026-11-23 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009637 | 2026-11-23 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 16 | 65 | 1040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009638 | 2026-11-23 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009639 | 2026-11-23 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009640 | 2026-11-23 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009641 | 2026-11-23 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 120 | 1020 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009642 | 2026-11-23 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 120 | 540 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009643 | 2026-11-23 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 1.5 | 120 | 180 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009644 | 2026-11-23 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009645 | 2026-11-23 | E038 | Paul Lemoine | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009646 | 2026-11-23 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 29 | 100 | 2900 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009647 | 2026-11-23 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009648 | 2026-11-23 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009649 | 2026-11-23 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009650 | 2026-11-23 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 90 | 90 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009651 | 2026-11-23 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18 | 67.5 | 1215 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009652 | 2026-11-23 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009653 | 2026-11-23 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 67.5 | 573.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009654 | 2026-11-23 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009655 | 2026-11-23 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 75 | 1462.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009656 | 2026-11-23 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 75 | 1537.5 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009657 | 2026-11-23 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 25 | 75 | 1875 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009658 | 2026-11-23 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009659 | 2026-11-23 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 75 | 525 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009660 | 2026-11-23 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009661 | 2026-11-23 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 97.5 | 1803.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009662 | 2026-11-23 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 97.5 | 731.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009663 | 2026-11-23 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 97.5 | 1365 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009664 | 2026-11-23 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 18 | 75 | 1350 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009665 | 2026-11-23 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 75 | 337.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009666 | 2026-11-23 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 75 | 112.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009667 | 2026-11-23 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009668 | 2026-11-23 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009669 | 2026-11-23 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 67.5 | 1417.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009670 | 2026-11-23 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 115 | 2185 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009671 | 2026-11-23 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009672 | 2026-11-23 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13 | 115 | 1495 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009673 | 2026-11-23 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 87.5 | 1793.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009674 | 2026-11-23 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 87.5 | 743.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009675 | 2026-11-23 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11 | 87.5 | 962.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009676 | 2026-11-23 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009677 | 2026-11-23 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009678 | 2026-11-23 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 90 | 1260 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009679 | 2026-11-23 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 60 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009680 | 2026-11-23 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 29 | 60 | 1740 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009681 | 2026-11-30 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009682 | 2026-11-30 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009683 | 2026-11-30 | E001 | Sophie Lambert | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009684 | 2026-11-30 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009685 | 2026-11-30 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009686 | 2026-11-30 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009687 | 2026-11-30 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009688 | 2026-11-30 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 36.5 | 97.5 | 3558.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009689 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009690 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009691 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009692 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009693 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009694 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009695 | 2026-11-30 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009696 | 2026-11-30 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33 | 80 | 2640 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009697 | 2026-11-30 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009698 | 2026-11-30 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009699 | 2026-11-30 | E003 | Elena Rossi | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009700 | 2026-11-30 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009701 | 2026-11-30 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009702 | 2026-11-30 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009703 | 2026-11-30 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009704 | 2026-11-30 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 31 | 62.5 | 1937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009705 | 2026-11-30 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009706 | 2026-11-30 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009707 | 2026-11-30 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009708 | 2026-11-30 | E005 | Nadia Benali | Finance | P003 | Core Banking Modernisation | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009709 | 2026-11-30 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009710 | 2026-11-30 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009711 | 2026-11-30 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009712 | 2026-11-30 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009713 | 2026-11-30 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 55 | 1842.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009714 | 2026-11-30 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009715 | 2026-11-30 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009716 | 2026-11-30 | E006 | Jean Schmit | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009717 | 2026-11-30 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009718 | 2026-11-30 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 36 | 187.5 | 6750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009719 | 2026-11-30 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009720 | 2026-11-30 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009721 | 2026-11-30 | E007 | Claire Muller | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009722 | 2026-11-30 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009723 | 2026-11-30 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009724 | 2026-11-30 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009725 | 2026-11-30 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009726 | 2026-11-30 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 20.5 | 157.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009727 | 2026-11-30 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009728 | 2026-11-30 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009729 | 2026-11-30 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009730 | 2026-11-30 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009731 | 2026-11-30 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009732 | 2026-11-30 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009733 | 2026-11-30 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009734 | 2026-11-30 | E009 | Amélie Dubois | Executive | P003 | Core Banking Modernisation | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009735 | 2026-11-30 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009736 | 2026-11-30 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 150 | 5550 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009737 | 2026-11-30 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009738 | 2026-11-30 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009739 | 2026-11-30 | E010 | David Martin | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009740 | 2026-11-30 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009741 | 2026-11-30 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009742 | 2026-11-30 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009743 | 2026-11-30 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009744 | 2026-11-30 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 105 | 2730 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009745 | 2026-11-30 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009746 | 2026-11-30 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009747 | 2026-11-30 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4.5 | 85 | 382.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009748 | 2026-11-30 | E012 | Julien Bernard | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | Yes | 9 | 82.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009749 | 2026-11-30 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 6.5 | 82.5 | 536.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009750 | 2026-11-30 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 82.5 | 41.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009751 | 2026-11-30 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009752 | 2026-11-30 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009753 | 2026-11-30 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009754 | 2026-11-30 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 13 | 67.5 | 877.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009755 | 2026-11-30 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 7.5 | 67.5 | 506.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009756 | 2026-11-30 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009757 | 2026-11-30 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009758 | 2026-11-30 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009759 | 2026-11-30 | E015 | Inès Petit | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009760 | 2026-11-30 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009761 | 2026-11-30 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009762 | 2026-11-30 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009763 | 2026-11-30 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009764 | 2026-11-30 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16.5 | 55 | 907.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009765 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009766 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009767 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P003 | Core Banking Modernisation | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009768 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009769 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009770 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009771 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009772 | 2026-11-30 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 26 | 65 | 1690 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009773 | 2026-11-30 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009774 | 2026-11-30 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 120 | 1380 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009775 | 2026-11-30 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3.5 | 120 | 420 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009776 | 2026-11-30 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 30 | 100 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009777 | 2026-11-30 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009778 | 2026-11-30 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 31.5 | 100 | 3150 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009779 | 2026-11-30 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009780 | 2026-11-30 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 26.5 | 75 | 1987.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009781 | 2026-11-30 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 75 | 1012.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009782 | 2026-11-30 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 29 | 67.5 | 1957.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009783 | 2026-11-30 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 67.5 | 573.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009784 | 2026-11-30 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2.5 | 67.5 | 168.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009785 | 2026-11-30 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 26 | 67.5 | 1755 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009786 | 2026-11-30 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 67.5 | 742.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009787 | 2026-11-30 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 3 | 67.5 | 202.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009788 | 2026-11-30 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 102.5 | 922.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009789 | 2026-11-30 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31 | 102.5 | 3177.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009790 | 2026-11-30 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 77.5 | 581.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009791 | 2026-11-30 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 77.5 | 2518.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009792 | 2026-11-30 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009793 | 2026-11-30 | E026 | Noah Durand | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 17 | 117.5 | 1997.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009794 | 2026-11-30 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 117.5 | 1762.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009795 | 2026-11-30 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 117.5 | 998.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009796 | 2026-11-30 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 82.5 | 1196.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009797 | 2026-11-30 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 82.5 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009798 | 2026-11-30 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 82.5 | 1443.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009799 | 2026-11-30 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18 | 95 | 1710 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009800 | 2026-11-30 | E028 | Arthur Mercier | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 95 | 807.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009801 | 2026-11-30 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 95 | 1282.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009802 | 2026-11-30 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 25.5 | 60 | 1530 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009803 | 2026-11-30 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 60 | 870 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009804 | 2026-11-30 | E030 | Rayan Fischer | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 90 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009805 | 2026-11-30 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009806 | 2026-11-30 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 90 | 1080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009807 | 2026-11-30 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009808 | 2026-11-30 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 62.5 | 531.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009809 | 2026-11-30 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 62.5 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009810 | 2026-11-30 | E032 | Maxime Richard | Applications | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 62.5 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009811 | 2026-11-30 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 62.5 | 718.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009812 | 2026-11-30 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 62.5 | 843.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009813 | 2026-11-30 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009814 | 2026-11-30 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009815 | 2026-11-30 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 13 | 105 | 1365 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009816 | 2026-11-30 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009817 | 2026-11-30 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009818 | 2026-11-30 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 72.5 | 326.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009819 | 2026-11-30 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 72.5 | 2283.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009820 | 2026-11-30 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32 | 65 | 2080 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009821 | 2026-11-30 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009822 | 2026-11-30 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009823 | 2026-11-30 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009824 | 2026-11-30 | E038 | Paul Lemoine | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 22 | 120 | 2640 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009825 | 2026-11-30 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 120 | 1500 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009826 | 2026-11-30 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 4 | 120 | 480 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009827 | 2026-11-30 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 120 | 180 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009828 | 2026-11-30 | E039 | Jade Santos | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 27.5 | 100 | 2750 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009829 | 2026-11-30 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 100 | 1100 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009830 | 2026-11-30 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1.5 | 100 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009831 | 2026-11-30 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009832 | 2026-11-30 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 90 | 1665 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009833 | 2026-11-30 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 90 | 450 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009834 | 2026-11-30 | E041 | Zoé Marques | Data & AI | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 67.5 | 1383.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009835 | 2026-11-30 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009836 | 2026-11-30 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009837 | 2026-11-30 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 75 | 1537.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009838 | 2026-11-30 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 75 | 1462.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009839 | 2026-11-30 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 23 | 75 | 1725 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009840 | 2026-11-30 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009841 | 2026-11-30 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 75 | 562.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009842 | 2026-11-30 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 2 | 75 | 150 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009843 | 2026-11-30 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 97.5 | 1950 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009844 | 2026-11-30 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009845 | 2026-11-30 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 97.5 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009846 | 2026-11-30 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 75 | 900 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009847 | 2026-11-30 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 3 | 75 | 225 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009848 | 2026-11-30 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009849 | 2026-11-30 | E045 | Louise Carvalho | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009850 | 2026-11-30 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009851 | 2026-11-30 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 67.5 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009852 | 2026-11-30 | E046 | Alexandre Blanc | Cloud & Platform | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009853 | 2026-11-30 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 115 | 920 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009854 | 2026-11-30 | E047 | Mia Nowak | Cybersecurity | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 3.5 | 115 | 402.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009855 | 2026-11-30 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4.5 | 115 | 517.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009856 | 2026-11-30 | E047 | Mia Nowak | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009857 | 2026-11-30 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 87.5 | 1662.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009858 | 2026-11-30 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009859 | 2026-11-30 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 87.5 | 1181.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009860 | 2026-11-30 | E049 | Nora Aydin | Consulting | P003 | Core Banking Modernisation | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 90 | 1710 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009861 | 2026-11-30 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 90 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009862 | 2026-11-30 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 90 | 1215 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009863 | 2026-11-30 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 60 | 720 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009864 | 2026-11-30 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 28 | 60 | 1680 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009865 | 2026-12-07 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009866 | 2026-12-07 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009867 | 2026-12-07 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009868 | 2026-12-07 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009869 | 2026-12-07 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009870 | 2026-12-07 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009871 | 2026-12-07 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 37 | 97.5 | 3607.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009872 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009873 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009874 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009875 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009876 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009877 | 2026-12-07 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009878 | 2026-12-07 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34 | 80 | 2720 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009879 | 2026-12-07 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009880 | 2026-12-07 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009881 | 2026-12-07 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009882 | 2026-12-07 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009883 | 2026-12-07 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009884 | 2026-12-07 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009885 | 2026-12-07 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 33.5 | 62.5 | 2093.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009886 | 2026-12-07 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 57.5 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009887 | 2026-12-07 | E004 | Thomas Weber | Finance | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009888 | 2026-12-07 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009889 | 2026-12-07 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009890 | 2026-12-07 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009891 | 2026-12-07 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009892 | 2026-12-07 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009893 | 2026-12-07 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009894 | 2026-12-07 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 35.5 | 55 | 1952.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009895 | 2026-12-07 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009896 | 2026-12-07 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009897 | 2026-12-07 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009898 | 2026-12-07 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 187.5 | 6937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009899 | 2026-12-07 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009900 | 2026-12-07 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009901 | 2026-12-07 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009902 | 2026-12-07 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009903 | 2026-12-07 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009904 | 2026-12-07 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009905 | 2026-12-07 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 21 | 157.5 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009906 | 2026-12-07 | E007 | Claire Muller | Executive | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009907 | 2026-12-07 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009908 | 2026-12-07 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009909 | 2026-12-07 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009910 | 2026-12-07 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009911 | 2026-12-07 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009912 | 2026-12-07 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009913 | 2026-12-07 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009914 | 2026-12-07 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 38.5 | 150 | 5775 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009915 | 2026-12-07 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009916 | 2026-12-07 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009917 | 2026-12-07 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009918 | 2026-12-07 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009919 | 2026-12-07 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009920 | 2026-12-07 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009921 | 2026-12-07 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 28 | 105 | 2940 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009922 | 2026-12-07 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19.5 | 85 | 1657.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009923 | 2026-12-07 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16 | 85 | 1360 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009924 | 2026-12-07 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4.5 | 85 | 382.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009925 | 2026-12-07 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 15.5 | 82.5 | 1278.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009926 | 2026-12-07 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 16.5 | 82.5 | 1361.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009927 | 2026-12-07 | E012 | Julien Bernard | Project Management | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009928 | 2026-12-07 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009929 | 2026-12-07 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009930 | 2026-12-07 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 11.5 | 67.5 | 776.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009931 | 2026-12-07 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8 | 67.5 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009932 | 2026-12-07 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 1.5 | 67.5 | 101.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009933 | 2026-12-07 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009934 | 2026-12-07 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009935 | 2026-12-07 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009936 | 2026-12-07 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009937 | 2026-12-07 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009938 | 2026-12-07 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009939 | 2026-12-07 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20.5 | 55 | 1127.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009940 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009941 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009942 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009943 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009944 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009945 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009946 | 2026-12-07 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 34 | 65 | 2210 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009947 | 2026-12-07 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 23.5 | 120 | 2820 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009948 | 2026-12-07 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009949 | 2026-12-07 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5.5 | 120 | 660 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009950 | 2026-12-07 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 30 | 100 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009951 | 2026-12-07 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 10 | 100 | 1000 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009952 | 2026-12-07 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 100 | 3050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009953 | 2026-12-07 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 100 | 850 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009954 | 2026-12-07 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 100 | 100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009955 | 2026-12-07 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 26 | 75 | 1950 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009956 | 2026-12-07 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14 | 75 | 1050 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009957 | 2026-12-07 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32.5 | 67.5 | 2193.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009958 | 2026-12-07 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009959 | 2026-12-07 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009960 | 2026-12-07 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 67.5 | 810 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009961 | 2026-12-07 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 102.5 | 871.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009962 | 2026-12-07 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 102.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009963 | 2026-12-07 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 77.5 | 581.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009964 | 2026-12-07 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32.5 | 77.5 | 2518.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009965 | 2026-12-07 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009966 | 2026-12-07 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 6.5 | 117.5 | 763.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009967 | 2026-12-07 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 3.5 | 117.5 | 411.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009968 | 2026-12-07 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6 | 117.5 | 705 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009969 | 2026-12-07 | E026 | Noah Durand | Cybersecurity | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009970 | 2026-12-07 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15.5 | 82.5 | 1278.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009971 | 2026-12-07 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 82.5 | 701.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009972 | 2026-12-07 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16 | 82.5 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009973 | 2026-12-07 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 95 | 1852.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009974 | 2026-12-07 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20.5 | 95 | 1947.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009975 | 2026-12-07 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 9.5 | 60 | 570 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009976 | 2026-12-07 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 6.5 | 60 | 390 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009977 | 2026-12-07 | E029 | Chloé Diallo | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009978 | 2026-12-07 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009979 | 2026-12-07 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 90 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009980 | 2026-12-07 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 62.5 | 1156.25 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009981 | 2026-12-07 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 62.5 | 531.25 | Rejected | Maya Fernandes | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009982 | 2026-12-07 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 5 | 62.5 | 312.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009983 | 2026-12-07 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 62.5 | 562.5 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009984 | 2026-12-07 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 23 | 62.5 | 1437.5 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009985 | 2026-12-07 | E032 | Maxime Richard | Applications | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009986 | 2026-12-07 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009987 | 2026-12-07 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 1.5 | 105 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009988 | 2026-12-07 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 13 | 105 | 1365 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009989 | 2026-12-07 | E033 | Aya Bauer | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 24 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009990 | 2026-12-07 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 72.5 | 181.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009991 | 2026-12-07 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 2.5 | 72.5 | 181.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009992 | 2026-12-07 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 19 | 72.5 | 1377.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009993 | 2026-12-07 | E034 | Victor Renard | Sales | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009994 | 2026-12-07 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009995 | 2026-12-07 | E035 | Alice Meier | HR | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009996 | 2026-12-07 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009997 | 2026-12-07 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009998 | 2026-12-07 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 120 | 1440 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-009999 | 2026-12-07 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 3.5 | 120 | 420 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010000 | 2026-12-07 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24.5 | 120 | 2940 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010001 | 2026-12-07 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 100 | 750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010002 | 2026-12-07 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 16.5 | 100 | 1650 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010003 | 2026-12-07 | E039 | Jade Santos | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010004 | 2026-12-07 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 90 | 1755 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010005 | 2026-12-07 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 90 | 1845 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010006 | 2026-12-07 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 10.5 | 67.5 | 708.75 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010007 | 2026-12-07 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 67.5 | 472.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010008 | 2026-12-07 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 14.5 | 67.5 | 978.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010009 | 2026-12-07 | E041 | Zoé Marques | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 8 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010010 | 2026-12-07 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 12.5 | 75 | 937.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010011 | 2026-12-07 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 75 | 862.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010012 | 2026-12-07 | E042 | Samuel Jung | Data & AI | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010013 | 2026-12-07 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 21.5 | 75 | 1612.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010014 | 2026-12-07 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 9 | 75 | 675 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010015 | 2026-12-07 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010016 | 2026-12-07 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 1 | 75 | 75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010017 | 2026-12-07 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 97.5 | 1901.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010018 | 2026-12-07 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 97.5 | 828.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010019 | 2026-12-07 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 97.5 | 1170 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010020 | 2026-12-07 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 31.5 | 75 | 2362.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010021 | 2026-12-07 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 75 | 600 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010022 | 2026-12-07 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 75 | 37.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010023 | 2026-12-07 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 67.5 | 1282.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010024 | 2026-12-07 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 67.5 | 1417.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010025 | 2026-12-07 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 115 | 2185 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010026 | 2026-12-07 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21 | 115 | 2415 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010027 | 2026-12-07 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 87.5 | 1618.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010028 | 2026-12-07 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 87.5 | 700 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010029 | 2026-12-07 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 87.5 | 1181.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010030 | 2026-12-07 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 5 | 90 | 450 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010031 | 2026-12-07 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 19 | 90 | 1710 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010032 | 2026-12-07 | E049 | Nora Aydin | Consulting | INT-LEAVE | Annual Leave | ABSENCE | Approved annual leave | No | 16 | 0 | 0 | Approved | Alice Meier | Approved absence. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010033 | 2026-12-07 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 60 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010034 | 2026-12-07 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27 | 60 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010035 | 2026-12-14 | E001 | Sophie Lambert | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010036 | 2026-12-14 | E001 | Sophie Lambert | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010037 | 2026-12-14 | E001 | Sophie Lambert | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010038 | 2026-12-14 | E001 | Sophie Lambert | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010039 | 2026-12-14 | E001 | Sophie Lambert | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010040 | 2026-12-14 | E001 | Sophie Lambert | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 0.5 | 97.5 | 48.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010041 | 2026-12-14 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 37 | 97.5 | 3607.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010042 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010043 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010044 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 80 | 40 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010045 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010046 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010047 | 2026-12-14 | E002 | Marc Hoffmann | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 80 | 80 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010048 | 2026-12-14 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 80 | 2760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010049 | 2026-12-14 | E003 | Elena Rossi | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010050 | 2026-12-14 | E003 | Elena Rossi | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010051 | 2026-12-14 | E003 | Elena Rossi | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010052 | 2026-12-14 | E003 | Elena Rossi | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1.5 | 62.5 | 93.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010053 | 2026-12-14 | E003 | Elena Rossi | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010054 | 2026-12-14 | E003 | Elena Rossi | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 62.5 | 62.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010055 | 2026-12-14 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 32.5 | 62.5 | 2031.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010056 | 2026-12-14 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 57.5 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010057 | 2026-12-14 | E005 | Nadia Benali | Finance | P001 | LuxHealth Data Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010058 | 2026-12-14 | E005 | Nadia Benali | Finance | P002 | Sovereign AI Factory | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010059 | 2026-12-14 | E005 | Nadia Benali | Finance | P004 | Smart Mobility Analytics | WP07 | Project financial control and cost validation | No | 0.5 | 55 | 27.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010060 | 2026-12-14 | E005 | Nadia Benali | Finance | P007 | Cyber Resilience Programme | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010061 | 2026-12-14 | E005 | Nadia Benali | Finance | P008 | Customer 360 Platform | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010062 | 2026-12-14 | E005 | Nadia Benali | Finance | P010 | GenAI Knowledge Assistant | WP07 | Project financial control and cost validation | No | 1 | 55 | 55 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010063 | 2026-12-14 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 34.5 | 55 | 1897.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010064 | 2026-12-14 | E006 | Jean Schmit | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010065 | 2026-12-14 | E006 | Jean Schmit | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010066 | 2026-12-14 | E006 | Jean Schmit | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 1 | 187.5 | 187.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010067 | 2026-12-14 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 37 | 187.5 | 6937.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010068 | 2026-12-14 | E007 | Claire Muller | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010069 | 2026-12-14 | E007 | Claire Muller | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010070 | 2026-12-14 | E007 | Claire Muller | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010071 | 2026-12-14 | E007 | Claire Muller | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 0.5 | 157.5 | 78.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010072 | 2026-12-14 | E007 | Claire Muller | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010073 | 2026-12-14 | E007 | Claire Muller | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 1 | 157.5 | 157.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010074 | 2026-12-14 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 34.5 | 157.5 | 5433.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010075 | 2026-12-14 | E008 | Luca Conti | Executive | P001 | LuxHealth Data Platform | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010076 | 2026-12-14 | E008 | Luca Conti | Executive | P002 | Sovereign AI Factory | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010077 | 2026-12-14 | E008 | Luca Conti | Executive | P004 | Smart Mobility Analytics | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010078 | 2026-12-14 | E008 | Luca Conti | Executive | P007 | Cyber Resilience Programme | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010079 | 2026-12-14 | E008 | Luca Conti | Executive | P010 | GenAI Knowledge Assistant | WP07 | Steering committee and executive decision support | No | 2 | 162.5 | 325 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010080 | 2026-12-14 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 30 | 162.5 | 4875 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010081 | 2026-12-14 | E009 | Amélie Dubois | Executive | P008 | Customer 360 Platform | WP07 | Steering committee and executive decision support | No | 1.5 | 150 | 225 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010082 | 2026-12-14 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 38.5 | 150 | 5775 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010083 | 2026-12-14 | E010 | David Martin | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010084 | 2026-12-14 | E010 | David Martin | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010085 | 2026-12-14 | E010 | David Martin | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010086 | 2026-12-14 | E010 | David Martin | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010087 | 2026-12-14 | E010 | David Martin | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010088 | 2026-12-14 | E010 | David Martin | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 105 | 210 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010089 | 2026-12-14 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 28 | 105 | 2940 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010090 | 2026-12-14 | E011 | Maya Fernandes | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | Yes | 19 | 85 | 1615 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010091 | 2026-12-14 | E011 | Maya Fernandes | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | Yes | 16.5 | 85 | 1402.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010092 | 2026-12-14 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 4.5 | 85 | 382.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010093 | 2026-12-14 | E012 | Julien Bernard | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | Yes | 17 | 82.5 | 1402.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010094 | 2026-12-14 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 23 | 82.5 | 1897.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010095 | 2026-12-14 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010096 | 2026-12-14 | E014 | Nicolas Wagner | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | Yes | 19.5 | 67.5 | 1316.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010097 | 2026-12-14 | E014 | Nicolas Wagner | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | Yes | 12 | 67.5 | 810 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010098 | 2026-12-14 | E014 | Nicolas Wagner | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | Yes | 8.5 | 67.5 | 573.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010099 | 2026-12-14 | E015 | Inès Petit | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010100 | 2026-12-14 | E015 | Inès Petit | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010101 | 2026-12-14 | E015 | Inès Petit | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010102 | 2026-12-14 | E015 | Inès Petit | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010103 | 2026-12-14 | E015 | Inès Petit | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 3 | 55 | 165 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010104 | 2026-12-14 | E015 | Inès Petit | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 3.5 | 55 | 192.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010105 | 2026-12-14 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 20 | 55 | 1100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010106 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P001 | LuxHealth Data Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010107 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P002 | Sovereign AI Factory | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010108 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P004 | Smart Mobility Analytics | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010109 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P007 | Cyber Resilience Programme | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010110 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P008 | Customer 360 Platform | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010111 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | P010 | GenAI Knowledge Assistant | WP07 | Project management, status, planning and governance | No | 2 | 65 | 130 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010112 | 2026-12-14 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 28 | 65 | 1820 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010113 | 2026-12-14 | E017 | Amina Amar | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 25 | 120 | 3000 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010114 | 2026-12-14 | E017 | Amina Amar | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 11 | 120 | 1320 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010115 | 2026-12-14 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 4 | 120 | 480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010116 | 2026-12-14 | E018 | Gabriel Simon | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 100 | 3050 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010117 | 2026-12-14 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 100 | 950 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010118 | 2026-12-14 | E019 | Eva Moreau | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 100 | 3200 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010119 | 2026-12-14 | E019 | Eva Moreau | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 100 | 800 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010120 | 2026-12-14 | E020 | Antoine Robert | Data & AI | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 30.5 | 75 | 2287.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010121 | 2026-12-14 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 9.5 | 75 | 712.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010122 | 2026-12-14 | E021 | Lea Nguyen | Data & AI | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 32 | 67.5 | 2160 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010123 | 2026-12-14 | E021 | Lea Nguyen | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 67.5 | 540 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010124 | 2026-12-14 | E022 | Hugo Laurent | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 28 | 67.5 | 1890 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010125 | 2026-12-14 | E022 | Hugo Laurent | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010126 | 2026-12-14 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 0.5 | 67.5 | 33.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010127 | 2026-12-14 | E023 | Mila Costa | Cloud & Platform | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 102.5 | 871.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010128 | 2026-12-14 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 31.5 | 102.5 | 3228.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010129 | 2026-12-14 | E024 | Louis Fontaine | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 77.5 | 620 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010130 | 2026-12-14 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 77.5 | 2480 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010131 | 2026-12-14 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010132 | 2026-12-14 | E026 | Noah Durand | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 15 | 117.5 | 1762.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010133 | 2026-12-14 | E026 | Noah Durand | Cybersecurity | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 117.5 | 822.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010134 | 2026-12-14 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 117.5 | 2115 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010135 | 2026-12-14 | E027 | Emma Lopez | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 14.5 | 82.5 | 1196.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010136 | 2026-12-14 | E027 | Emma Lopez | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 82.5 | 660 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010137 | 2026-12-14 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 17.5 | 82.5 | 1443.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010138 | 2026-12-14 | E028 | Arthur Mercier | Consulting | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 18.5 | 95 | 1757.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010139 | 2026-12-14 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 21.5 | 95 | 2042.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010140 | 2026-12-14 | E029 | Chloé Diallo | Consulting | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 26.5 | 60 | 1590 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010141 | 2026-12-14 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 13.5 | 60 | 810 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010142 | 2026-12-14 | E030 | Rayan Fischer | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010143 | 2026-12-14 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 90 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010144 | 2026-12-14 | E031 | Lucie Pereira | Applications | P001 | LuxHealth Data Platform | WP06 | Deployment, transition, documentation and closure | Yes | 19.5 | 62.5 | 1218.75 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010145 | 2026-12-14 | E031 | Lucie Pereira | Applications | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 62.5 | 531.25 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010146 | 2026-12-14 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12 | 62.5 | 750 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010147 | 2026-12-14 | E032 | Maxime Richard | Applications | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 13 | 62.5 | 812.5 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010148 | 2026-12-14 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 27 | 62.5 | 1687.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010149 | 2026-12-14 | E033 | Aya Bauer | Sales | P002 | Sovereign AI Factory | WP07 | Commercial coordination and client relationship support | Yes | 4.5 | 105 | 472.5 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010150 | 2026-12-14 | E033 | Aya Bauer | Sales | P010 | GenAI Knowledge Assistant | WP07 | Commercial coordination and client relationship support | Yes | 4 | 105 | 420 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010151 | 2026-12-14 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 31.5 | 105 | 3307.5 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010152 | 2026-12-14 | E034 | Victor Renard | Sales | P001 | LuxHealth Data Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010153 | 2026-12-14 | E034 | Victor Renard | Sales | P008 | Customer 360 Platform | WP07 | Commercial coordination and client relationship support | Yes | 4 | 72.5 | 290 | Approved | Maya Fernandes | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010154 | 2026-12-14 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 32 | 72.5 | 2320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010155 | 2026-12-14 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 65 | 2600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010156 | 2026-12-14 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 55 | 2200 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010157 | 2026-12-14 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 40 | 67.5 | 2700 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010158 | 2026-12-14 | E038 | Paul Lemoine | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 120 | 1380 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010159 | 2026-12-14 | E038 | Paul Lemoine | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 4.5 | 120 | 540 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010160 | 2026-12-14 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 120 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010161 | 2026-12-14 | E039 | Jade Santos | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 12 | 100 | 1200 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010162 | 2026-12-14 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 28 | 100 | 2800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010163 | 2026-12-14 | E040 | Adam Klein | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 90 | 1800 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010164 | 2026-12-14 | E040 | Adam Klein | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 90 | 1800 | Pending | Nicolas Wagner | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010165 | 2026-12-14 | E041 | Zoé Marques | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 67.5 | 776.25 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010166 | 2026-12-14 | E041 | Zoé Marques | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 67.5 | 506.25 | Rejected | Julien Bernard | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010167 | 2026-12-14 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 15 | 67.5 | 1012.5 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010168 | 2026-12-14 | E042 | Samuel Jung | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 21 | 75 | 1575 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010169 | 2026-12-14 | E042 | Samuel Jung | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 19 | 75 | 1425 | Pending | Julien Bernard | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010170 | 2026-12-14 | E043 | Manon Franco | Data & AI | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 24 | 75 | 1800 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010171 | 2026-12-14 | E043 | Manon Franco | Data & AI | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 8.5 | 75 | 637.5 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010172 | 2026-12-14 | E043 | Manon Franco | Data & AI | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 75 | 600 | Approved | Julien Bernard | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010173 | 2026-12-14 | E044 | Yanis Vidal | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20.5 | 97.5 | 1998.75 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010174 | 2026-12-14 | E044 | Yanis Vidal | Cloud & Platform | P004 | Smart Mobility Analytics | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 97.5 | 780 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010175 | 2026-12-14 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 11.5 | 97.5 | 1121.25 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010176 | 2026-12-14 | E045 | Louise Carvalho | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 33 | 75 | 2475 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010177 | 2026-12-14 | E045 | Louise Carvalho | Cloud & Platform | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7 | 75 | 525 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010178 | 2026-12-14 | E046 | Alexandre Blanc | Cloud & Platform | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 21.5 | 67.5 | 1451.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010179 | 2026-12-14 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18.5 | 67.5 | 1248.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010180 | 2026-12-14 | E047 | Mia Nowak | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 115 | 2300 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010181 | 2026-12-14 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 20 | 115 | 2300 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010182 | 2026-12-14 | E048 | Raphaël Meyer | Cybersecurity | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 20 | 87.5 | 1750 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010183 | 2026-12-14 | E048 | Raphaël Meyer | Cybersecurity | P002 | Sovereign AI Factory | WP06 | Deployment, transition, documentation and closure | Yes | 7.5 | 87.5 | 656.25 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010184 | 2026-12-14 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 12.5 | 87.5 | 1093.75 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010185 | 2026-12-14 | E049 | Nora Aydin | Consulting | P007 | Cyber Resilience Programme | WP06 | Deployment, transition, documentation and closure | Yes | 8 | 90 | 720 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010186 | 2026-12-14 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 32 | 90 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010187 | 2026-12-14 | E050 | Mathis Girard | Consulting | P008 | Customer 360 Platform | WP06 | Deployment, transition, documentation and closure | Yes | 11.5 | 60 | 690 | Approved | Nicolas Wagner | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010188 | 2026-12-14 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 28.5 | 60 | 1710 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010189 | 2026-12-21 | E001 | Sophie Lambert | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 97.5 | 2340 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010190 | 2026-12-21 | E001 | Sophie Lambert | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010191 | 2026-12-21 | E002 | Marc Hoffmann | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 80 | 1920 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010192 | 2026-12-21 | E002 | Marc Hoffmann | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010193 | 2026-12-21 | E003 | Elena Rossi | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 62.5 | 1500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010194 | 2026-12-21 | E003 | Elena Rossi | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010195 | 2026-12-21 | E004 | Thomas Weber | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 57.5 | 1380 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010196 | 2026-12-21 | E004 | Thomas Weber | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010197 | 2026-12-21 | E005 | Nadia Benali | Finance | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010198 | 2026-12-21 | E005 | Nadia Benali | Finance | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010199 | 2026-12-21 | E006 | Jean Schmit | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24 | 187.5 | 4500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010200 | 2026-12-21 | E006 | Jean Schmit | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010201 | 2026-12-21 | E007 | Claire Muller | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24 | 157.5 | 3780 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010202 | 2026-12-21 | E007 | Claire Muller | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010203 | 2026-12-21 | E008 | Luca Conti | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24 | 162.5 | 3900 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010204 | 2026-12-21 | E008 | Luca Conti | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010205 | 2026-12-21 | E009 | Amélie Dubois | Executive | INT-MGMT | Company management and executive governance | INTERNAL | Company management and executive governance | No | 24 | 150 | 3600 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010206 | 2026-12-21 | E009 | Amélie Dubois | Executive | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010207 | 2026-12-21 | E010 | David Martin | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010208 | 2026-12-21 | E010 | David Martin | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010209 | 2026-12-21 | E011 | Maya Fernandes | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 85 | 2040 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010210 | 2026-12-21 | E011 | Maya Fernandes | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010211 | 2026-12-21 | E012 | Julien Bernard | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 82.5 | 1980 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010212 | 2026-12-21 | E012 | Julien Bernard | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010213 | 2026-12-21 | E013 | Sara Khan | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010214 | 2026-12-21 | E013 | Sara Khan | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010215 | 2026-12-21 | E014 | Nicolas Wagner | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 18 | 67.5 | 1215 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010216 | 2026-12-21 | E014 | Nicolas Wagner | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010217 | 2026-12-21 | E015 | Inès Petit | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 55 | 1320 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010218 | 2026-12-21 | E015 | Inès Petit | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010219 | 2026-12-21 | E016 | Olivier Lefevre | Project Management | INT-PMO | Portfolio management, resource planning and PMO improvement | INTERNAL | Portfolio management, resource planning and PMO improvement | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010220 | 2026-12-21 | E016 | Olivier Lefevre | Project Management | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010221 | 2026-12-21 | E017 | Amina Amar | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 120 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010222 | 2026-12-21 | E017 | Amina Amar | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010223 | 2026-12-21 | E018 | Gabriel Simon | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 100 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010224 | 2026-12-21 | E018 | Gabriel Simon | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010225 | 2026-12-21 | E019 | Eva Moreau | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 100 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010226 | 2026-12-21 | E019 | Eva Moreau | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010227 | 2026-12-21 | E020 | Antoine Robert | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 75 | 1800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010228 | 2026-12-21 | E020 | Antoine Robert | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010229 | 2026-12-21 | E021 | Lea Nguyen | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010230 | 2026-12-21 | E021 | Lea Nguyen | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010231 | 2026-12-21 | E022 | Hugo Laurent | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010232 | 2026-12-21 | E022 | Hugo Laurent | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010233 | 2026-12-21 | E023 | Mila Costa | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 102.5 | 2460 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010234 | 2026-12-21 | E023 | Mila Costa | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010235 | 2026-12-21 | E024 | Louis Fontaine | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 77.5 | 1860 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010236 | 2026-12-21 | E024 | Louis Fontaine | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010237 | 2026-12-21 | E025 | Camille Garcia | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010238 | 2026-12-21 | E025 | Camille Garcia | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010239 | 2026-12-21 | E026 | Noah Durand | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 117.5 | 2820 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010240 | 2026-12-21 | E026 | Noah Durand | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010241 | 2026-12-21 | E027 | Emma Lopez | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 82.5 | 1980 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010242 | 2026-12-21 | E027 | Emma Lopez | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010243 | 2026-12-21 | E028 | Arthur Mercier | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 95 | 2280 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010244 | 2026-12-21 | E028 | Arthur Mercier | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010245 | 2026-12-21 | E029 | Chloé Diallo | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 60 | 1440 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010246 | 2026-12-21 | E029 | Chloé Diallo | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010247 | 2026-12-21 | E030 | Rayan Fischer | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 90 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010248 | 2026-12-21 | E030 | Rayan Fischer | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010249 | 2026-12-21 | E031 | Lucie Pereira | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 18 | 62.5 | 1125 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010250 | 2026-12-21 | E031 | Lucie Pereira | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010251 | 2026-12-21 | E032 | Maxime Richard | Applications | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 62.5 | 1500 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010252 | 2026-12-21 | E032 | Maxime Richard | Applications | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010253 | 2026-12-21 | E033 | Aya Bauer | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 24 | 105 | 2520 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010254 | 2026-12-21 | E033 | Aya Bauer | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010255 | 2026-12-21 | E034 | Victor Renard | Sales | INT-SALES | Business development, proposals and account planning | INTERNAL | Business development, proposals and account planning | No | 24 | 72.5 | 1740 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010256 | 2026-12-21 | E034 | Victor Renard | Sales | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010257 | 2026-12-21 | E035 | Alice Meier | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 65 | 1560 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010258 | 2026-12-21 | E035 | Alice Meier | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010259 | 2026-12-21 | E036 | Nathan Cohen | HR | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 18 | 55 | 990 | Rejected | David Martin | Returned for missing hours or incomplete activity description. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010260 | 2026-12-21 | E036 | Nathan Cohen | HR | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010261 | 2026-12-21 | E037 | Lina Gomes | Operations | INT-CORP | Corporate operations and internal services | INTERNAL | Corporate operations and internal services | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010262 | 2026-12-21 | E037 | Lina Gomes | Operations | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010263 | 2026-12-21 | E038 | Paul Lemoine | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 120 | 2880 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010264 | 2026-12-21 | E038 | Paul Lemoine | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010265 | 2026-12-21 | E039 | Jade Santos | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 100 | 2400 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010266 | 2026-12-21 | E039 | Jade Santos | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010267 | 2026-12-21 | E040 | Adam Klein | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 90 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010268 | 2026-12-21 | E040 | Adam Klein | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010269 | 2026-12-21 | E041 | Zoé Marques | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010270 | 2026-12-21 | E041 | Zoé Marques | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010271 | 2026-12-21 | E042 | Samuel Jung | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 75 | 1800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010272 | 2026-12-21 | E042 | Samuel Jung | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010273 | 2026-12-21 | E043 | Manon Franco | Data & AI | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 75 | 1800 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010274 | 2026-12-21 | E043 | Manon Franco | Data & AI | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010275 | 2026-12-21 | E044 | Yanis Vidal | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 97.5 | 2340 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010276 | 2026-12-21 | E044 | Yanis Vidal | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010277 | 2026-12-21 | E045 | Louise Carvalho | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 75 | 1800 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010278 | 2026-12-21 | E045 | Louise Carvalho | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010279 | 2026-12-21 | E046 | Alexandre Blanc | Cloud & Platform | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 67.5 | 1620 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010280 | 2026-12-21 | E046 | Alexandre Blanc | Cloud & Platform | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010281 | 2026-12-21 | E047 | Mia Nowak | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 115 | 2760 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010282 | 2026-12-21 | E047 | Mia Nowak | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010283 | 2026-12-21 | E048 | Raphaël Meyer | Cybersecurity | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 87.5 | 2100 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010284 | 2026-12-21 | E048 | Raphaël Meyer | Cybersecurity | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010285 | 2026-12-21 | E049 | Nora Aydin | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 90 | 2160 | Approved | David Martin | Approved as submitted. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010286 | 2026-12-21 | E049 | Nora Aydin | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010287 | 2026-12-21 | E050 | Mathis Girard | Consulting | INT-ADMIN | Internal administration, community work and non-client activities | INTERNAL | Internal administration, community work and non-client activities | No | 24 | 60 | 1440 | Pending | David Martin | Awaiting project manager validation. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
TS-010288 | 2026-12-21 | E050 | Mathis Girard | Consulting | INT-HOLIDAY | Public Holiday | ABSENCE | Luxembourg public holiday | No | 16 | 0 | 0 | Approved | Alice Meier | System calendar entry. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE

## Approvals
approval_period | employee_id | employee_name | department | expected_hours | submitted_hours | client_project_hours | billable_hours | internal_hours | leave_hours | public_holiday_hours | submission_date | approval_status | approval_date | approver_name | rejected_line_count | pending_line_count | classification | synthetic_record
2026-01 | E001 | Sophie Lambert | Finance | 160 | 160 | 9.5 | 0 | 142.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E001 | Sophie Lambert | Finance | 160 | 160 | 8 | 0 | 112 | 40 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E001 | Sophie Lambert | Finance | 200 | 200 | 17 | 0 | 167 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E001 | Sophie Lambert | Finance | 160 | 160 | 18 | 0 | 134 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E001 | Sophie Lambert | Finance | 160 | 158 | 10.5 | 0 | 99.5 | 32 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 1 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E001 | Sophie Lambert | Finance | 200 | 200 | 25 | 0 | 167 | 0 | 8 | 2026-07-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 11 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E001 | Sophie Lambert | Finance | 160 | 160 | 15 | 0 | 121 | 24 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E001 | Sophie Lambert | Finance | 200 | 200 | 25 | 0 | 159 | 8 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E001 | Sophie Lambert | Finance | 160 | 160 | 18 | 0 | 142 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E001 | Sophie Lambert | Finance | 160 | 160 | 16 | 0 | 144 | 0 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E001 | Sophie Lambert | Finance | 200 | 200 | 17.5 | 0 | 174.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E001 | Sophie Lambert | Finance | 120 | 120 | 6 | 0 | 98 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E002 | Marc Hoffmann | Finance | 160 | 160 | 16 | 0 | 136 | 0 | 8 | 2026-02-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 6 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E002 | Marc Hoffmann | Finance | 160 | 160 | 25.5 | 0 | 134.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E002 | Marc Hoffmann | Finance | 200 | 200 | 38.5 | 0 | 161.5 | 0 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 9 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E002 | Marc Hoffmann | Finance | 160 | 160 | 29.5 | 0 | 122.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E002 | Marc Hoffmann | Finance | 160 | 160 | 23.5 | 0 | 104.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E002 | Marc Hoffmann | Finance | 200 | 200 | 41.5 | 0 | 134.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E002 | Marc Hoffmann | Finance | 160 | 148 | 24.5 | 0 | 75.5 | 48 | 0 | 2026-08-02 | Rejected |  | Relevant Project Manager / Line Manager | 11 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E002 | Marc Hoffmann | Finance | 200 | 200 | 41.5 | 0 | 150.5 | 0 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E002 | Marc Hoffmann | Finance | 160 | 160 | 30 | 0 | 106 | 24 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E002 | Marc Hoffmann | Finance | 160 | 160 | 24.5 | 0 | 119.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E002 | Marc Hoffmann | Finance | 200 | 200 | 29.5 | 0 | 162.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E002 | Marc Hoffmann | Finance | 120 | 120 | 11.5 | 0 | 92.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E003 | Elena Rossi | Finance | 160 | 160 | 21 | 0 | 131 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E003 | Elena Rossi | Finance | 160 | 160 | 30 | 0 | 114 | 16 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E003 | Elena Rossi | Finance | 200 | 192 | 39 | 0 | 129 | 24 | 0 | 2026-04-02 | Rejected |  | Relevant Project Manager / Line Manager | 9 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E003 | Elena Rossi | Finance | 160 | 160 | 38 | 0 | 106 | 8 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E003 | Elena Rossi | Finance | 160 | 160 | 36.5 | 0 | 83.5 | 24 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E003 | Elena Rossi | Finance | 200 | 200 | 49.5 | 0 | 126.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E003 | Elena Rossi | Finance | 160 | 160 | 45.5 | 0 | 114.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E003 | Elena Rossi | Finance | 200 | 200 | 51 | 0 | 125 | 16 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E003 | Elena Rossi | Finance | 160 | 160 | 40.5 | 0 | 119.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E003 | Elena Rossi | Finance | 160 | 160 | 33 | 0 | 111 | 16 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E003 | Elena Rossi | Finance | 200 | 200 | 39 | 0 | 153 | 0 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 8 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E003 | Elena Rossi | Finance | 120 | 120 | 14 | 0 | 90 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E004 | Thomas Weber | Finance | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 144 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E004 | Thomas Weber | Finance | 200 | 200 | 0 | 0 | 152 | 40 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E004 | Thomas Weber | Finance | 200 | 200 | 0 | 0 | 176 | 16 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 152 | 8 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E004 | Thomas Weber | Finance | 160 | 160 | 0 | 0 | 136 | 24 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E004 | Thomas Weber | Finance | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-12-02 | Approved | 2026-12-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E004 | Thomas Weber | Finance | 120 | 120 | 0 | 0 | 88 | 16 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E005 | Nadia Benali | Finance | 160 | 160 | 16.5 | 0 | 135.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E005 | Nadia Benali | Finance | 160 | 160 | 25.5 | 0 | 134.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E005 | Nadia Benali | Finance | 200 | 200 | 32 | 0 | 144 | 24 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E005 | Nadia Benali | Finance | 160 | 160 | 26.5 | 0 | 109.5 | 16 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E005 | Nadia Benali | Finance | 160 | 160 | 27.5 | 0 | 116.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E005 | Nadia Benali | Finance | 200 | 200 | 40.5 | 0 | 135.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E005 | Nadia Benali | Finance | 160 | 160 | 31.5 | 0 | 104.5 | 24 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E005 | Nadia Benali | Finance | 200 | 200 | 40 | 0 | 152 | 0 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E005 | Nadia Benali | Finance | 160 | 154 | 33.5 | 0 | 120.5 | 0 | 0 | 2026-10-02 | Rejected |  | Relevant Project Manager / Line Manager | 10 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E005 | Nadia Benali | Finance | 160 | 152 | 27 | 0 | 109 | 16 | 0 | 2026-11-02 | Rejected |  | Relevant Project Manager / Line Manager | 9 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E005 | Nadia Benali | Finance | 200 | 200 | 25 | 0 | 143 | 24 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E005 | Nadia Benali | Finance | 120 | 120 | 10 | 0 | 94 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E006 | Jean Schmit | Executive | 160 | 156 | 9.5 | 0 | 122.5 | 16 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E006 | Jean Schmit | Executive | 160 | 160 | 16 | 0 | 144 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E006 | Jean Schmit | Executive | 200 | 200 | 20 | 0 | 180 | 0 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E006 | Jean Schmit | Executive | 160 | 160 | 14 | 0 | 122 | 16 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E006 | Jean Schmit | Executive | 160 | 160 | 12.5 | 0 | 107.5 | 24 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E006 | Jean Schmit | Executive | 200 | 200 | 18 | 0 | 158 | 16 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E006 | Jean Schmit | Executive | 160 | 160 | 16 | 0 | 144 | 0 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E006 | Jean Schmit | Executive | 200 | 200 | 20 | 0 | 172 | 0 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E006 | Jean Schmit | Executive | 160 | 160 | 16 | 0 | 144 | 0 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E006 | Jean Schmit | Executive | 160 | 158 | 14 | 0 | 120 | 24 | 0 | 2026-11-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E006 | Jean Schmit | Executive | 200 | 200 | 17 | 0 | 151 | 24 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 5 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E006 | Jean Schmit | Executive | 120 | 120 | 6 | 0 | 98 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E007 | Claire Muller | Executive | 160 | 160 | 16.5 | 0 | 135.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E007 | Claire Muller | Executive | 160 | 160 | 25.5 | 0 | 134.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E007 | Claire Muller | Executive | 200 | 200 | 31.5 | 0 | 144.5 | 24 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E007 | Claire Muller | Executive | 160 | 160 | 24.5 | 0 | 103.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E007 | Claire Muller | Executive | 160 | 160 | 28.5 | 0 | 115.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E007 | Claire Muller | Executive | 200 | 200 | 35.5 | 0 | 140.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E007 | Claire Muller | Executive | 160 | 160 | 32 | 0 | 120 | 8 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E007 | Claire Muller | Executive | 200 | 200 | 37.5 | 0 | 138.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E007 | Claire Muller | Executive | 160 | 160 | 30.5 | 0 | 129.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E007 | Claire Muller | Executive | 160 | 160 | 26.5 | 0 | 133.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E007 | Claire Muller | Executive | 200 | 200 | 26.5 | 0 | 149.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E007 | Claire Muller | Executive | 120 | 120 | 8.5 | 0 | 79.5 | 16 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E008 | Luca Conti | Executive | 160 | 160 | 13.5 | 0 | 138.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E008 | Luca Conti | Executive | 160 | 160 | 24 | 0 | 136 | 0 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E008 | Luca Conti | Executive | 200 | 200 | 32.5 | 0 | 127.5 | 40 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E008 | Luca Conti | Executive | 160 | 160 | 23 | 0 | 89 | 40 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E008 | Luca Conti | Executive | 160 | 160 | 35 | 0 | 109 | 0 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 6 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E008 | Luca Conti | Executive | 200 | 200 | 47.5 | 0 | 144.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E008 | Luca Conti | Executive | 160 | 160 | 40 | 0 | 120 | 0 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E008 | Luca Conti | Executive | 200 | 200 | 39 | 0 | 113 | 40 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E008 | Luca Conti | Executive | 160 | 160 | 40 | 0 | 120 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E008 | Luca Conti | Executive | 160 | 160 | 40 | 0 | 120 | 0 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E008 | Luca Conti | Executive | 200 | 200 | 48 | 0 | 144 | 0 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E008 | Luca Conti | Executive | 120 | 120 | 20 | 0 | 84 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E009 | Amélie Dubois | Executive | 160 | 160 | 18 | 0 | 134 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E009 | Amélie Dubois | Executive | 160 | 158 | 24 | 0 | 134 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E009 | Amélie Dubois | Executive | 200 | 196 | 28 | 0 | 152 | 16 | 0 | 2026-04-02 | Approved | 2026-04-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E009 | Amélie Dubois | Executive | 160 | 160 | 25 | 0 | 103 | 24 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E009 | Amélie Dubois | Executive | 160 | 160 | 20 | 0 | 84 | 40 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E009 | Amélie Dubois | Executive | 200 | 200 | 36.5 | 0 | 155.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E009 | Amélie Dubois | Executive | 160 | 160 | 30.5 | 0 | 129.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E009 | Amélie Dubois | Executive | 200 | 200 | 33 | 0 | 143 | 16 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E009 | Amélie Dubois | Executive | 160 | 160 | 24.5 | 0 | 135.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E009 | Amélie Dubois | Executive | 160 | 160 | 17 | 0 | 127 | 16 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E009 | Amélie Dubois | Executive | 200 | 200 | 14.5 | 0 | 169.5 | 8 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E009 | Amélie Dubois | Executive | 120 | 120 | 3 | 0 | 101 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E010 | David Martin | Project Management | 160 | 160 | 36 | 0 | 116 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E010 | David Martin | Project Management | 160 | 160 | 50.5 | 0 | 93.5 | 16 | 0 | 2026-03-02 | Approved | 2026-03-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E010 | David Martin | Project Management | 200 | 200 | 80 | 0 | 120 | 0 | 0 | 2026-04-02 | Approved | 2026-04-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E010 | David Martin | Project Management | 160 | 160 | 55.5 | 0 | 72.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E010 | David Martin | Project Management | 160 | 160 | 70 | 0 | 74 | 0 | 16 | 2026-06-02 | Approved | 2026-06-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E010 | David Martin | Project Management | 200 | 200 | 95 | 0 | 97 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E010 | David Martin | Project Management | 160 | 160 | 60 | 0 | 60 | 40 | 0 | 2026-08-02 | Approved | 2026-08-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E010 | David Martin | Project Management | 200 | 200 | 84.5 | 0 | 83.5 | 24 | 8 | 2026-09-02 | Approved | 2026-09-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E010 | David Martin | Project Management | 160 | 160 | 72 | 0 | 88 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E010 | David Martin | Project Management | 160 | 160 | 58 | 0 | 86 | 16 | 0 | 2026-11-02 | Approved | 2026-11-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E010 | David Martin | Project Management | 200 | 200 | 66.5 | 0 | 125.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E010 | David Martin | Project Management | 120 | 120 | 24 | 0 | 80 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E011 | Maya Fernandes | Project Management | 160 | 160 | 92 | 92 | 60 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E011 | Maya Fernandes | Project Management | 160 | 160 | 156.5 | 156.5 | 3.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E011 | Maya Fernandes | Project Management | 200 | 201 | 181 | 181 | 4 | 16 | 0 | 2026-04-02 | Approved | 2026-04-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E011 | Maya Fernandes | Project Management | 160 | 161 | 151 | 151 | 2 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E011 | Maya Fernandes | Project Management | 160 | 160 | 115.5 | 115.5 | 4.5 | 24 | 16 | 2026-06-02 | Approved | 2026-06-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E011 | Maya Fernandes | Project Management | 200 | 201 | 174.5 | 174.5 | 2.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E011 | Maya Fernandes | Project Management | 160 | 160.5 | 142 | 142 | 2.5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E011 | Maya Fernandes | Project Management | 200 | 200 | 191.5 | 191.5 | 0.5 | 0 | 8 | 2026-09-02 | Approved | 2026-09-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E011 | Maya Fernandes | Project Management | 160 | 160.5 | 151 | 151 | 1.5 | 8 | 0 | 2026-10-02 | Approved | 2026-10-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E011 | Maya Fernandes | Project Management | 160 | 160 | 136.5 | 136.5 | 23.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E011 | Maya Fernandes | Project Management | 200 | 200 | 133.5 | 133.5 | 18.5 | 40 | 8 | 2026-12-02 | Approved | 2026-12-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E011 | Maya Fernandes | Project Management | 120 | 120 | 71 | 71 | 33 | 0 | 16 | 2027-01-02 | Approved | 2027-01-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E012 | Julien Bernard | Project Management | 160 | 160 | 82.5 | 82.5 | 69.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E012 | Julien Bernard | Project Management | 160 | 162 | 85 | 85 | 77 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E012 | Julien Bernard | Project Management | 200 | 200 | 180.5 | 180.5 | 3.5 | 16 | 0 | 2026-04-02 | Approved | 2026-04-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E012 | Julien Bernard | Project Management | 160 | 160 | 112 | 112 | 0 | 40 | 8 | 2026-05-02 | Approved | 2026-05-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E012 | Julien Bernard | Project Management | 160 | 160 | 142.5 | 142.5 | 1.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E012 | Julien Bernard | Project Management | 200 | 200 | 188 | 188 | 4 | 0 | 8 | 2026-07-02 | Approved | 2026-07-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E012 | Julien Bernard | Project Management | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 2026-08-02 | Approved | 2026-08-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E012 | Julien Bernard | Project Management | 200 | 200 | 188 | 188 | 4 | 0 | 8 | 2026-09-02 | Approved | 2026-09-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E012 | Julien Bernard | Project Management | 160 | 160 | 142.5 | 142.5 | 1.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E012 | Julien Bernard | Project Management | 160 | 160 | 158.5 | 158.5 | 1.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E012 | Julien Bernard | Project Management | 200 | 204 | 147.5 | 147.5 | 8.5 | 40 | 8 | 2026-12-02 | Approved | 2026-12-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E012 | Julien Bernard | Project Management | 120 | 120 | 32.5 | 32.5 | 63.5 | 8 | 16 | 2027-01-02 | Approved | 2027-01-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E013 | Sara Khan | Project Management | 160 | 160 | 77.5 | 77.5 | 74.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E013 | Sara Khan | Project Management | 160 | 160 | 132 | 132 | 4 | 24 | 0 | 2026-03-02 | Approved | 2026-03-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E013 | Sara Khan | Project Management | 200 | 200 | 174 | 174 | 2 | 24 | 0 | 2026-04-02 | Approved | 2026-04-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E013 | Sara Khan | Project Management | 160 | 160 | 134.5 | 134.5 | 1.5 | 16 | 8 | 2026-05-02 | Approved | 2026-05-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E013 | Sara Khan | Project Management | 160 | 160 | 124.5 | 124.5 | 3.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E013 | Sara Khan | Project Management | 200 | 200 | 173 | 173 | 3 | 16 | 8 | 2026-07-02 | Approved | 2026-07-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E013 | Sara Khan | Project Management | 160 | 160 | 157 | 157 | 3 | 0 | 0 | 2026-08-02 | Pending |  | David Martin | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E013 | Sara Khan | Project Management | 200 | 200 | 166.5 | 166.5 | 1.5 | 24 | 8 | 2026-09-02 | Approved | 2026-09-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E013 | Sara Khan | Project Management | 160 | 154 | 82 | 82 | 72 | 0 | 0 | 2026-10-02 | Rejected |  | David Martin | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E013 | Sara Khan | Project Management | 160 | 160 | 81 | 81 | 79 | 0 | 0 | 2026-11-02 | Approved | 2026-11-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E013 | Sara Khan | Project Management | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E013 | Sara Khan | Project Management | 120 | 120 | 0 | 0 | 104 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E014 | Nicolas Wagner | Project Management | 160 | 160 | 62 | 62 | 90 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E014 | Nicolas Wagner | Project Management | 160 | 160 | 73 | 73 | 71 | 16 | 0 | 2026-03-02 | Approved | 2026-03-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E014 | Nicolas Wagner | Project Management | 200 | 200 | 93 | 93 | 91 | 16 | 0 | 2026-04-02 | Approved | 2026-04-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E014 | Nicolas Wagner | Project Management | 160 | 160 | 104 | 104 | 24 | 24 | 8 | 2026-05-02 | Approved | 2026-05-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E014 | Nicolas Wagner | Project Management | 160 | 160 | 138.5 | 138.5 | 5.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E014 | Nicolas Wagner | Project Management | 200 | 206 | 188 | 188 | 10 | 0 | 8 | 2026-07-02 | Approved | 2026-07-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E014 | Nicolas Wagner | Project Management | 160 | 166 | 158.5 | 158.5 | 7.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E014 | Nicolas Wagner | Project Management | 200 | 200 | 166 | 166 | 2 | 24 | 8 | 2026-09-02 | Approved | 2026-09-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E014 | Nicolas Wagner | Project Management | 160 | 160 | 142 | 142 | 2 | 16 | 0 | 2026-10-02 | Approved | 2026-10-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E014 | Nicolas Wagner | Project Management | 160 | 161 | 152 | 152 | 1 | 8 | 0 | 2026-11-02 | Approved | 2026-11-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E014 | Nicolas Wagner | Project Management | 200 | 200 | 173.5 | 173.5 | 2.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E014 | Nicolas Wagner | Project Management | 120 | 114 | 78.5 | 78.5 | 19.5 | 0 | 16 | 2027-01-02 | Rejected |  | David Martin | 1 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E015 | Inès Petit | Project Management | 160 | 160 | 57.5 | 0 | 94.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E015 | Inès Petit | Project Management | 160 | 160 | 77.5 | 0 | 58.5 | 24 | 0 | 2026-03-02 | Approved | 2026-03-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E015 | Inès Petit | Project Management | 200 | 200 | 128.5 | 0 | 71.5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E015 | Inès Petit | Project Management | 160 | 160 | 98 | 0 | 38 | 16 | 8 | 2026-05-02 | Approved | 2026-05-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E015 | Inès Petit | Project Management | 160 | 160 | 116 | 0 | 28 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E015 | Inès Petit | Project Management | 200 | 200 | 142.5 | 0 | 33.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E015 | Inès Petit | Project Management | 160 | 160 | 127.5 | 0 | 32.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E015 | Inès Petit | Project Management | 200 | 200 | 136.5 | 0 | 31.5 | 24 | 8 | 2026-09-02 | Approved | 2026-09-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E015 | Inès Petit | Project Management | 160 | 160 | 98 | 0 | 38 | 24 | 0 | 2026-10-02 | Approved | 2026-10-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E015 | Inès Petit | Project Management | 160 | 160 | 104 | 0 | 56 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E015 | Inès Petit | Project Management | 200 | 200 | 101.5 | 0 | 74.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E015 | Inès Petit | Project Management | 120 | 120 | 39.5 | 0 | 64.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 36 | 0 | 116 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 56 | 0 | 104 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E016 | Olivier Lefevre | Project Management | 200 | 200 | 80 | 0 | 120 | 0 | 0 | 2026-04-02 | Approved | 2026-04-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E016 | Olivier Lefevre | Project Management | 160 | 164 | 58.5 | 0 | 73.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 70.5 | 0 | 73.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E016 | Olivier Lefevre | Project Management | 200 | 196 | 79.5 | 0 | 76.5 | 32 | 8 | 2026-07-02 | Approved | 2026-07-05 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 75 | 0 | 77 | 8 | 0 | 2026-08-02 | Approved | 2026-08-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E016 | Olivier Lefevre | Project Management | 200 | 200 | 85.5 | 0 | 90.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 64 | 0 | 80 | 16 | 0 | 2026-10-02 | Approved | 2026-10-06 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E016 | Olivier Lefevre | Project Management | 160 | 160 | 56 | 0 | 80 | 24 | 0 | 2026-11-02 | Approved | 2026-11-04 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E016 | Olivier Lefevre | Project Management | 200 | 200 | 66.5 | 0 | 125.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E016 | Olivier Lefevre | Project Management | 120 | 126 | 24 | 0 | 86 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | David Martin | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E017 | Amina Amar | Data & AI | 160 | 162 | 87.5 | 87.5 | 66.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E017 | Amina Amar | Data & AI | 160 | 160 | 142.5 | 142.5 | 17.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E017 | Amina Amar | Data & AI | 200 | 200 | 167.5 | 167.5 | 24.5 | 8 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E017 | Amina Amar | Data & AI | 160 | 160 | 110.5 | 110.5 | 17.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E017 | Amina Amar | Data & AI | 160 | 156 | 129.5 | 129.5 | 10.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E017 | Amina Amar | Data & AI | 200 | 200 | 173.5 | 173.5 | 18.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E017 | Amina Amar | Data & AI | 160 | 160 | 109 | 109 | 11 | 40 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E017 | Amina Amar | Data & AI | 200 | 194.5 | 172 | 172 | 14.5 | 0 | 8 | 2026-09-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E017 | Amina Amar | Data & AI | 160 | 160 | 144.5 | 144.5 | 15.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E017 | Amina Amar | Data & AI | 160 | 160 | 99 | 99 | 13 | 48 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E017 | Amina Amar | Data & AI | 200 | 200 | 173.5 | 173.5 | 18.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E017 | Amina Amar | Data & AI | 120 | 120 | 70.5 | 70.5 | 33.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 104 | 104 | 48 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 127 | 127 | 17 | 16 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E018 | Gabriel Simon | Data & AI | 200 | 200 | 180.5 | 180.5 | 19.5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 117 | 117 | 11 | 24 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 133 | 133 | 11 | 0 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E018 | Gabriel Simon | Data & AI | 200 | 200 | 176.5 | 176.5 | 15.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 141.5 | 141.5 | 18.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E018 | Gabriel Simon | Data & AI | 200 | 204 | 159.5 | 159.5 | 20.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E018 | Gabriel Simon | Data & AI | 160 | 160 | 141.5 | 141.5 | 18.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E018 | Gabriel Simon | Data & AI | 160 | 157 | 110 | 110 | 7 | 40 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E018 | Gabriel Simon | Data & AI | 200 | 200 | 122.5 | 122.5 | 45.5 | 24 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E018 | Gabriel Simon | Data & AI | 120 | 120 | 60.5 | 60.5 | 43.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E019 | Eva Moreau | Data & AI | 160 | 160 | 0 | 0 | 128 | 24 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E019 | Eva Moreau | Data & AI | 160 | 160 | 126 | 126 | 26 | 8 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E019 | Eva Moreau | Data & AI | 200 | 200 | 155 | 155 | 29 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E019 | Eva Moreau | Data & AI | 160 | 160 | 109.5 | 109.5 | 26.5 | 16 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E019 | Eva Moreau | Data & AI | 160 | 160 | 140 | 140 | 4 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E019 | Eva Moreau | Data & AI | 200 | 200 | 173.5 | 173.5 | 2.5 | 16 | 8 | 2026-07-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E019 | Eva Moreau | Data & AI | 160 | 160 | 131 | 131 | 5 | 24 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E019 | Eva Moreau | Data & AI | 200 | 200 | 189.5 | 189.5 | 2.5 | 0 | 8 | 2026-09-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E019 | Eva Moreau | Data & AI | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 2026-10-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E019 | Eva Moreau | Data & AI | 160 | 160 | 142 | 142 | 2 | 16 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E019 | Eva Moreau | Data & AI | 200 | 200 | 190.5 | 190.5 | 1.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E019 | Eva Moreau | Data & AI | 120 | 120 | 79 | 79 | 25 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E020 | Antoine Robert | Data & AI | 160 | 160 | 102 | 102 | 50 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E020 | Antoine Robert | Data & AI | 160 | 160 | 150.5 | 150.5 | 1.5 | 8 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E020 | Antoine Robert | Data & AI | 200 | 200 | 198.5 | 198.5 | 1.5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E020 | Antoine Robert | Data & AI | 160 | 160 | 146 | 146 | 6 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E020 | Antoine Robert | Data & AI | 160 | 160 | 125.5 | 125.5 | 2.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E020 | Antoine Robert | Data & AI | 200 | 200 | 185.5 | 185.5 | 6.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E020 | Antoine Robert | Data & AI | 160 | 160 | 157.5 | 157.5 | 2.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E020 | Antoine Robert | Data & AI | 200 | 200 | 149 | 149 | 3 | 40 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E020 | Antoine Robert | Data & AI | 160 | 160 | 131.5 | 131.5 | 4.5 | 24 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E020 | Antoine Robert | Data & AI | 160 | 160 | 138 | 138 | 6 | 16 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E020 | Antoine Robert | Data & AI | 200 | 204 | 126 | 126 | 54 | 16 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E020 | Antoine Robert | Data & AI | 120 | 120 | 56.5 | 56.5 | 47.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 130.5 | 130.5 | 29.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E021 | Lea Nguyen | Data & AI | 200 | 200 | 157 | 157 | 43 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 108.5 | 108.5 | 27.5 | 16 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 117 | 117 | 3 | 24 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E021 | Lea Nguyen | Data & AI | 200 | 200 | 169.5 | 169.5 | 6.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 139 | 139 | 5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E021 | Lea Nguyen | Data & AI | 200 | 199.5 | 149.5 | 149.5 | 2 | 40 | 8 | 2026-09-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 151 | 151 | 1 | 8 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E021 | Lea Nguyen | Data & AI | 160 | 160 | 154.5 | 154.5 | 5.5 | 0 | 0 | 2026-11-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E021 | Lea Nguyen | Data & AI | 200 | 200 | 189.5 | 189.5 | 2.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E021 | Lea Nguyen | Data & AI | 120 | 120 | 80 | 80 | 24 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E022 | Hugo Laurent | Data & AI | 200 | 200 | 128 | 128 | 56 | 16 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 84 | 84 | 36 | 32 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 117 | 117 | 3 | 24 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E022 | Hugo Laurent | Data & AI | 200 | 204 | 191.5 | 191.5 | 4.5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 141 | 141 | 3 | 16 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E022 | Hugo Laurent | Data & AI | 200 | 200 | 188.5 | 188.5 | 3.5 | 0 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 139.5 | 139.5 | 4.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E022 | Hugo Laurent | Data & AI | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E022 | Hugo Laurent | Data & AI | 200 | 200 | 185.5 | 185.5 | 6.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E022 | Hugo Laurent | Data & AI | 120 | 120 | 79.5 | 79.5 | 24.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 146.5 | 146.5 | 5.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 155 | 155 | 5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E023 | Mila Costa | Cloud & Platform | 200 | 200 | 165 | 165 | 3 | 32 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 121.5 | 121.5 | 6.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 112 | 112 | 0 | 32 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E023 | Mila Costa | Cloud & Platform | 200 | 200 | 190 | 190 | 2 | 0 | 8 | 2026-07-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 153.5 | 153.5 | 6.5 | 0 | 0 | 2026-08-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E023 | Mila Costa | Cloud & Platform | 200 | 204 | 188 | 188 | 8 | 0 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 33 | 33 | 127 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E023 | Mila Costa | Cloud & Platform | 160 | 160 | 27.5 | 27.5 | 116.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E023 | Mila Costa | Cloud & Platform | 200 | 200 | 36.5 | 36.5 | 139.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E023 | Mila Costa | Cloud & Platform | 120 | 120 | 17 | 17 | 87 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 121.5 | 121.5 | 30.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 157 | 157 | 3 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E024 | Louis Fontaine | Cloud & Platform | 200 | 200 | 197 | 197 | 3 | 0 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E024 | Louis Fontaine | Cloud & Platform | 160 | 158.5 | 130 | 130 | 4.5 | 16 | 8 | 2026-05-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 139 | 139 | 5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E024 | Louis Fontaine | Cloud & Platform | 200 | 200 | 181.5 | 181.5 | 2.5 | 8 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 115 | 115 | 5 | 40 | 0 | 2026-08-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E024 | Louis Fontaine | Cloud & Platform | 200 | 204 | 149.5 | 149.5 | 6.5 | 40 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 28.5 | 28.5 | 115.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E024 | Louis Fontaine | Cloud & Platform | 160 | 160 | 30.5 | 30.5 | 129.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E024 | Louis Fontaine | Cloud & Platform | 200 | 200 | 37.5 | 37.5 | 154.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E024 | Louis Fontaine | Cloud & Platform | 120 | 120 | 15.5 | 15.5 | 88.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 152 | 152 | 0 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E025 | Camille Garcia | Cloud & Platform | 200 | 200 | 195 | 195 | 5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 150.5 | 150.5 | 1.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 120 | 120 | 0 | 24 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E025 | Camille Garcia | Cloud & Platform | 200 | 200 | 166 | 166 | 2 | 24 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 144 | 144 | 0 | 16 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E025 | Camille Garcia | Cloud & Platform | 200 | 200 | 171.5 | 171.5 | 4.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 49.5 | 49.5 | 110.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E025 | Camille Garcia | Cloud & Platform | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E025 | Camille Garcia | Cloud & Platform | 200 | 200 | 0 | 0 | 168 | 24 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E025 | Camille Garcia | Cloud & Platform | 120 | 120 | 0 | 0 | 104 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E026 | Noah Durand | Cybersecurity | 160 | 154 | 138.5 | 138.5 | 7.5 | 0 | 8 | 2026-02-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E026 | Noah Durand | Cybersecurity | 160 | 160 | 158 | 158 | 2 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E026 | Noah Durand | Cybersecurity | 200 | 200 | 180 | 180 | 4 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E026 | Noah Durand | Cybersecurity | 160 | 164.5 | 142.5 | 142.5 | 6 | 8 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E026 | Noah Durand | Cybersecurity | 160 | 160.5 | 141 | 141 | 3.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E026 | Noah Durand | Cybersecurity | 200 | 200 | 147 | 147 | 5 | 40 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E026 | Noah Durand | Cybersecurity | 160 | 160 | 158.5 | 158.5 | 1.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E026 | Noah Durand | Cybersecurity | 200 | 200.5 | 172.5 | 172.5 | 4 | 16 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E026 | Noah Durand | Cybersecurity | 160 | 161 | 143.5 | 143.5 | 1.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E026 | Noah Durand | Cybersecurity | 160 | 160 | 156 | 156 | 4 | 0 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E026 | Noah Durand | Cybersecurity | 200 | 200.5 | 188.5 | 188.5 | 4 | 0 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 4 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E026 | Noah Durand | Cybersecurity | 120 | 120 | 32 | 32 | 48 | 24 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E027 | Emma Lopez | Cybersecurity | 160 | 158 | 104.5 | 104.5 | 37.5 | 8 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E027 | Emma Lopez | Cybersecurity | 160 | 158.5 | 158 | 158 | 0.5 | 0 | 0 | 2026-03-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E027 | Emma Lopez | Cybersecurity | 200 | 200 | 181 | 181 | 3 | 16 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E027 | Emma Lopez | Cybersecurity | 160 | 160.5 | 150 | 150 | 2.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E027 | Emma Lopez | Cybersecurity | 160 | 160.5 | 144 | 144 | 0.5 | 0 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E027 | Emma Lopez | Cybersecurity | 200 | 201 | 191 | 191 | 2 | 0 | 8 | 2026-07-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E027 | Emma Lopez | Cybersecurity | 160 | 162.5 | 142 | 142 | 4.5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E027 | Emma Lopez | Cybersecurity | 200 | 200.5 | 135.5 | 135.5 | 1 | 56 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E027 | Emma Lopez | Cybersecurity | 160 | 160 | 82 | 82 | 54 | 24 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E027 | Emma Lopez | Cybersecurity | 160 | 154 | 94.5 | 94.5 | 59.5 | 0 | 0 | 2026-11-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E027 | Emma Lopez | Cybersecurity | 200 | 200 | 116 | 116 | 76 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E027 | Emma Lopez | Cybersecurity | 120 | 120 | 46.5 | 46.5 | 57.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E028 | Arthur Mercier | Consulting | 160 | 160 | 106 | 106 | 46 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E028 | Arthur Mercier | Consulting | 160 | 160 | 159.5 | 159.5 | 0.5 | 0 | 0 | 2026-03-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E028 | Arthur Mercier | Consulting | 200 | 200 | 173 | 173 | 3 | 24 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E028 | Arthur Mercier | Consulting | 160 | 160 | 148.5 | 148.5 | 3.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E028 | Arthur Mercier | Consulting | 160 | 160 | 142.5 | 142.5 | 1.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E028 | Arthur Mercier | Consulting | 200 | 200 | 166.5 | 166.5 | 1.5 | 24 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E028 | Arthur Mercier | Consulting | 160 | 160.5 | 157.5 | 157.5 | 3 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E028 | Arthur Mercier | Consulting | 200 | 200 | 173.5 | 173.5 | 2.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E028 | Arthur Mercier | Consulting | 160 | 160.5 | 120.5 | 120.5 | 0 | 40 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E028 | Arthur Mercier | Consulting | 160 | 160 | 157 | 157 | 3 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E028 | Arthur Mercier | Consulting | 200 | 200 | 121.5 | 121.5 | 54.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E028 | Arthur Mercier | Consulting | 120 | 120 | 38 | 38 | 66 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E029 | Chloé Diallo | Consulting | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E029 | Chloé Diallo | Consulting | 160 | 160 | 65.5 | 65.5 | 94.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E029 | Chloé Diallo | Consulting | 200 | 200 | 180.5 | 180.5 | 3.5 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E029 | Chloé Diallo | Consulting | 160 | 158.5 | 150.5 | 150.5 | 0 | 0 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E029 | Chloé Diallo | Consulting | 160 | 160 | 119.5 | 119.5 | 0.5 | 24 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E029 | Chloé Diallo | Consulting | 200 | 200 | 178.5 | 178.5 | 5.5 | 8 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E029 | Chloé Diallo | Consulting | 160 | 160 | 157.5 | 157.5 | 2.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E029 | Chloé Diallo | Consulting | 200 | 200 | 174 | 174 | 2 | 16 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E029 | Chloé Diallo | Consulting | 160 | 160 | 141.5 | 141.5 | 2.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E029 | Chloé Diallo | Consulting | 160 | 160 | 140 | 140 | 4 | 16 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E029 | Chloé Diallo | Consulting | 200 | 200 | 116.5 | 116.5 | 75.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E029 | Chloé Diallo | Consulting | 120 | 120 | 36 | 36 | 44 | 24 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E030 | Rayan Fischer | Applications | 160 | 160 | 151.5 | 151.5 | 0.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E030 | Rayan Fischer | Applications | 160 | 160 | 156.5 | 156.5 | 3.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E030 | Rayan Fischer | Applications | 200 | 200.5 | 168.5 | 168.5 | 0 | 32 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E030 | Rayan Fischer | Applications | 160 | 160 | 149 | 149 | 3 | 0 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E030 | Rayan Fischer | Applications | 160 | 160.5 | 140 | 140 | 4.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E030 | Rayan Fischer | Applications | 200 | 200 | 181 | 181 | 3 | 8 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E030 | Rayan Fischer | Applications | 160 | 159.5 | 157 | 157 | 2.5 | 0 | 0 | 2026-08-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E030 | Rayan Fischer | Applications | 200 | 200 | 141 | 141 | 3 | 48 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E030 | Rayan Fischer | Applications | 160 | 160 | 126 | 126 | 2 | 32 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E030 | Rayan Fischer | Applications | 160 | 160 | 117 | 117 | 43 | 0 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E030 | Rayan Fischer | Applications | 200 | 200 | 130.5 | 130.5 | 61.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E030 | Rayan Fischer | Applications | 120 | 120 | 16 | 16 | 88 | 0 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E031 | Lucie Pereira | Applications | 160 | 160 | 109 | 109 | 27 | 16 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E031 | Lucie Pereira | Applications | 160 | 160 | 114.5 | 114.5 | 29.5 | 16 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E031 | Lucie Pereira | Applications | 200 | 200.5 | 173.5 | 173.5 | 3 | 24 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E031 | Lucie Pereira | Applications | 160 | 160.5 | 132 | 132 | 4.5 | 16 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E031 | Lucie Pereira | Applications | 160 | 160 | 143.5 | 143.5 | 0.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E031 | Lucie Pereira | Applications | 200 | 200.5 | 174.5 | 174.5 | 2 | 16 | 8 | 2026-07-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E031 | Lucie Pereira | Applications | 160 | 160 | 131.5 | 131.5 | 4.5 | 24 | 0 | 2026-08-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E031 | Lucie Pereira | Applications | 200 | 200 | 181.5 | 181.5 | 2.5 | 8 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 4 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E031 | Lucie Pereira | Applications | 160 | 160 | 158 | 158 | 2 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E031 | Lucie Pereira | Applications | 160 | 160 | 112.5 | 112.5 | 47.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E031 | Lucie Pereira | Applications | 200 | 200 | 132 | 132 | 60 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E031 | Lucie Pereira | Applications | 120 | 106 | 55 | 55 | 35 | 0 | 16 | 2027-01-02 | Rejected |  | Relevant Project Manager / Line Manager | 4 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E032 | Maxime Richard | Applications | 160 | 162 | 104.5 | 104.5 | 49.5 | 0 | 8 | 2026-02-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E032 | Maxime Richard | Applications | 160 | 166 | 102 | 102 | 48 | 16 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E032 | Maxime Richard | Applications | 200 | 202 | 136 | 136 | 66 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E032 | Maxime Richard | Applications | 160 | 160 | 104.5 | 104.5 | 47.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E032 | Maxime Richard | Applications | 160 | 160 | 128 | 128 | 0 | 16 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E032 | Maxime Richard | Applications | 200 | 200.5 | 165.5 | 165.5 | 3 | 24 | 8 | 2026-07-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 4 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E032 | Maxime Richard | Applications | 160 | 160.5 | 144 | 144 | 0.5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E032 | Maxime Richard | Applications | 200 | 201 | 167 | 167 | 2 | 24 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E032 | Maxime Richard | Applications | 160 | 160 | 158 | 158 | 2 | 0 | 0 | 2026-10-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E032 | Maxime Richard | Applications | 160 | 160 | 117 | 117 | 43 | 0 | 0 | 2026-11-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E032 | Maxime Richard | Applications | 200 | 200 | 119.5 | 119.5 | 56.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E032 | Maxime Richard | Applications | 120 | 120 | 22 | 22 | 74 | 8 | 16 | 2027-01-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E033 | Aya Bauer | Sales | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E033 | Aya Bauer | Sales | 160 | 156 | 15.5 | 15.5 | 140.5 | 0 | 0 | 2026-03-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E033 | Aya Bauer | Sales | 200 | 200 | 19.5 | 19.5 | 164.5 | 16 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E033 | Aya Bauer | Sales | 160 | 152 | 16 | 16 | 128 | 0 | 8 | 2026-05-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E033 | Aya Bauer | Sales | 160 | 160 | 26.5 | 26.5 | 101.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E033 | Aya Bauer | Sales | 200 | 200 | 35.5 | 35.5 | 140.5 | 16 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E033 | Aya Bauer | Sales | 160 | 160 | 31 | 31 | 129 | 0 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E033 | Aya Bauer | Sales | 200 | 200 | 38.5 | 38.5 | 153.5 | 0 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E033 | Aya Bauer | Sales | 160 | 160 | 32 | 32 | 128 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E033 | Aya Bauer | Sales | 160 | 160 | 28.5 | 28.5 | 115.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E033 | Aya Bauer | Sales | 200 | 200 | 31.5 | 31.5 | 128.5 | 32 | 8 | 2026-12-02 | Approved | 2026-12-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E033 | Aya Bauer | Sales | 120 | 120 | 11.5 | 11.5 | 68.5 | 24 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E034 | Victor Renard | Sales | 160 | 160 | 16.5 | 16.5 | 135.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E034 | Victor Renard | Sales | 160 | 160 | 12.5 | 12.5 | 107.5 | 40 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E034 | Victor Renard | Sales | 200 | 200 | 19 | 19 | 181 | 0 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E034 | Victor Renard | Sales | 160 | 160 | 29.5 | 29.5 | 122.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E034 | Victor Renard | Sales | 160 | 160 | 29.5 | 29.5 | 114.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E034 | Victor Renard | Sales | 200 | 200 | 34.5 | 34.5 | 133.5 | 24 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E034 | Victor Renard | Sales | 160 | 160 | 32 | 32 | 128 | 0 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E034 | Victor Renard | Sales | 200 | 200 | 35.5 | 35.5 | 140.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E034 | Victor Renard | Sales | 160 | 160 | 28 | 28 | 116 | 16 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E034 | Victor Renard | Sales | 160 | 160 | 33 | 33 | 127 | 0 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E034 | Victor Renard | Sales | 200 | 200 | 36.5 | 36.5 | 147.5 | 8 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E034 | Victor Renard | Sales | 120 | 120 | 13 | 13 | 75 | 16 | 16 | 2027-01-02 | Approved | 2027-01-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 128 | 24 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E035 | Alice Meier | HR | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 144 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E035 | Alice Meier | HR | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E035 | Alice Meier | HR | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E035 | Alice Meier | HR | 160 | 160 | 0 | 0 | 128 | 32 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E035 | Alice Meier | HR | 200 | 200 | 0 | 0 | 160 | 32 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 1 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E035 | Alice Meier | HR | 120 | 120 | 0 | 0 | 88 | 16 | 16 | 2027-01-02 | Approved | 2027-01-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 136 | 24 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E036 | Nathan Cohen | HR | 200 | 200 | 0 | 0 | 184 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 144 | 0 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E036 | Nathan Cohen | HR | 200 | 200 | 0 | 0 | 152 | 40 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E036 | Nathan Cohen | HR | 160 | 156 | 0 | 0 | 156 | 0 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E036 | Nathan Cohen | HR | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 1 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 136 | 24 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E036 | Nathan Cohen | HR | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E036 | Nathan Cohen | HR | 200 | 200 | 0 | 0 | 192 | 0 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E036 | Nathan Cohen | HR | 120 | 114 | 0 | 0 | 98 | 0 | 16 | 2027-01-02 | Rejected |  | Relevant Project Manager / Line Manager | 1 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E037 | Lina Gomes | Operations | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 2026-04-02 | Approved | 2026-04-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 120 | 32 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 144 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E037 | Lina Gomes | Operations | 200 | 200 | 0 | 0 | 160 | 32 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E037 | Lina Gomes | Operations | 200 | 192 | 0 | 0 | 184 | 0 | 8 | 2026-09-02 | Rejected |  | Relevant Project Manager / Line Manager | 1 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E037 | Lina Gomes | Operations | 160 | 152 | 0 | 0 | 136 | 16 | 0 | 2026-10-02 | Rejected |  | Relevant Project Manager / Line Manager | 1 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E037 | Lina Gomes | Operations | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E037 | Lina Gomes | Operations | 200 | 200 | 0 | 0 | 168 | 24 | 8 | 2026-12-02 | Approved | 2026-12-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E037 | Lina Gomes | Operations | 120 | 120 | 0 | 0 | 104 | 0 | 16 | 2027-01-02 | Approved | 2027-01-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E038 | Paul Lemoine | Data & AI | 160 | 160 | 79.5 | 79.5 | 56.5 | 16 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E038 | Paul Lemoine | Data & AI | 160 | 160 | 99 | 99 | 61 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E038 | Paul Lemoine | Data & AI | 200 | 200 | 137 | 137 | 63 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E038 | Paul Lemoine | Data & AI | 160 | 160 | 143.5 | 143.5 | 0.5 | 8 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E038 | Paul Lemoine | Data & AI | 160 | 160.5 | 143.5 | 143.5 | 1 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E038 | Paul Lemoine | Data & AI | 200 | 200 | 172 | 172 | 4 | 16 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E038 | Paul Lemoine | Data & AI | 160 | 160 | 142.5 | 142.5 | 1.5 | 16 | 0 | 2026-08-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E038 | Paul Lemoine | Data & AI | 200 | 200 | 148.5 | 148.5 | 3.5 | 40 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E038 | Paul Lemoine | Data & AI | 160 | 160 | 158 | 158 | 2 | 0 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E038 | Paul Lemoine | Data & AI | 160 | 166 | 156.5 | 156.5 | 9.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E038 | Paul Lemoine | Data & AI | 200 | 202 | 163.5 | 163.5 | 6.5 | 24 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E038 | Paul Lemoine | Data & AI | 120 | 120 | 31.5 | 31.5 | 72.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E039 | Jade Santos | Data & AI | 160 | 160 | 106 | 106 | 46 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E039 | Jade Santos | Data & AI | 160 | 160 | 118.5 | 118.5 | 41.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E039 | Jade Santos | Data & AI | 200 | 200 | 136.5 | 136.5 | 55.5 | 8 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E039 | Jade Santos | Data & AI | 160 | 160 | 134 | 134 | 2 | 16 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E039 | Jade Santos | Data & AI | 160 | 160 | 142 | 142 | 2 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E039 | Jade Santos | Data & AI | 200 | 206 | 128 | 128 | 6 | 64 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E039 | Jade Santos | Data & AI | 160 | 160 | 159 | 159 | 1 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E039 | Jade Santos | Data & AI | 200 | 200 | 189.5 | 189.5 | 2.5 | 0 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E039 | Jade Santos | Data & AI | 160 | 160 | 155 | 155 | 5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E039 | Jade Santos | Data & AI | 160 | 160 | 155.5 | 155.5 | 4.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E039 | Jade Santos | Data & AI | 200 | 200 | 172.5 | 172.5 | 3.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E039 | Jade Santos | Data & AI | 120 | 120 | 19.5 | 19.5 | 68.5 | 16 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E040 | Adam Klein | Data & AI | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E040 | Adam Klein | Data & AI | 160 | 160 | 0 | 0 | 144 | 16 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E040 | Adam Klein | Data & AI | 200 | 202 | 0 | 0 | 178 | 24 | 0 | 2026-04-02 | Approved | 2026-04-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E040 | Adam Klein | Data & AI | 160 | 152 | 62 | 62 | 58 | 24 | 8 | 2026-05-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E040 | Adam Klein | Data & AI | 160 | 160 | 144 | 144 | 0 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E040 | Adam Klein | Data & AI | 200 | 202 | 176 | 176 | 2 | 16 | 8 | 2026-07-02 | Approved | 2026-07-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E040 | Adam Klein | Data & AI | 160 | 160 | 144 | 144 | 0 | 16 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E040 | Adam Klein | Data & AI | 200 | 200 | 177.5 | 177.5 | 6.5 | 8 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E040 | Adam Klein | Data & AI | 160 | 160 | 156 | 156 | 4 | 0 | 0 | 2026-10-02 | Approved | 2026-10-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E040 | Adam Klein | Data & AI | 160 | 164 | 140.5 | 140.5 | 7.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E040 | Adam Klein | Data & AI | 200 | 204 | 187 | 187 | 9 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E040 | Adam Klein | Data & AI | 120 | 120 | 80 | 80 | 24 | 0 | 16 | 2027-01-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E041 | Zoé Marques | Data & AI | 160 | 160 | 72 | 72 | 80 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E041 | Zoé Marques | Data & AI | 160 | 160 | 64.5 | 64.5 | 63.5 | 32 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E041 | Zoé Marques | Data & AI | 200 | 200 | 164 | 164 | 36 | 0 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E041 | Zoé Marques | Data & AI | 160 | 160 | 125.5 | 125.5 | 2.5 | 24 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E041 | Zoé Marques | Data & AI | 160 | 160 | 125 | 125 | 3 | 16 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E041 | Zoé Marques | Data & AI | 200 | 200.5 | 191.5 | 191.5 | 1 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E041 | Zoé Marques | Data & AI | 160 | 160 | 142 | 142 | 2 | 16 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E041 | Zoé Marques | Data & AI | 200 | 200 | 189.5 | 189.5 | 2.5 | 0 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E041 | Zoé Marques | Data & AI | 160 | 160 | 154 | 154 | 6 | 0 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E041 | Zoé Marques | Data & AI | 160 | 160 | 133.5 | 133.5 | 2.5 | 24 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E041 | Zoé Marques | Data & AI | 200 | 200 | 186.5 | 186.5 | 5.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E041 | Zoé Marques | Data & AI | 120 | 114 | 36.5 | 36.5 | 53.5 | 8 | 16 | 2027-01-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E042 | Samuel Jung | Data & AI | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E042 | Samuel Jung | Data & AI | 160 | 160 | 0 | 0 | 160 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E042 | Samuel Jung | Data & AI | 200 | 200 | 93.5 | 93.5 | 90.5 | 16 | 0 | 2026-04-02 | Approved | 2026-04-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E042 | Samuel Jung | Data & AI | 160 | 160 | 73 | 73 | 79 | 0 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E042 | Samuel Jung | Data & AI | 160 | 160 | 117 | 117 | 3 | 24 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E042 | Samuel Jung | Data & AI | 200 | 199 | 157.5 | 157.5 | 1.5 | 32 | 8 | 2026-07-02 | Rejected |  | Relevant Project Manager / Line Manager | 4 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E042 | Samuel Jung | Data & AI | 160 | 160 | 132.5 | 132.5 | 3.5 | 24 | 0 | 2026-08-02 | Approved | 2026-08-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E042 | Samuel Jung | Data & AI | 200 | 200 | 190 | 190 | 2 | 0 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E042 | Samuel Jung | Data & AI | 160 | 160 | 149.5 | 149.5 | 2.5 | 8 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E042 | Samuel Jung | Data & AI | 160 | 160 | 156.5 | 156.5 | 3.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E042 | Samuel Jung | Data & AI | 200 | 200 | 190 | 190 | 2 | 0 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E042 | Samuel Jung | Data & AI | 120 | 120 | 64 | 64 | 24 | 16 | 16 | 2027-01-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E043 | Manon Franco | Data & AI | 160 | 160 | 0 | 0 | 152 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E043 | Manon Franco | Data & AI | 160 | 158 | 0 | 0 | 158 | 0 | 0 | 2026-03-02 | Approved | 2026-03-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E043 | Manon Franco | Data & AI | 200 | 200 | 119.5 | 119.5 | 80.5 | 0 | 0 | 2026-04-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E043 | Manon Franco | Data & AI | 160 | 160 | 120.5 | 120.5 | 31.5 | 0 | 8 | 2026-05-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E043 | Manon Franco | Data & AI | 160 | 160 | 141 | 141 | 3 | 0 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E043 | Manon Franco | Data & AI | 200 | 200.5 | 144.5 | 144.5 | 0 | 48 | 8 | 2026-07-02 | Approved | 2026-07-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E043 | Manon Franco | Data & AI | 160 | 160.5 | 143 | 143 | 1.5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E043 | Manon Franco | Data & AI | 200 | 201 | 189 | 189 | 4 | 0 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E043 | Manon Franco | Data & AI | 160 | 161 | 120.5 | 120.5 | 0.5 | 40 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E043 | Manon Franco | Data & AI | 160 | 160 | 158.5 | 158.5 | 1.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E043 | Manon Franco | Data & AI | 200 | 200 | 171 | 171 | 5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E043 | Manon Franco | Data & AI | 120 | 120.5 | 79.5 | 79.5 | 25 | 0 | 16 | 2027-01-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 1 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E044 | Yanis Vidal | Cloud & Platform | 160 | 160 | 107.5 | 107.5 | 44.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E044 | Yanis Vidal | Cloud & Platform | 160 | 152 | 113.5 | 113.5 | 22.5 | 16 | 0 | 2026-03-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E044 | Yanis Vidal | Cloud & Platform | 200 | 200.5 | 183.5 | 183.5 | 1 | 16 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E044 | Yanis Vidal | Cloud & Platform | 160 | 162 | 151 | 151 | 3 | 0 | 8 | 2026-05-02 | Approved | 2026-05-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E044 | Yanis Vidal | Cloud & Platform | 160 | 160 | 143.5 | 143.5 | 0.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E044 | Yanis Vidal | Cloud & Platform | 200 | 200 | 143 | 143 | 1 | 48 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E044 | Yanis Vidal | Cloud & Platform | 160 | 160 | 142 | 142 | 2 | 16 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E044 | Yanis Vidal | Cloud & Platform | 200 | 204.5 | 174 | 174 | 6.5 | 16 | 8 | 2026-09-02 | Approved | 2026-09-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E044 | Yanis Vidal | Cloud & Platform | 160 | 160 | 113.5 | 113.5 | 46.5 | 0 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E044 | Yanis Vidal | Cloud & Platform | 160 | 160 | 110.5 | 110.5 | 49.5 | 0 | 0 | 2026-11-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E044 | Yanis Vidal | Cloud & Platform | 200 | 200 | 125.5 | 125.5 | 58.5 | 8 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E044 | Yanis Vidal | Cloud & Platform | 120 | 120 | 56.5 | 56.5 | 47.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 91.5 | 91.5 | 60.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 154.5 | 154.5 | 5.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E045 | Louise Carvalho | Cloud & Platform | 200 | 200 | 165 | 165 | 3 | 32 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 135 | 135 | 1 | 16 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 127.5 | 127.5 | 0.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E045 | Louise Carvalho | Cloud & Platform | 200 | 204.5 | 184.5 | 184.5 | 12 | 0 | 8 | 2026-07-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 153 | 153 | 7 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E045 | Louise Carvalho | Cloud & Platform | 200 | 200 | 190 | 190 | 2 | 0 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 2 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 156 | 156 | 4 | 0 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E045 | Louise Carvalho | Cloud & Platform | 160 | 160 | 155.5 | 155.5 | 4.5 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E045 | Louise Carvalho | Cloud & Platform | 200 | 200 | 133.5 | 133.5 | 2.5 | 56 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E045 | Louise Carvalho | Cloud & Platform | 120 | 120 | 79.5 | 79.5 | 24.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 160 | 135.5 | 135.5 | 16.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 160 | 157.5 | 157.5 | 2.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E046 | Alexandre Blanc | Cloud & Platform | 200 | 200 | 166.5 | 166.5 | 1.5 | 32 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 160 | 151 | 151 | 1 | 0 | 8 | 2026-05-02 | Approved | 2026-05-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 158.5 | 126.5 | 126.5 | 0 | 16 | 16 | 2026-06-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E046 | Alexandre Blanc | Cloud & Platform | 200 | 198.5 | 185.5 | 185.5 | 5 | 0 | 8 | 2026-07-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 160 | 158.5 | 158.5 | 1.5 | 0 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E046 | Alexandre Blanc | Cloud & Platform | 200 | 200 | 150 | 150 | 2 | 40 | 8 | 2026-09-02 | Approved | 2026-09-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 152 | 128.5 | 128.5 | 23.5 | 0 | 0 | 2026-10-02 | Rejected |  | Relevant Project Manager / Line Manager | 2 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E046 | Alexandre Blanc | Cloud & Platform | 160 | 162 | 71.5 | 71.5 | 74.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E046 | Alexandre Blanc | Cloud & Platform | 200 | 200 | 87.5 | 87.5 | 88.5 | 16 | 8 | 2026-12-02 | Approved | 2026-12-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E046 | Alexandre Blanc | Cloud & Platform | 120 | 120 | 40.5 | 40.5 | 63.5 | 0 | 16 | 2027-01-02 | Approved | 2027-01-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 92.5 | 92.5 | 59.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 142 | 142 | 2 | 16 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E047 | Mia Nowak | Cybersecurity | 200 | 205 | 196.5 | 196.5 | 8.5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 151.5 | 151.5 | 0.5 | 0 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 143.5 | 143.5 | 0.5 | 0 | 16 | 2026-06-02 | Approved | 2026-06-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E047 | Mia Nowak | Cybersecurity | 200 | 206 | 175 | 175 | 7 | 16 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 132 | 132 | 4 | 24 | 0 | 2026-08-02 | Approved | 2026-08-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E047 | Mia Nowak | Cybersecurity | 200 | 200 | 189 | 189 | 3 | 0 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E047 | Mia Nowak | Cybersecurity | 160 | 158 | 138 | 138 | 4 | 16 | 0 | 2026-10-02 | Rejected |  | Relevant Project Manager / Line Manager | 3 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E047 | Mia Nowak | Cybersecurity | 160 | 160 | 148 | 148 | 4 | 8 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E047 | Mia Nowak | Cybersecurity | 200 | 196 | 105.5 | 105.5 | 42.5 | 40 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E047 | Mia Nowak | Cybersecurity | 120 | 120 | 39 | 39 | 65 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E048 | Raphaël Meyer | Cybersecurity | 160 | 160 | 57.5 | 57.5 | 94.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E048 | Raphaël Meyer | Cybersecurity | 160 | 164 | 160 | 160 | 4 | 0 | 0 | 2026-03-02 | Approved | 2026-03-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E048 | Raphaël Meyer | Cybersecurity | 200 | 200 | 197.5 | 197.5 | 2.5 | 0 | 0 | 2026-04-02 | Approved | 2026-04-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E048 | Raphaël Meyer | Cybersecurity | 160 | 160 | 86 | 86 | 2 | 64 | 8 | 2026-05-02 | Approved | 2026-05-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E048 | Raphaël Meyer | Cybersecurity | 160 | 160 | 123.5 | 123.5 | 4.5 | 16 | 16 | 2026-06-02 | Approved | 2026-06-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E048 | Raphaël Meyer | Cybersecurity | 200 | 200 | 191 | 191 | 1 | 0 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E048 | Raphaël Meyer | Cybersecurity | 160 | 160 | 138.5 | 138.5 | 5.5 | 16 | 0 | 2026-08-02 | Approved | 2026-08-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E048 | Raphaël Meyer | Cybersecurity | 200 | 200 | 180.5 | 180.5 | 3.5 | 8 | 8 | 2026-09-02 | Approved | 2026-09-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E048 | Raphaël Meyer | Cybersecurity | 160 | 167 | 143.5 | 143.5 | 7.5 | 16 | 0 | 2026-10-02 | Approved | 2026-10-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E048 | Raphaël Meyer | Cybersecurity | 160 | 160.5 | 158.5 | 158.5 | 2 | 0 | 0 | 2026-11-02 | Approved | 2026-11-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E048 | Raphaël Meyer | Cybersecurity | 200 | 200 | 133.5 | 133.5 | 58.5 | 0 | 8 | 2026-12-02 | Approved | 2026-12-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E048 | Raphaël Meyer | Cybersecurity | 120 | 120 | 54 | 54 | 50 | 0 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E049 | Nora Aydin | Consulting | 160 | 160 | 145 | 145 | 7 | 0 | 8 | 2026-02-02 | Approved | 2026-02-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E049 | Nora Aydin | Consulting | 160 | 160 | 159 | 159 | 1 | 0 | 0 | 2026-03-02 | Approved | 2026-03-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E049 | Nora Aydin | Consulting | 200 | 200 | 158.5 | 158.5 | 1.5 | 40 | 0 | 2026-04-02 | Approved | 2026-04-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E049 | Nora Aydin | Consulting | 160 | 160 | 135 | 135 | 1 | 16 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E049 | Nora Aydin | Consulting | 160 | 161 | 137 | 137 | 0 | 8 | 16 | 2026-06-02 | Approved | 2026-06-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E049 | Nora Aydin | Consulting | 200 | 200 | 187 | 187 | 5 | 0 | 8 | 2026-07-02 | Approved | 2026-07-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E049 | Nora Aydin | Consulting | 160 | 160 | 158 | 158 | 2 | 0 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E049 | Nora Aydin | Consulting | 200 | 200 | 166.5 | 166.5 | 1.5 | 24 | 8 | 2026-09-02 | Approved | 2026-09-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E049 | Nora Aydin | Consulting | 160 | 160 | 159 | 159 | 1 | 0 | 0 | 2026-10-02 | Approved | 2026-10-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E049 | Nora Aydin | Consulting | 160 | 160 | 100.5 | 100.5 | 43.5 | 16 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E049 | Nora Aydin | Consulting | 200 | 200 | 126.5 | 126.5 | 65.5 | 0 | 8 | 2026-12-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 3 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E049 | Nora Aydin | Consulting | 120 | 120 | 13 | 13 | 75 | 16 | 16 | 2027-01-02 | Approved | 2027-01-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E050 | Mathis Girard | Consulting | 160 | 160 | 105.5 | 105.5 | 46.5 | 0 | 8 | 2026-02-02 | Approved | 2026-02-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E050 | Mathis Girard | Consulting | 160 | 160 | 113.5 | 113.5 | 46.5 | 0 | 0 | 2026-03-02 | Approved | 2026-03-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E050 | Mathis Girard | Consulting | 200 | 200 | 131 | 131 | 53 | 16 | 0 | 2026-04-02 | Approved | 2026-04-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E050 | Mathis Girard | Consulting | 160 | 160 | 134 | 134 | 2 | 16 | 8 | 2026-05-02 | Approved | 2026-05-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E050 | Mathis Girard | Consulting | 160 | 160 | 118 | 118 | 2 | 24 | 16 | 2026-06-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 4 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E050 | Mathis Girard | Consulting | 200 | 200 | 185 | 185 | 7 | 0 | 8 | 2026-07-02 | Approved | 2026-07-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E050 | Mathis Girard | Consulting | 160 | 160 | 149 | 149 | 3 | 8 | 0 | 2026-08-02 | Approved | 2026-08-06 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E050 | Mathis Girard | Consulting | 200 | 200 | 190.5 | 190.5 | 1.5 | 0 | 8 | 2026-09-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 7 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E050 | Mathis Girard | Consulting | 160 | 160 | 119 | 119 | 25 | 16 | 0 | 2026-10-02 | Approved | 2026-10-04 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E050 | Mathis Girard | Consulting | 160 | 160 | 49 | 49 | 111 | 0 | 0 | 2026-11-02 | Approved | 2026-11-05 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E050 | Mathis Girard | Consulting | 200 | 200 | 45.5 | 45.5 | 106.5 | 40 | 8 | 2026-12-02 | Approved | 2026-12-03 | Relevant Project Manager / Line Manager | 0 | 0 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E050 | Mathis Girard | Consulting | 120 | 120 | 24.5 | 24.5 | 79.5 | 0 | 16 | 2027-01-02 | Pending |  | Relevant Project Manager / Line Manager | 0 | 1 | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE

## Work Packages
record_type | project_id | project_name | item_id | item_name | planned_start_date | planned_end_date | actual_or_forecast_date | planned_effort_hours | owner_name | status | acceptance_criteria | classification | synthetic_record
Work Package | P001 | LuxHealth Data Platform | WP01 | Initiation and discovery | 2026-01-05 | 2026-02-16 | 2026-02-18 | 1081.2 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP02 | Architecture and detailed design | 2026-02-02 | 2026-04-12 | 2026-04-12 | 1776.3 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP03 | Build and configuration | 2026-03-22 | 2026-08-08 | 2026-08-08 | 3578.3 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP04 | Data, integration and migration | 2026-04-19 | 2026-09-05 | 2026-09-05 | 3578.3 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP05 | Testing, validation and remediation | 2026-08-01 | 2026-10-30 | 2026-11-04 | 2316.9 | Amina Amar | In Progress | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP06 | Deployment, transition and closure | 2026-10-17 | 2026-12-18 | 2026-12-23 | 1596.1 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P001 | LuxHealth Data Platform | WP07 | Project management and governance | 2026-01-05 | 2026-12-18 | 2026-12-18 | 8932.8 | Maya Fernandes | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M01 | Project kickoff | 2026-01-12 | 2026-01-12 | 2026-01-17 | 0 | Maya Fernandes | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M02 | Design baseline approved | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0 | Maya Fernandes | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M03 | Minimum viable release completed | 2026-07-15 | 2026-07-15 | 2026-07-15 | 0 | Maya Fernandes | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M04 | User acceptance testing completed | 2026-10-17 | 2026-10-17 | 2026-10-17 | 0 | Maya Fernandes | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M05 | Production go-live / final delivery | 2026-12-04 | 2026-12-04 | 2026-12-04 | 0 | Maya Fernandes | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P001 | LuxHealth Data Platform | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-21 | 0 | Maya Fernandes | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP01 | Initiation and discovery | 2026-02-02 | 2026-03-12 | 2026-03-12 | 771.9 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP02 | Architecture and detailed design | 2026-02-28 | 2026-05-02 | 2026-05-02 | 1279.8 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP03 | Build and configuration | 2026-04-13 | 2026-08-19 | 2026-08-24 | 2600.2 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP04 | Data, integration and migration | 2026-05-09 | 2026-09-13 | 2026-09-13 | 2579.9 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP05 | Testing, validation and remediation | 2026-08-12 | 2026-11-03 | 2026-10-31 | 1686.1 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP06 | Deployment, transition and closure | 2026-10-22 | 2026-12-18 | 2026-12-23 | 1157.9 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P002 | Sovereign AI Factory | WP07 | Project management and governance | 2026-02-02 | 2026-12-18 | 2026-12-20 | 6480.3 | Maya Fernandes | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M01 | Project kickoff | 2026-02-08 | 2026-02-08 | 2026-02-06 | 0 | Maya Fernandes | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M02 | Design baseline approved | 2026-04-23 | 2026-04-23 | 2026-05-01 | 0 | Maya Fernandes | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M03 | Minimum viable release completed | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0 | Maya Fernandes | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M04 | User acceptance testing completed | 2026-10-22 | 2026-10-22 | 2026-10-22 | 0 | Maya Fernandes | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M05 | Production go-live / final delivery | 2026-12-05 | 2026-12-05 | 2026-12-05 | 0 | Maya Fernandes | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P002 | Sovereign AI Factory | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-18 | 0 | Maya Fernandes | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP01 | Initiation and discovery | 2026-01-05 | 2026-02-13 | 2026-02-10 | 1090.9 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP02 | Architecture and detailed design | 2026-01-31 | 2026-04-07 | 2026-04-12 | 1846.1 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP03 | Build and configuration | 2026-03-18 | 2026-07-28 | 2026-08-02 | 3692.2 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP04 | Data, integration and migration | 2026-04-14 | 2026-08-23 | 2026-08-28 | 3664.3 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP05 | Testing, validation and remediation | 2026-07-21 | 2026-10-15 | 2026-10-12 | 2405.5 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP06 | Deployment, transition and closure | 2026-10-02 | 2026-11-30 | 2026-11-30 | 1650.3 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P003 | Core Banking Modernisation | WP07 | Project management and governance | 2026-01-05 | 2026-11-30 | 2026-12-02 | 9202.6 | Julien Bernard | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M01 | Project kickoff | 2026-01-12 | 2026-01-12 | 2026-01-20 | 0 | Julien Bernard | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M02 | Design baseline approved | 2026-03-28 | 2026-03-28 | 2026-03-28 | 0 | Julien Bernard | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M03 | Minimum viable release completed | 2026-07-05 | 2026-07-05 | 2026-07-13 | 0 | Julien Bernard | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M04 | User acceptance testing completed | 2026-10-02 | 2026-10-02 | 2026-10-05 | 0 | Julien Bernard | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M05 | Production go-live / final delivery | 2026-11-17 | 2026-11-17 | 2026-11-15 | 0 | Julien Bernard | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P003 | Core Banking Modernisation | M06 | Project closure accepted | 2026-11-30 | 2026-11-30 | 2026-12-08 | 0 | Julien Bernard | Forecast Late | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP01 | Initiation and discovery | 2026-03-02 | 2026-04-06 | 2026-04-03 | 796 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP02 | Architecture and detailed design | 2026-03-25 | 2026-05-22 | 2026-05-22 | 1319.1 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP03 | Build and configuration | 2026-05-05 | 2026-08-29 | 2026-08-29 | 2638.2 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP04 | Data, integration and migration | 2026-05-28 | 2026-09-22 | 2026-09-22 | 2660.9 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP05 | Testing, validation and remediation | 2026-08-24 | 2026-11-07 | 2026-11-07 | 1705.7 | Amina Amar | In Progress | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP06 | Deployment, transition and closure | 2026-10-27 | 2026-12-18 | 2026-12-20 | 1182.6 | Amina Amar | Not Started | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P004 | Smart Mobility Analytics | WP07 | Project management and governance | 2026-03-02 | 2026-12-18 | 2026-12-23 | 6618.2 | Julien Bernard | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M01 | Project kickoff | 2026-03-08 | 2026-03-08 | 2026-03-06 | 0 | Julien Bernard | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M02 | Design baseline approved | 2026-05-14 | 2026-05-14 | 2026-05-17 | 0 | Julien Bernard | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M03 | Minimum viable release completed | 2026-08-09 | 2026-08-09 | 2026-08-09 | 0 | Julien Bernard | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M04 | User acceptance testing completed | 2026-10-27 | 2026-10-27 | 2026-10-25 | 0 | Julien Bernard | Forecast On Time | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M05 | Production go-live / final delivery | 2026-12-06 | 2026-12-06 | 2026-12-14 | 0 | Julien Bernard | Forecast Late | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P004 | Smart Mobility Analytics | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-18 | 0 | Julien Bernard | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP01 | Initiation and discovery | 2026-01-05 | 2026-02-03 | 2026-02-08 | 699.3 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP02 | Architecture and detailed design | 2026-01-24 | 2026-03-13 | 2026-03-13 | 1157.5 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP03 | Build and configuration | 2026-02-26 | 2026-06-02 | 2026-06-04 | 2315 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP04 | Data, integration and migration | 2026-03-17 | 2026-06-21 | 2026-06-21 | 2315 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP05 | Testing, validation and remediation | 2026-05-28 | 2026-07-29 | 2026-07-31 | 1495.1 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP06 | Deployment, transition and closure | 2026-07-19 | 2026-08-31 | 2026-09-02 | 1036.9 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P005 | Cloud Landing Zone | WP07 | Project management and governance | 2026-01-05 | 2026-08-31 | 2026-08-28 | 5739.2 | Sara Khan | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M01 | Project kickoff | 2026-01-10 | 2026-01-10 | 2026-01-13 | 0 | Sara Khan | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M02 | Design baseline approved | 2026-03-06 | 2026-03-06 | 2026-03-04 | 0 | Sara Khan | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M03 | Minimum viable release completed | 2026-05-16 | 2026-05-16 | 2026-05-21 | 0 | Sara Khan | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M04 | User acceptance testing completed | 2026-07-19 | 2026-07-19 | 2026-07-22 | 0 | Sara Khan | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M05 | Production go-live / final delivery | 2026-08-21 | 2026-08-21 | 2026-08-21 | 0 | Sara Khan | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P005 | Cloud Landing Zone | M06 | Project closure accepted | 2026-08-31 | 2026-08-31 | 2026-09-08 | 0 | Sara Khan | Forecast Late | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP01 | Initiation and discovery | 2026-02-02 | 2026-03-06 | 2026-03-06 | 479.1 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP02 | Architecture and detailed design | 2026-02-24 | 2026-04-19 | 2026-04-16 | 808.5 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP03 | Build and configuration | 2026-04-02 | 2026-07-19 | 2026-07-24 | 1616.9 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP04 | Data, integration and migration | 2026-04-24 | 2026-08-10 | 2026-08-07 | 1616.9 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP05 | Testing, validation and remediation | 2026-07-14 | 2026-09-22 | 2026-09-22 | 1048 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP06 | Deployment, transition and closure | 2026-09-11 | 2026-10-30 | 2026-11-04 | 733.6 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P006 | AML Data Quality | WP07 | Project management and governance | 2026-02-02 | 2026-10-30 | 2026-10-27 | 4042.3 | Sara Khan | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M01 | Project kickoff | 2026-02-07 | 2026-02-07 | 2026-02-10 | 0 | Sara Khan | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M02 | Design baseline approved | 2026-04-11 | 2026-04-11 | 2026-04-19 | 0 | Sara Khan | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M03 | Minimum viable release completed | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0 | Sara Khan | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M04 | User acceptance testing completed | 2026-09-11 | 2026-09-11 | 2026-09-09 | 0 | Sara Khan | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M05 | Production go-live / final delivery | 2026-10-19 | 2026-10-19 | 2026-10-19 | 0 | Sara Khan | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P006 | AML Data Quality | M06 | Project closure accepted | 2026-10-30 | 2026-10-30 | 2026-10-30 | 0 | Sara Khan | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP01 | Initiation and discovery | 2026-01-12 | 2026-02-22 | 2026-02-22 | 1090.6 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP02 | Architecture and detailed design | 2026-02-08 | 2026-04-17 | 2026-04-17 | 1808.8 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP03 | Build and configuration | 2026-03-28 | 2026-08-11 | 2026-08-16 | 3617.6 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP04 | Data, integration and migration | 2026-04-24 | 2026-09-07 | 2026-09-07 | 3617.6 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP05 | Testing, validation and remediation | 2026-08-04 | 2026-10-31 | 2026-10-31 | 2340.8 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP06 | Deployment, transition and closure | 2026-10-18 | 2026-12-18 | 2026-12-15 | 1622.6 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P007 | Cyber Resilience Programme | WP07 | Project management and governance | 2026-01-12 | 2026-12-18 | 2026-12-18 | 9044 | Nicolas Wagner | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M01 | Project kickoff | 2026-01-19 | 2026-01-19 | 2026-01-24 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M02 | Design baseline approved | 2026-04-07 | 2026-04-07 | 2026-04-05 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M03 | Minimum viable release completed | 2026-07-18 | 2026-07-18 | 2026-07-18 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M04 | User acceptance testing completed | 2026-10-18 | 2026-10-18 | 2026-10-18 | 0 | Nicolas Wagner | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M05 | Production go-live / final delivery | 2026-12-04 | 2026-12-04 | 2026-12-12 | 0 | Nicolas Wagner | Forecast Late | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P007 | Cyber Resilience Programme | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-26 | 0 | Nicolas Wagner | Forecast Late | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP01 | Initiation and discovery | 2026-04-06 | 2026-05-07 | 2026-05-07 | 446.4 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP02 | Architecture and detailed design | 2026-04-26 | 2026-06-17 | 2026-06-17 | 748.8 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP03 | Build and configuration | 2026-06-01 | 2026-09-12 | 2026-09-17 | 1483.2 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP04 | Data, integration and migration | 2026-06-22 | 2026-10-02 | 2026-10-07 | 1468.8 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP05 | Testing, validation and remediation | 2026-09-07 | 2026-11-12 | 2026-11-09 | 950.4 | Amina Amar | In Progress | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP06 | Deployment, transition and closure | 2026-11-02 | 2026-12-18 | 2026-12-20 | 662.4 | Amina Amar | Not Started | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P008 | Customer 360 Platform | WP07 | Project management and governance | 2026-04-06 | 2026-12-18 | 2026-12-18 | 3686.4 | Nicolas Wagner | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M01 | Project kickoff | 2026-04-11 | 2026-04-11 | 2026-04-09 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M02 | Design baseline approved | 2026-06-09 | 2026-06-09 | 2026-06-09 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M03 | Minimum viable release completed | 2026-08-25 | 2026-08-25 | 2026-08-23 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M04 | User acceptance testing completed | 2026-11-02 | 2026-11-02 | 2026-11-10 | 0 | Nicolas Wagner | Forecast Late | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M05 | Production go-live / final delivery | 2026-12-08 | 2026-12-08 | 2026-12-08 | 0 | Nicolas Wagner | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P008 | Customer 360 Platform | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-26 | 0 | Nicolas Wagner | Forecast Late | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP01 | Initiation and discovery | 2026-01-05 | 2026-02-06 | 2026-02-06 | 506.5 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP02 | Architecture and detailed design | 2026-01-26 | 2026-03-21 | 2026-03-18 | 854.7 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP03 | Build and configuration | 2026-03-05 | 2026-06-20 | 2026-06-25 | 1693.7 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP04 | Data, integration and migration | 2026-03-26 | 2026-07-12 | 2026-07-12 | 1709.5 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP05 | Testing, validation and remediation | 2026-06-15 | 2026-08-23 | 2026-08-23 | 1092.2 | Amina Amar | Completed | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP06 | Deployment, transition and closure | 2026-08-13 | 2026-09-30 | 2026-09-30 | 759.8 | Amina Amar | In Progress | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P009 | ERP Integration | WP07 | Project management and governance | 2026-01-05 | 2026-09-30 | 2026-09-30 | 4242.1 | Maya Fernandes | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M01 | Project kickoff | 2026-01-10 | 2026-01-10 | 2026-01-15 | 0 | Maya Fernandes | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M02 | Design baseline approved | 2026-03-13 | 2026-03-13 | 2026-03-21 | 0 | Maya Fernandes | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M03 | Minimum viable release completed | 2026-06-01 | 2026-06-01 | 2026-06-09 | 0 | Maya Fernandes | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M04 | User acceptance testing completed | 2026-08-13 | 2026-08-13 | 2026-08-13 | 0 | Maya Fernandes | Completed | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M05 | Production go-live / final delivery | 2026-09-19 | 2026-09-19 | 2026-09-27 | 0 | Maya Fernandes | Forecast Late | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P009 | ERP Integration | M06 | Project closure accepted | 2026-09-30 | 2026-09-30 | 2026-09-30 | 0 | Maya Fernandes | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP01 | Initiation and discovery | 2026-05-04 | 2026-05-31 | 2026-05-28 | 436.6 | Amina Amar | Completed | Initiation and discovery deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP02 | Architecture and detailed design | 2026-05-22 | 2026-07-07 | 2026-07-12 | 743.9 | Amina Amar | Completed | Architecture and detailed design deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP03 | Build and configuration | 2026-06-23 | 2026-09-22 | 2026-09-22 | 1471.6 | Amina Amar | Completed | Build and configuration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP04 | Data, integration and migration | 2026-07-11 | 2026-10-11 | 2026-10-13 | 1487.8 | Amina Amar | Completed | Data, integration and migration deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP05 | Testing, validation and remediation | 2026-09-18 | 2026-11-16 | 2026-11-16 | 954.1 | Amina Amar | In Progress | Testing, validation and remediation deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP06 | Deployment, transition and closure | 2026-11-07 | 2026-12-18 | 2026-12-18 | 663 | Amina Amar | Not Started | Deployment, transition and closure deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Work Package | P010 | GenAI Knowledge Assistant | WP07 | Project management and governance | 2026-05-04 | 2026-12-18 | 2026-12-20 | 3687.1 | Nicolas Wagner | In Progress | Project management and governance deliverables reviewed and accepted by the project governance body. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M01 | Project kickoff | 2026-05-09 | 2026-05-09 | 2026-05-17 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Project kickoff' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M02 | Design baseline approved | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Design baseline approved' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M03 | Minimum viable release completed | 2026-09-06 | 2026-09-06 | 2026-09-11 | 0 | Nicolas Wagner | Completed | Formal evidence that 'Minimum viable release completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M04 | User acceptance testing completed | 2026-11-07 | 2026-11-07 | 2026-11-07 | 0 | Nicolas Wagner | Forecast On Time | Formal evidence that 'User acceptance testing completed' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M05 | Production go-live / final delivery | 2026-12-09 | 2026-12-09 | 2026-12-09 | 0 | Nicolas Wagner | Forecast On Time | Formal evidence that 'Production go-live / final delivery' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
Milestone | P010 | GenAI Knowledge Assistant | M06 | Project closure accepted | 2026-12-18 | 2026-12-18 | 2026-12-21 | 0 | Nicolas Wagner | Forecast On Time | Formal evidence that 'Project closure accepted' has been achieved and approved. | PROJECT_MANAGEMENT_RESTRICTED | TRUE

## Cost Control
project_id | project_name | project_manager_name | baseline_labor_budget_hours | baseline_labor_budget_eur | baseline_nonlabor_budget_eur | baseline_total_cost_budget_eur | approved_change_cost_eur | adjusted_total_cost_budget_eur | actual_labor_hours_to_date | actual_billable_hours_to_date | actual_labor_cost_to_date_eur | actual_nonlabor_cost_to_date_eur | actual_total_cost_to_date_eur | estimate_to_complete_eur | estimate_at_completion_eur | forecast_cost_variance_eur | planned_completion_pct | actual_completion_pct | planned_value_eur | earned_value_eur | cost_performance_index | schedule_performance_index | forecast_schedule_variance_days | cost_schedule_rag_status | classification | synthetic_record
P001 | LuxHealth Data Platform | Maya Fernandes | 8958.5 | 825580.29 | 112619.4 | 938199.69 | 25000 | 963199.69 | 8179 | 7511.5 | 754131.25 | 95048.5 | 849179.75 | 92694.51 | 941874.26 | 21325.43 | 86 | 84.3 | 828351.73 | 811977.34 | 0.96 | 0.98 | 7 | Amber | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P002 | Sovereign AI Factory | Maya Fernandes | 6500.6 | 573097.14 | 195467.59 | 768564.73 | 36000 | 804564.73 | 5913.5 | 5307.5 | 521965 | 182656.73 | 704621.73 | 67218.22 | 771839.95 | 32724.78 | 92 | 93.5 | 740199.55 | 752268.02 | 1.07 | 1.02 | -6 | Green | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P003 | Core Banking Modernisation | Julien Bernard | 9230.6 | 862549.29 | 158639.16 | 1021188.45 | 36000 | 1057188.45 | 8492.5 | 7884 | 793187.5 | 127039.56 | 920227.06 | 100834.52 | 1021061.58 | 36126.87 | 100 | 88.3 | 1057188.45 | 933497.4 | 1.01 | 0.88 | 39 | Red | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P004 | Smart Mobility Analytics | Julien Bernard | 6640.9 | 495315.43 | 95524.29 | 590839.72 | 36000 | 626839.72 | 5996 | 5481.5 | 447666.25 | 74216.24 | 521882.49 | 71184.99 | 593067.48 | 33772.24 | 82 | 79.8 | 514008.57 | 500218.1 | 0.96 | 0.97 | 9 | Amber | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P005 | Cloud Landing Zone | Sara Khan | 5763.3 | 462430.86 | 101714.72 | 564145.58 | 36000 | 600145.58 | 5237 | 4830.5 | 419803.75 | 91108.06 | 510911.81 | 52165.98 | 563077.79 | 37067.79 | 100 | 93.7 | 600145.58 | 562336.41 | 1.1 | 0.94 | 14 | Amber | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P006 | AML Data Quality | Sara Khan | 4057.3 | 336194.86 | 71566.59 | 407761.45 | 73000 | 480761.45 | 3690.5 | 3230.5 | 306046.25 | 66732.92 | 372779.17 | 36451.95 | 409231.12 | 71530.33 | 100 | 88.2 | 480761.45 | 424031.6 | 1.14 | 0.88 | 32 | Red | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P007 | Cyber Resilience Programme | Nicolas Wagner | 9070.6 | 798743.79 | 92041.18 | 890784.97 | 125000 | 1015784.97 | 8233.5 | 7586 | 725005 | 86793.86 | 811798.86 | 78487.68 | 890286.54 | 125498.43 | 88 | 90.6 | 893890.77 | 920301.18 | 1.13 | 1.03 | -10 | Green | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P008 | Customer 360 Platform | Nicolas Wagner | 3700.8 | 312218.29 | 83090.5 | 395308.79 | 18000 | 413308.79 | 3336 | 2908 | 281141.25 | 66659.6 | 347800.85 | 49364.44 | 397165.29 | 16143.5 | 78 | 76.3 | 322380.86 | 315354.61 | 0.91 | 0.98 | 5 | Amber | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P009 | ERP Integration | Maya Fernandes | 4257.9 | 309888 | 94802.89 | 404690.89 | 48000 | 452690.89 | 3889.5 | 3431 | 283041.25 | 80958.2 | 363999.45 | 41740.85 | 405740.3 | 46950.59 | 100 | 89 | 452690.89 | 402894.89 | 1.11 | 0.89 | 29 | Red | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE
P010 | GenAI Knowledge Assistant | Nicolas Wagner | 3703.3 | 292760.14 | 71195.51 | 363955.65 | 0 | 363955.65 | 3354.5 | 2948 | 266007.5 | 61633.02 | 327640.52 | 38722.7 | 366363.22 | -2407.57 | 74 | 79.6 | 269327.18 | 289708.7 | 0.88 | 1.08 | -18 | Red | PROJECT_MANAGEMENT_RESTRICTED_COST | TRUE

## Utilization
month | employee_id | employee_name | department | job_title | gross_capacity_hours | leave_hours | public_holiday_hours | productive_capacity_hours | client_project_hours | billable_hours | internal_hours | client_utilization_pct | billable_utilization_pct | target_utilization_pct | variance_to_target_pct_points | allocation_status | classification | synthetic_record
2026-01 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 0 | 8 | 152 | 9.5 | 0 | 142.5 | 6.2 | 0 | 10 | -3.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 40 | 0 | 120 | 8 | 0 | 112 | 6.7 | 0 | 10 | -3.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E001 | Sophie Lambert | Finance | Finance Director | 200 | 16 | 0 | 184 | 17 | 0 | 167 | 9.2 | 0 | 10 | -0.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 0 | 8 | 152 | 18 | 0 | 134 | 11.8 | 0 | 10 | 1.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 32 | 16 | 112 | 10.5 | 0 | 99.5 | 9.4 | 0 | 10 | -0.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E001 | Sophie Lambert | Finance | Finance Director | 200 | 0 | 8 | 192 | 25 | 0 | 167 | 13 | 0 | 10 | 3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 24 | 0 | 136 | 15 | 0 | 121 | 11 | 0 | 10 | 1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E001 | Sophie Lambert | Finance | Finance Director | 200 | 8 | 8 | 184 | 25 | 0 | 159 | 13.6 | 0 | 10 | 3.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 0 | 0 | 160 | 18 | 0 | 142 | 11.2 | 0 | 10 | 1.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E001 | Sophie Lambert | Finance | Finance Director | 160 | 0 | 0 | 160 | 16 | 0 | 144 | 10 | 0 | 10 | 0 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E001 | Sophie Lambert | Finance | Finance Director | 200 | 0 | 8 | 192 | 17.5 | 0 | 174.5 | 9.1 | 0 | 10 | -0.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E001 | Sophie Lambert | Finance | Finance Director | 120 | 0 | 16 | 104 | 6 | 0 | 98 | 5.8 | 0 | 10 | -4.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 0 | 8 | 152 | 16 | 0 | 136 | 10.5 | 0 | 10 | 0.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 0 | 0 | 160 | 25.5 | 0 | 134.5 | 15.9 | 0 | 10 | 5.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 200 | 0 | 0 | 200 | 38.5 | 0 | 161.5 | 19.2 | 0 | 10 | 9.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 0 | 8 | 152 | 29.5 | 0 | 122.5 | 19.4 | 0 | 10 | 9.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 16 | 16 | 128 | 23.5 | 0 | 104.5 | 18.4 | 0 | 10 | 8.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 200 | 16 | 8 | 176 | 41.5 | 0 | 134.5 | 23.6 | 0 | 10 | 13.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 48 | 0 | 112 | 24.5 | 0 | 75.5 | 21.9 | 0 | 10 | 11.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 200 | 0 | 8 | 192 | 41.5 | 0 | 150.5 | 21.6 | 0 | 10 | 11.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 24 | 0 | 136 | 30 | 0 | 106 | 22.1 | 0 | 10 | 12.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 160 | 16 | 0 | 144 | 24.5 | 0 | 119.5 | 17 | 0 | 10 | 7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 200 | 0 | 8 | 192 | 29.5 | 0 | 162.5 | 15.4 | 0 | 10 | 5.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E002 | Marc Hoffmann | Finance | Senior Financial Controller | 120 | 0 | 16 | 104 | 11.5 | 0 | 92.5 | 11.1 | 0 | 10 | 1.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 0 | 8 | 152 | 21 | 0 | 131 | 13.8 | 0 | 10 | 3.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 16 | 0 | 144 | 30 | 0 | 114 | 20.8 | 0 | 10 | 10.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E003 | Elena Rossi | Finance | Management Accountant | 200 | 24 | 0 | 176 | 39 | 0 | 129 | 22.2 | 0 | 10 | 12.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 8 | 8 | 144 | 38 | 0 | 106 | 26.4 | 0 | 10 | 16.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 24 | 16 | 120 | 36.5 | 0 | 83.5 | 30.4 | 0 | 10 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E003 | Elena Rossi | Finance | Management Accountant | 200 | 16 | 8 | 176 | 49.5 | 0 | 126.5 | 28.1 | 0 | 10 | 18.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 0 | 0 | 160 | 45.5 | 0 | 114.5 | 28.4 | 0 | 10 | 18.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E003 | Elena Rossi | Finance | Management Accountant | 200 | 16 | 8 | 176 | 51 | 0 | 125 | 29 | 0 | 10 | 19 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 0 | 0 | 160 | 40.5 | 0 | 119.5 | 25.3 | 0 | 10 | 15.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E003 | Elena Rossi | Finance | Management Accountant | 160 | 16 | 0 | 144 | 33 | 0 | 111 | 22.9 | 0 | 10 | 12.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E003 | Elena Rossi | Finance | Management Accountant | 200 | 0 | 8 | 192 | 39 | 0 | 153 | 20.3 | 0 | 10 | 10.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E003 | Elena Rossi | Finance | Management Accountant | 120 | 0 | 16 | 104 | 14 | 0 | 90 | 13.5 | 0 | 10 | 3.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 200 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 0 | 16 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 200 | 40 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 200 | 16 | 8 | 176 | 0 | 0 | 176 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 8 | 0 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 160 | 24 | 0 | 136 | 0 | 0 | 136 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E004 | Thomas Weber | Finance | Payroll & Benefits Specialist | 120 | 16 | 16 | 88 | 0 | 0 | 88 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 0 | 8 | 152 | 16.5 | 0 | 135.5 | 10.9 | 0 | 10 | 0.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 0 | 0 | 160 | 25.5 | 0 | 134.5 | 15.9 | 0 | 10 | 5.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E005 | Nadia Benali | Finance | Financial Analyst | 200 | 24 | 0 | 176 | 32 | 0 | 144 | 18.2 | 0 | 10 | 8.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 16 | 8 | 136 | 26.5 | 0 | 109.5 | 19.5 | 0 | 10 | 9.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 0 | 16 | 144 | 27.5 | 0 | 116.5 | 19.1 | 0 | 10 | 9.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E005 | Nadia Benali | Finance | Financial Analyst | 200 | 16 | 8 | 176 | 40.5 | 0 | 135.5 | 23 | 0 | 10 | 13 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 24 | 0 | 136 | 31.5 | 0 | 104.5 | 23.2 | 0 | 10 | 13.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E005 | Nadia Benali | Finance | Financial Analyst | 200 | 0 | 8 | 192 | 40 | 0 | 152 | 20.8 | 0 | 10 | 10.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 0 | 0 | 160 | 33.5 | 0 | 120.5 | 20.9 | 0 | 10 | 10.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E005 | Nadia Benali | Finance | Financial Analyst | 160 | 16 | 0 | 144 | 27 | 0 | 109 | 18.8 | 0 | 10 | 8.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E005 | Nadia Benali | Finance | Financial Analyst | 200 | 24 | 8 | 168 | 25 | 0 | 143 | 14.9 | 0 | 10 | 4.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E005 | Nadia Benali | Finance | Financial Analyst | 120 | 0 | 16 | 104 | 10 | 0 | 94 | 9.6 | 0 | 10 | -0.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 16 | 8 | 136 | 9.5 | 0 | 122.5 | 7 | 0 | 10 | -3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 0 | 0 | 160 | 16 | 0 | 144 | 10 | 0 | 10 | 0 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E006 | Jean Schmit | Executive | Chief Executive Officer | 200 | 0 | 0 | 200 | 20 | 0 | 180 | 10 | 0 | 10 | 0 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 16 | 8 | 136 | 14 | 0 | 122 | 10.3 | 0 | 10 | 0.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 24 | 16 | 120 | 12.5 | 0 | 107.5 | 10.4 | 0 | 10 | 0.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E006 | Jean Schmit | Executive | Chief Executive Officer | 200 | 16 | 8 | 176 | 18 | 0 | 158 | 10.2 | 0 | 10 | 0.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 0 | 0 | 160 | 16 | 0 | 144 | 10 | 0 | 10 | 0 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E006 | Jean Schmit | Executive | Chief Executive Officer | 200 | 0 | 8 | 192 | 20 | 0 | 172 | 10.4 | 0 | 10 | 0.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 0 | 0 | 160 | 16 | 0 | 144 | 10 | 0 | 10 | 0 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E006 | Jean Schmit | Executive | Chief Executive Officer | 160 | 24 | 0 | 136 | 14 | 0 | 120 | 10.3 | 0 | 10 | 0.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E006 | Jean Schmit | Executive | Chief Executive Officer | 200 | 24 | 8 | 168 | 17 | 0 | 151 | 10.1 | 0 | 10 | 0.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E006 | Jean Schmit | Executive | Chief Executive Officer | 120 | 0 | 16 | 104 | 6 | 0 | 98 | 5.8 | 0 | 10 | -4.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 0 | 8 | 152 | 16.5 | 0 | 135.5 | 10.9 | 0 | 10 | 0.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 0 | 0 | 160 | 25.5 | 0 | 134.5 | 15.9 | 0 | 10 | 5.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E007 | Claire Muller | Executive | Chief Financial Officer | 200 | 24 | 0 | 176 | 31.5 | 0 | 144.5 | 17.9 | 0 | 10 | 7.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 24 | 8 | 128 | 24.5 | 0 | 103.5 | 19.1 | 0 | 10 | 9.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 0 | 16 | 144 | 28.5 | 0 | 115.5 | 19.8 | 0 | 10 | 9.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E007 | Claire Muller | Executive | Chief Financial Officer | 200 | 16 | 8 | 176 | 35.5 | 0 | 140.5 | 20.2 | 0 | 10 | 10.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 8 | 0 | 152 | 32 | 0 | 120 | 21.1 | 0 | 10 | 11.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E007 | Claire Muller | Executive | Chief Financial Officer | 200 | 16 | 8 | 176 | 37.5 | 0 | 138.5 | 21.3 | 0 | 10 | 11.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 0 | 0 | 160 | 30.5 | 0 | 129.5 | 19.1 | 0 | 10 | 9.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E007 | Claire Muller | Executive | Chief Financial Officer | 160 | 0 | 0 | 160 | 26.5 | 0 | 133.5 | 16.6 | 0 | 10 | 6.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E007 | Claire Muller | Executive | Chief Financial Officer | 200 | 16 | 8 | 176 | 26.5 | 0 | 149.5 | 15.1 | 0 | 10 | 5.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E007 | Claire Muller | Executive | Chief Financial Officer | 120 | 16 | 16 | 88 | 8.5 | 0 | 79.5 | 9.7 | 0 | 10 | -0.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 8 | 152 | 13.5 | 0 | 138.5 | 8.9 | 0 | 10 | -1.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 0 | 160 | 24 | 0 | 136 | 15 | 0 | 10 | 5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E008 | Luca Conti | Executive | Chief Technology Officer | 200 | 40 | 0 | 160 | 32.5 | 0 | 127.5 | 20.3 | 0 | 10 | 10.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 40 | 8 | 112 | 23 | 0 | 89 | 20.5 | 0 | 10 | 10.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 16 | 144 | 35 | 0 | 109 | 24.3 | 0 | 10 | 14.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E008 | Luca Conti | Executive | Chief Technology Officer | 200 | 0 | 8 | 192 | 47.5 | 0 | 144.5 | 24.7 | 0 | 10 | 14.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 0 | 160 | 40 | 0 | 120 | 25 | 0 | 10 | 15 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E008 | Luca Conti | Executive | Chief Technology Officer | 200 | 40 | 8 | 152 | 39 | 0 | 113 | 25.7 | 0 | 10 | 15.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 0 | 160 | 40 | 0 | 120 | 25 | 0 | 10 | 15 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E008 | Luca Conti | Executive | Chief Technology Officer | 160 | 0 | 0 | 160 | 40 | 0 | 120 | 25 | 0 | 10 | 15 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E008 | Luca Conti | Executive | Chief Technology Officer | 200 | 0 | 8 | 192 | 48 | 0 | 144 | 25 | 0 | 10 | 15 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E008 | Luca Conti | Executive | Chief Technology Officer | 120 | 0 | 16 | 104 | 20 | 0 | 84 | 19.2 | 0 | 10 | 9.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 0 | 8 | 152 | 18 | 0 | 134 | 11.8 | 0 | 10 | 1.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 0 | 0 | 160 | 24 | 0 | 134 | 15 | 0 | 10 | 5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 200 | 16 | 0 | 184 | 28 | 0 | 152 | 15.2 | 0 | 10 | 5.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 24 | 8 | 128 | 25 | 0 | 103 | 19.5 | 0 | 10 | 9.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 40 | 16 | 104 | 20 | 0 | 84 | 19.2 | 0 | 10 | 9.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 200 | 0 | 8 | 192 | 36.5 | 0 | 155.5 | 19 | 0 | 10 | 9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 0 | 0 | 160 | 30.5 | 0 | 129.5 | 19.1 | 0 | 10 | 9.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 200 | 16 | 8 | 176 | 33 | 0 | 143 | 18.8 | 0 | 10 | 8.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 0 | 0 | 160 | 24.5 | 0 | 135.5 | 15.3 | 0 | 10 | 5.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 160 | 16 | 0 | 144 | 17 | 0 | 127 | 11.8 | 0 | 10 | 1.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 200 | 8 | 8 | 184 | 14.5 | 0 | 169.5 | 7.9 | 0 | 10 | -2.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E009 | Amélie Dubois | Executive | Chief Operating Officer | 120 | 0 | 16 | 104 | 3 | 0 | 101 | 2.9 | 0 | 10 | -7.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E010 | David Martin | Project Management | PMO Director | 160 | 0 | 8 | 152 | 36 | 0 | 116 | 23.7 | 0 | 68 | -44.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E010 | David Martin | Project Management | PMO Director | 160 | 16 | 0 | 144 | 50.5 | 0 | 93.5 | 35.1 | 0 | 68 | -32.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E010 | David Martin | Project Management | PMO Director | 200 | 0 | 0 | 200 | 80 | 0 | 120 | 40 | 0 | 68 | -28 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E010 | David Martin | Project Management | PMO Director | 160 | 24 | 8 | 128 | 55.5 | 0 | 72.5 | 43.4 | 0 | 68 | -24.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E010 | David Martin | Project Management | PMO Director | 160 | 0 | 16 | 144 | 70 | 0 | 74 | 48.6 | 0 | 68 | -19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E010 | David Martin | Project Management | PMO Director | 200 | 0 | 8 | 192 | 95 | 0 | 97 | 49.5 | 0 | 68 | -18.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E010 | David Martin | Project Management | PMO Director | 160 | 40 | 0 | 120 | 60 | 0 | 60 | 50 | 0 | 68 | -18 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E010 | David Martin | Project Management | PMO Director | 200 | 24 | 8 | 168 | 84.5 | 0 | 83.5 | 50.3 | 0 | 68 | -17.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E010 | David Martin | Project Management | PMO Director | 160 | 0 | 0 | 160 | 72 | 0 | 88 | 45 | 0 | 68 | -23 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E010 | David Martin | Project Management | PMO Director | 160 | 16 | 0 | 144 | 58 | 0 | 86 | 40.3 | 0 | 68 | -27.7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E010 | David Martin | Project Management | PMO Director | 200 | 0 | 8 | 192 | 66.5 | 0 | 125.5 | 34.6 | 0 | 68 | -33.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E010 | David Martin | Project Management | PMO Director | 120 | 0 | 16 | 104 | 24 | 0 | 80 | 23.1 | 0 | 68 | -44.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 0 | 8 | 152 | 92 | 92 | 60 | 60.5 | 60.5 | 68 | -7.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 0 | 0 | 160 | 156.5 | 156.5 | 3.5 | 97.8 | 97.8 | 68 | 29.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 200 | 16 | 0 | 184 | 181 | 181 | 4 | 98.4 | 98.4 | 68 | 30.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 0 | 8 | 152 | 151 | 151 | 2 | 99.3 | 99.3 | 68 | 31.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 24 | 16 | 120 | 115.5 | 115.5 | 4.5 | 96.2 | 96.2 | 68 | 28.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 200 | 16 | 8 | 176 | 174.5 | 174.5 | 2.5 | 99.1 | 99.1 | 68 | 31.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 16 | 0 | 144 | 142 | 142 | 2.5 | 98.6 | 98.6 | 68 | 30.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 200 | 0 | 8 | 192 | 191.5 | 191.5 | 0.5 | 99.7 | 99.7 | 68 | 31.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 8 | 0 | 152 | 151 | 151 | 1.5 | 99.3 | 99.3 | 68 | 31.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 160 | 0 | 0 | 160 | 136.5 | 136.5 | 23.5 | 85.3 | 85.3 | 68 | 17.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 200 | 40 | 8 | 152 | 133.5 | 133.5 | 18.5 | 87.8 | 87.8 | 68 | 19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E011 | Maya Fernandes | Project Management | Senior Project Manager | 120 | 0 | 16 | 104 | 71 | 71 | 33 | 68.3 | 68.3 | 68 | 0.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 0 | 8 | 152 | 82.5 | 82.5 | 69.5 | 54.3 | 54.3 | 68 | -13.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 0 | 0 | 160 | 85 | 85 | 77 | 53.1 | 53.1 | 68 | -14.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E012 | Julien Bernard | Project Management | Senior Project Manager | 200 | 16 | 0 | 184 | 180.5 | 180.5 | 3.5 | 98.1 | 98.1 | 68 | 30.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 40 | 8 | 112 | 112 | 112 | 0 | 100 | 100 | 68 | 32 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 0 | 16 | 144 | 142.5 | 142.5 | 1.5 | 99 | 99 | 68 | 31 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E012 | Julien Bernard | Project Management | Senior Project Manager | 200 | 0 | 8 | 192 | 188 | 188 | 4 | 97.9 | 97.9 | 68 | 29.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 0 | 0 | 160 | 160 | 160 | 0 | 100 | 100 | 68 | 32 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E012 | Julien Bernard | Project Management | Senior Project Manager | 200 | 0 | 8 | 192 | 188 | 188 | 4 | 97.9 | 97.9 | 68 | 29.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 16 | 0 | 144 | 142.5 | 142.5 | 1.5 | 99 | 99 | 68 | 31 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E012 | Julien Bernard | Project Management | Senior Project Manager | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 1.5 | 99.1 | 99.1 | 68 | 31.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E012 | Julien Bernard | Project Management | Senior Project Manager | 200 | 40 | 8 | 152 | 147.5 | 147.5 | 8.5 | 97 | 97 | 68 | 29 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E012 | Julien Bernard | Project Management | Senior Project Manager | 120 | 8 | 16 | 96 | 32.5 | 32.5 | 63.5 | 33.9 | 33.9 | 68 | -34.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E013 | Sara Khan | Project Management | Project Manager | 160 | 0 | 8 | 152 | 77.5 | 77.5 | 74.5 | 51 | 51 | 68 | -17 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E013 | Sara Khan | Project Management | Project Manager | 160 | 24 | 0 | 136 | 132 | 132 | 4 | 97.1 | 97.1 | 68 | 29.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E013 | Sara Khan | Project Management | Project Manager | 200 | 24 | 0 | 176 | 174 | 174 | 2 | 98.9 | 98.9 | 68 | 30.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E013 | Sara Khan | Project Management | Project Manager | 160 | 16 | 8 | 136 | 134.5 | 134.5 | 1.5 | 98.9 | 98.9 | 68 | 30.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E013 | Sara Khan | Project Management | Project Manager | 160 | 16 | 16 | 128 | 124.5 | 124.5 | 3.5 | 97.3 | 97.3 | 68 | 29.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E013 | Sara Khan | Project Management | Project Manager | 200 | 16 | 8 | 176 | 173 | 173 | 3 | 98.3 | 98.3 | 68 | 30.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E013 | Sara Khan | Project Management | Project Manager | 160 | 0 | 0 | 160 | 157 | 157 | 3 | 98.1 | 98.1 | 68 | 30.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E013 | Sara Khan | Project Management | Project Manager | 200 | 24 | 8 | 168 | 166.5 | 166.5 | 1.5 | 99.1 | 99.1 | 68 | 31.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E013 | Sara Khan | Project Management | Project Manager | 160 | 0 | 0 | 160 | 82 | 82 | 72 | 51.2 | 51.2 | 68 | -16.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E013 | Sara Khan | Project Management | Project Manager | 160 | 0 | 0 | 160 | 81 | 81 | 79 | 50.6 | 50.6 | 68 | -17.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E013 | Sara Khan | Project Management | Project Manager | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 68 | -68 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E013 | Sara Khan | Project Management | Project Manager | 120 | 0 | 16 | 104 | 0 | 0 | 104 | 0 | 0 | 68 | -68 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 0 | 8 | 152 | 62 | 62 | 90 | 40.8 | 40.8 | 68 | -27.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 16 | 0 | 144 | 73 | 73 | 71 | 50.7 | 50.7 | 68 | -17.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E014 | Nicolas Wagner | Project Management | Project Manager | 200 | 16 | 0 | 184 | 93 | 93 | 91 | 50.5 | 50.5 | 68 | -17.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 24 | 8 | 128 | 104 | 104 | 24 | 81.2 | 81.2 | 68 | 13.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 0 | 16 | 144 | 138.5 | 138.5 | 5.5 | 96.2 | 96.2 | 68 | 28.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E014 | Nicolas Wagner | Project Management | Project Manager | 200 | 0 | 8 | 192 | 188 | 188 | 10 | 97.9 | 97.9 | 68 | 29.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 7.5 | 99.1 | 99.1 | 68 | 31.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E014 | Nicolas Wagner | Project Management | Project Manager | 200 | 24 | 8 | 168 | 166 | 166 | 2 | 98.8 | 98.8 | 68 | 30.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 16 | 0 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 68 | 30.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E014 | Nicolas Wagner | Project Management | Project Manager | 160 | 8 | 0 | 152 | 152 | 152 | 1 | 100 | 100 | 68 | 32 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E014 | Nicolas Wagner | Project Management | Project Manager | 200 | 16 | 8 | 176 | 173.5 | 173.5 | 2.5 | 98.6 | 98.6 | 68 | 30.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E014 | Nicolas Wagner | Project Management | Project Manager | 120 | 0 | 16 | 104 | 78.5 | 78.5 | 19.5 | 75.5 | 75.5 | 68 | 7.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 0 | 8 | 152 | 57.5 | 0 | 94.5 | 37.8 | 0 | 68 | -30.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 24 | 0 | 136 | 77.5 | 0 | 58.5 | 57 | 0 | 68 | -11 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E015 | Inès Petit | Project Management | PMO Analyst | 200 | 0 | 0 | 200 | 128.5 | 0 | 71.5 | 64.2 | 0 | 68 | -3.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 16 | 8 | 136 | 98 | 0 | 38 | 72.1 | 0 | 68 | 4.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 0 | 16 | 144 | 116 | 0 | 28 | 80.6 | 0 | 68 | 12.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E015 | Inès Petit | Project Management | PMO Analyst | 200 | 16 | 8 | 176 | 142.5 | 0 | 33.5 | 81 | 0 | 68 | 13 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 0 | 0 | 160 | 127.5 | 0 | 32.5 | 79.7 | 0 | 68 | 11.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E015 | Inès Petit | Project Management | PMO Analyst | 200 | 24 | 8 | 168 | 136.5 | 0 | 31.5 | 81.2 | 0 | 68 | 13.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 24 | 0 | 136 | 98 | 0 | 38 | 72.1 | 0 | 68 | 4.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E015 | Inès Petit | Project Management | PMO Analyst | 160 | 0 | 0 | 160 | 104 | 0 | 56 | 65 | 0 | 68 | -3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E015 | Inès Petit | Project Management | PMO Analyst | 200 | 16 | 8 | 176 | 101.5 | 0 | 74.5 | 57.7 | 0 | 68 | -10.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E015 | Inès Petit | Project Management | PMO Analyst | 120 | 0 | 16 | 104 | 39.5 | 0 | 64.5 | 38 | 0 | 68 | -30 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 0 | 8 | 152 | 36 | 0 | 116 | 23.7 | 0 | 68 | -44.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 0 | 0 | 160 | 56 | 0 | 104 | 35 | 0 | 68 | -33 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E016 | Olivier Lefevre | Project Management | Resource Manager | 200 | 0 | 0 | 200 | 80 | 0 | 120 | 40 | 0 | 68 | -28 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 24 | 8 | 128 | 58.5 | 0 | 73.5 | 45.7 | 0 | 68 | -22.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 0 | 16 | 144 | 70.5 | 0 | 73.5 | 49 | 0 | 68 | -19 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E016 | Olivier Lefevre | Project Management | Resource Manager | 200 | 32 | 8 | 160 | 79.5 | 0 | 76.5 | 49.7 | 0 | 68 | -18.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 8 | 0 | 152 | 75 | 0 | 77 | 49.3 | 0 | 68 | -18.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E016 | Olivier Lefevre | Project Management | Resource Manager | 200 | 16 | 8 | 176 | 85.5 | 0 | 90.5 | 48.6 | 0 | 68 | -19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 16 | 0 | 144 | 64 | 0 | 80 | 44.4 | 0 | 68 | -23.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E016 | Olivier Lefevre | Project Management | Resource Manager | 160 | 24 | 0 | 136 | 56 | 0 | 80 | 41.2 | 0 | 68 | -26.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E016 | Olivier Lefevre | Project Management | Resource Manager | 200 | 0 | 8 | 192 | 66.5 | 0 | 125.5 | 34.6 | 0 | 68 | -33.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E016 | Olivier Lefevre | Project Management | Resource Manager | 120 | 0 | 16 | 104 | 24 | 0 | 86 | 23.1 | 0 | 68 | -44.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 0 | 8 | 152 | 87.5 | 87.5 | 66.5 | 57.6 | 57.6 | 78 | -20.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 0 | 0 | 160 | 142.5 | 142.5 | 17.5 | 89.1 | 89.1 | 78 | 11.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 200 | 8 | 0 | 192 | 167.5 | 167.5 | 24.5 | 87.2 | 87.2 | 78 | 9.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 24 | 8 | 128 | 110.5 | 110.5 | 17.5 | 86.3 | 86.3 | 78 | 8.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 0 | 16 | 144 | 129.5 | 129.5 | 10.5 | 89.9 | 89.9 | 78 | 11.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 200 | 0 | 8 | 192 | 173.5 | 173.5 | 18.5 | 90.4 | 90.4 | 78 | 12.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 40 | 0 | 120 | 109 | 109 | 11 | 90.8 | 90.8 | 78 | 12.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 200 | 0 | 8 | 192 | 172 | 172 | 14.5 | 89.6 | 89.6 | 78 | 11.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 0 | 0 | 160 | 144.5 | 144.5 | 15.5 | 90.3 | 90.3 | 78 | 12.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 160 | 48 | 0 | 112 | 99 | 99 | 13 | 88.4 | 88.4 | 78 | 10.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 200 | 0 | 8 | 192 | 173.5 | 173.5 | 18.5 | 90.4 | 90.4 | 78 | 12.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E017 | Amina Amar | Data & AI | Principal Data & AI Architect | 120 | 0 | 16 | 104 | 70.5 | 70.5 | 33.5 | 67.8 | 67.8 | 78 | -10.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 0 | 8 | 152 | 104 | 104 | 48 | 68.4 | 68.4 | 78 | -9.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 16 | 0 | 144 | 127 | 127 | 17 | 88.2 | 88.2 | 78 | 10.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 200 | 0 | 0 | 200 | 180.5 | 180.5 | 19.5 | 90.2 | 90.2 | 78 | 12.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 24 | 8 | 128 | 117 | 117 | 11 | 91.4 | 91.4 | 78 | 13.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 0 | 16 | 144 | 133 | 133 | 11 | 92.4 | 92.4 | 78 | 14.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 200 | 0 | 8 | 192 | 176.5 | 176.5 | 15.5 | 91.9 | 91.9 | 78 | 13.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 141.5 | 141.5 | 18.5 | 88.4 | 88.4 | 78 | 10.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 200 | 16 | 8 | 176 | 159.5 | 159.5 | 20.5 | 90.6 | 90.6 | 78 | 12.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 141.5 | 141.5 | 18.5 | 88.4 | 88.4 | 78 | 10.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 160 | 40 | 0 | 120 | 110 | 110 | 7 | 91.7 | 91.7 | 78 | 13.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 200 | 24 | 8 | 168 | 122.5 | 122.5 | 45.5 | 72.9 | 72.9 | 78 | -5.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E018 | Gabriel Simon | Data & AI | Senior Data Architect | 120 | 0 | 16 | 104 | 60.5 | 60.5 | 43.5 | 58.2 | 58.2 | 78 | -19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 24 | 8 | 128 | 0 | 0 | 128 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 8 | 0 | 152 | 126 | 126 | 26 | 82.9 | 82.9 | 78 | 4.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 200 | 16 | 0 | 184 | 155 | 155 | 29 | 84.2 | 84.2 | 78 | 6.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 16 | 8 | 136 | 109.5 | 109.5 | 26.5 | 80.5 | 80.5 | 78 | 2.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 0 | 16 | 144 | 140 | 140 | 4 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 200 | 16 | 8 | 176 | 173.5 | 173.5 | 2.5 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 24 | 0 | 136 | 131 | 131 | 5 | 96.3 | 96.3 | 78 | 18.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 200 | 0 | 8 | 192 | 189.5 | 189.5 | 2.5 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 0 | 0 | 160 | 160 | 160 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 160 | 16 | 0 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 200 | 0 | 8 | 192 | 190.5 | 190.5 | 1.5 | 99.2 | 99.2 | 78 | 21.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E019 | Eva Moreau | Data & AI | Senior AI Engineer | 120 | 0 | 16 | 104 | 79 | 79 | 25 | 76 | 76 | 78 | -2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 0 | 8 | 152 | 102 | 102 | 50 | 67.1 | 67.1 | 78 | -10.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 8 | 0 | 152 | 150.5 | 150.5 | 1.5 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E020 | Antoine Robert | Data & AI | Data Engineer | 200 | 0 | 0 | 200 | 198.5 | 198.5 | 1.5 | 99.2 | 99.2 | 78 | 21.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 0 | 8 | 152 | 146 | 146 | 6 | 96.1 | 96.1 | 78 | 18.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 16 | 16 | 128 | 125.5 | 125.5 | 2.5 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E020 | Antoine Robert | Data & AI | Data Engineer | 200 | 0 | 8 | 192 | 185.5 | 185.5 | 6.5 | 96.6 | 96.6 | 78 | 18.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 0 | 0 | 160 | 157.5 | 157.5 | 2.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E020 | Antoine Robert | Data & AI | Data Engineer | 200 | 40 | 8 | 152 | 149 | 149 | 3 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 24 | 0 | 136 | 131.5 | 131.5 | 4.5 | 96.7 | 96.7 | 78 | 18.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E020 | Antoine Robert | Data & AI | Data Engineer | 160 | 16 | 0 | 144 | 138 | 138 | 6 | 95.8 | 95.8 | 78 | 17.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E020 | Antoine Robert | Data & AI | Data Engineer | 200 | 16 | 8 | 176 | 126 | 126 | 54 | 71.6 | 71.6 | 78 | -6.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E020 | Antoine Robert | Data & AI | Data Engineer | 120 | 0 | 16 | 104 | 56.5 | 56.5 | 47.5 | 54.3 | 54.3 | 78 | -23.7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 0 | 0 | 160 | 130.5 | 130.5 | 29.5 | 81.6 | 81.6 | 78 | 3.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E021 | Lea Nguyen | Data & AI | ML Engineer | 200 | 0 | 0 | 200 | 157 | 157 | 43 | 78.5 | 78.5 | 78 | 0.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 16 | 8 | 136 | 108.5 | 108.5 | 27.5 | 79.8 | 79.8 | 78 | 1.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 24 | 16 | 120 | 117 | 117 | 3 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E021 | Lea Nguyen | Data & AI | ML Engineer | 200 | 16 | 8 | 176 | 169.5 | 169.5 | 6.5 | 96.3 | 96.3 | 78 | 18.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 16 | 0 | 144 | 139 | 139 | 5 | 96.5 | 96.5 | 78 | 18.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E021 | Lea Nguyen | Data & AI | ML Engineer | 200 | 40 | 8 | 152 | 149.5 | 149.5 | 2 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 8 | 0 | 152 | 151 | 151 | 1 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E021 | Lea Nguyen | Data & AI | ML Engineer | 160 | 0 | 0 | 160 | 154.5 | 154.5 | 5.5 | 96.6 | 96.6 | 78 | 18.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E021 | Lea Nguyen | Data & AI | ML Engineer | 200 | 0 | 8 | 192 | 189.5 | 189.5 | 2.5 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E021 | Lea Nguyen | Data & AI | ML Engineer | 120 | 0 | 16 | 104 | 80 | 80 | 24 | 76.9 | 76.9 | 78 | -1.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E022 | Hugo Laurent | Data & AI | Data Scientist | 200 | 16 | 0 | 184 | 128 | 128 | 56 | 69.6 | 69.6 | 78 | -8.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 32 | 8 | 120 | 84 | 84 | 36 | 70 | 70 | 78 | -8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 24 | 16 | 120 | 117 | 117 | 3 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E022 | Hugo Laurent | Data & AI | Data Scientist | 200 | 0 | 8 | 192 | 191.5 | 191.5 | 4.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 16 | 0 | 144 | 141 | 141 | 3 | 97.9 | 97.9 | 78 | 19.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E022 | Hugo Laurent | Data & AI | Data Scientist | 200 | 0 | 8 | 192 | 188.5 | 188.5 | 3.5 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 16 | 0 | 144 | 139.5 | 139.5 | 4.5 | 96.9 | 96.9 | 78 | 18.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E022 | Hugo Laurent | Data & AI | Data Scientist | 160 | 0 | 0 | 160 | 160 | 160 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E022 | Hugo Laurent | Data & AI | Data Scientist | 200 | 0 | 8 | 192 | 185.5 | 185.5 | 6.5 | 96.6 | 96.6 | 78 | 18.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E022 | Hugo Laurent | Data & AI | Data Scientist | 120 | 0 | 16 | 104 | 79.5 | 79.5 | 24.5 | 76.4 | 76.4 | 78 | -1.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 0 | 8 | 152 | 146.5 | 146.5 | 5.5 | 96.4 | 96.4 | 78 | 18.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 0 | 0 | 160 | 155 | 155 | 5 | 96.9 | 96.9 | 78 | 18.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 200 | 32 | 0 | 168 | 165 | 165 | 3 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 24 | 8 | 128 | 121.5 | 121.5 | 6.5 | 94.9 | 94.9 | 78 | 16.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 32 | 16 | 112 | 112 | 112 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 200 | 0 | 8 | 192 | 190 | 190 | 2 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 0 | 0 | 160 | 153.5 | 153.5 | 6.5 | 95.9 | 95.9 | 78 | 17.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 200 | 0 | 8 | 192 | 188 | 188 | 8 | 97.9 | 97.9 | 78 | 19.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 0 | 0 | 160 | 33 | 33 | 127 | 20.6 | 20.6 | 78 | -57.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 160 | 16 | 0 | 144 | 27.5 | 27.5 | 116.5 | 19.1 | 19.1 | 78 | -58.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 200 | 16 | 8 | 176 | 36.5 | 36.5 | 139.5 | 20.7 | 20.7 | 78 | -57.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E023 | Mila Costa | Cloud & Platform | Cloud Architect | 120 | 0 | 16 | 104 | 17 | 17 | 87 | 16.3 | 16.3 | 78 | -61.7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 0 | 8 | 152 | 121.5 | 121.5 | 30.5 | 79.9 | 79.9 | 78 | 1.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 157 | 157 | 3 | 98.1 | 98.1 | 78 | 20.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 200 | 0 | 0 | 200 | 197 | 197 | 3 | 98.5 | 98.5 | 78 | 20.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 16 | 8 | 136 | 130 | 130 | 4.5 | 95.6 | 95.6 | 78 | 17.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 0 | 16 | 144 | 139 | 139 | 5 | 96.5 | 96.5 | 78 | 18.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 200 | 8 | 8 | 184 | 181.5 | 181.5 | 2.5 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 40 | 0 | 120 | 115 | 115 | 5 | 95.8 | 95.8 | 78 | 17.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 200 | 40 | 8 | 152 | 149.5 | 149.5 | 6.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 16 | 0 | 144 | 28.5 | 28.5 | 115.5 | 19.8 | 19.8 | 78 | -58.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 30.5 | 30.5 | 129.5 | 19.1 | 19.1 | 78 | -58.9 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 200 | 0 | 8 | 192 | 37.5 | 37.5 | 154.5 | 19.5 | 19.5 | 78 | -58.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E024 | Louis Fontaine | Cloud & Platform | DevOps Engineer | 120 | 0 | 16 | 104 | 15.5 | 15.5 | 88.5 | 14.9 | 14.9 | 78 | -63.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 0 | 8 | 152 | 152 | 152 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 0 | 0 | 160 | 160 | 160 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 200 | 0 | 0 | 200 | 195 | 195 | 5 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 0 | 8 | 152 | 150.5 | 150.5 | 1.5 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 24 | 16 | 120 | 120 | 120 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 200 | 24 | 8 | 168 | 166 | 166 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 16 | 0 | 144 | 144 | 144 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 200 | 16 | 8 | 176 | 171.5 | 171.5 | 4.5 | 97.4 | 97.4 | 78 | 19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 0 | 0 | 160 | 49.5 | 49.5 | 110.5 | 30.9 | 30.9 | 78 | -47.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 200 | 24 | 8 | 168 | 0 | 0 | 168 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E025 | Camille Garcia | Cloud & Platform | Platform Engineer | 120 | 0 | 16 | 104 | 0 | 0 | 104 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 0 | 8 | 152 | 138.5 | 138.5 | 7.5 | 91.1 | 91.1 | 78 | 13.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 0 | 0 | 160 | 158 | 158 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E026 | Noah Durand | Cybersecurity | Security Architect | 200 | 16 | 0 | 184 | 180 | 180 | 4 | 97.8 | 97.8 | 78 | 19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 8 | 8 | 144 | 142.5 | 142.5 | 6 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 0 | 16 | 144 | 141 | 141 | 3.5 | 97.9 | 97.9 | 78 | 19.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E026 | Noah Durand | Cybersecurity | Security Architect | 200 | 40 | 8 | 152 | 147 | 147 | 5 | 96.7 | 96.7 | 78 | 18.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E026 | Noah Durand | Cybersecurity | Security Architect | 200 | 16 | 8 | 176 | 172.5 | 172.5 | 4 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 16 | 0 | 144 | 143.5 | 143.5 | 1.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E026 | Noah Durand | Cybersecurity | Security Architect | 160 | 0 | 0 | 160 | 156 | 156 | 4 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E026 | Noah Durand | Cybersecurity | Security Architect | 200 | 0 | 8 | 192 | 188.5 | 188.5 | 4 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E026 | Noah Durand | Cybersecurity | Security Architect | 120 | 24 | 16 | 80 | 32 | 32 | 48 | 40 | 40 | 78 | -38 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 8 | 8 | 144 | 104.5 | 104.5 | 37.5 | 72.6 | 72.6 | 78 | -5.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 0 | 0 | 160 | 158 | 158 | 0.5 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 200 | 16 | 0 | 184 | 181 | 181 | 3 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 0 | 8 | 152 | 150 | 150 | 2.5 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 0 | 16 | 144 | 144 | 144 | 0.5 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 200 | 0 | 8 | 192 | 191 | 191 | 2 | 99.5 | 99.5 | 78 | 21.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 16 | 0 | 144 | 142 | 142 | 4.5 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 200 | 56 | 8 | 136 | 135.5 | 135.5 | 1 | 99.6 | 99.6 | 78 | 21.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 24 | 0 | 136 | 82 | 82 | 54 | 60.3 | 60.3 | 78 | -17.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 160 | 0 | 0 | 160 | 94.5 | 94.5 | 59.5 | 59.1 | 59.1 | 78 | -18.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 200 | 0 | 8 | 192 | 116 | 116 | 76 | 60.4 | 60.4 | 78 | -17.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E027 | Emma Lopez | Cybersecurity | Security Engineer | 120 | 0 | 16 | 104 | 46.5 | 46.5 | 57.5 | 44.7 | 44.7 | 78 | -33.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 8 | 152 | 106 | 106 | 46 | 69.7 | 69.7 | 78 | -8.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 159.5 | 159.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 200 | 24 | 0 | 176 | 173 | 173 | 3 | 98.3 | 98.3 | 78 | 20.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 8 | 152 | 148.5 | 148.5 | 3.5 | 97.7 | 97.7 | 78 | 19.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 16 | 144 | 142.5 | 142.5 | 1.5 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 200 | 24 | 8 | 168 | 166.5 | 166.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 157.5 | 157.5 | 3 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 200 | 16 | 8 | 176 | 173.5 | 173.5 | 2.5 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 40 | 0 | 120 | 120.5 | 120.5 | 0 | 100.4 | 100.4 | 78 | 22.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 157 | 157 | 3 | 98.1 | 98.1 | 78 | 20.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 200 | 16 | 8 | 176 | 121.5 | 121.5 | 54.5 | 69 | 69 | 78 | -9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E028 | Arthur Mercier | Consulting | Senior Business Consultant | 120 | 0 | 16 | 104 | 38 | 38 | 66 | 36.5 | 36.5 | 78 | -41.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 0 | 0 | 160 | 65.5 | 65.5 | 94.5 | 40.9 | 40.9 | 78 | -37.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E029 | Chloé Diallo | Consulting | Business Consultant | 200 | 16 | 0 | 184 | 180.5 | 180.5 | 3.5 | 98.1 | 98.1 | 78 | 20.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 0 | 8 | 152 | 150.5 | 150.5 | 0 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 24 | 16 | 120 | 119.5 | 119.5 | 0.5 | 99.6 | 99.6 | 78 | 21.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E029 | Chloé Diallo | Consulting | Business Consultant | 200 | 8 | 8 | 184 | 178.5 | 178.5 | 5.5 | 97 | 97 | 78 | 19 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 0 | 0 | 160 | 157.5 | 157.5 | 2.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E029 | Chloé Diallo | Consulting | Business Consultant | 200 | 16 | 8 | 176 | 174 | 174 | 2 | 98.9 | 98.9 | 78 | 20.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 16 | 0 | 144 | 141.5 | 141.5 | 2.5 | 98.3 | 98.3 | 78 | 20.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E029 | Chloé Diallo | Consulting | Business Consultant | 160 | 16 | 0 | 144 | 140 | 140 | 4 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E029 | Chloé Diallo | Consulting | Business Consultant | 200 | 0 | 8 | 192 | 116.5 | 116.5 | 75.5 | 60.7 | 60.7 | 78 | -17.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E029 | Chloé Diallo | Consulting | Business Consultant | 120 | 24 | 16 | 80 | 36 | 36 | 44 | 45 | 45 | 78 | -33 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 8 | 152 | 151.5 | 151.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 0 | 160 | 156.5 | 156.5 | 3.5 | 97.8 | 97.8 | 78 | 19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 200 | 32 | 0 | 168 | 168.5 | 168.5 | 0 | 100.3 | 100.3 | 78 | 22.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 8 | 152 | 149 | 149 | 3 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 16 | 144 | 140 | 140 | 4.5 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 200 | 8 | 8 | 184 | 181 | 181 | 3 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 0 | 160 | 157 | 157 | 2.5 | 98.1 | 98.1 | 78 | 20.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 200 | 48 | 8 | 144 | 141 | 141 | 3 | 97.9 | 97.9 | 78 | 19.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 32 | 0 | 128 | 126 | 126 | 2 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 160 | 0 | 0 | 160 | 117 | 117 | 43 | 73.1 | 73.1 | 78 | -4.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 200 | 0 | 8 | 192 | 130.5 | 130.5 | 61.5 | 68 | 68 | 78 | -10 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E030 | Rayan Fischer | Applications | Senior Software Engineer | 120 | 0 | 16 | 104 | 16 | 16 | 88 | 15.4 | 15.4 | 78 | -62.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 16 | 8 | 136 | 109 | 109 | 27 | 80.1 | 80.1 | 78 | 2.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 16 | 0 | 144 | 114.5 | 114.5 | 29.5 | 79.5 | 79.5 | 78 | 1.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E031 | Lucie Pereira | Applications | Software Engineer | 200 | 24 | 0 | 176 | 173.5 | 173.5 | 3 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 16 | 8 | 136 | 132 | 132 | 4.5 | 97.1 | 97.1 | 78 | 19.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 0 | 16 | 144 | 143.5 | 143.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E031 | Lucie Pereira | Applications | Software Engineer | 200 | 16 | 8 | 176 | 174.5 | 174.5 | 2 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 24 | 0 | 136 | 131.5 | 131.5 | 4.5 | 96.7 | 96.7 | 78 | 18.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E031 | Lucie Pereira | Applications | Software Engineer | 200 | 8 | 8 | 184 | 181.5 | 181.5 | 2.5 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 0 | 0 | 160 | 158 | 158 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E031 | Lucie Pereira | Applications | Software Engineer | 160 | 0 | 0 | 160 | 112.5 | 112.5 | 47.5 | 70.3 | 70.3 | 78 | -7.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E031 | Lucie Pereira | Applications | Software Engineer | 200 | 0 | 8 | 192 | 132 | 132 | 60 | 68.8 | 68.8 | 78 | -9.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E031 | Lucie Pereira | Applications | Software Engineer | 120 | 0 | 16 | 104 | 55 | 55 | 35 | 52.9 | 52.9 | 78 | -25.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 0 | 8 | 152 | 104.5 | 104.5 | 49.5 | 68.8 | 68.8 | 78 | -9.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 16 | 0 | 144 | 102 | 102 | 48 | 70.8 | 70.8 | 78 | -7.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E032 | Maxime Richard | Applications | QA Engineer | 200 | 0 | 0 | 200 | 136 | 136 | 66 | 68 | 68 | 78 | -10 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 0 | 8 | 152 | 104.5 | 104.5 | 47.5 | 68.8 | 68.8 | 78 | -9.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 16 | 16 | 128 | 128 | 128 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E032 | Maxime Richard | Applications | QA Engineer | 200 | 24 | 8 | 168 | 165.5 | 165.5 | 3 | 98.5 | 98.5 | 78 | 20.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 16 | 0 | 144 | 144 | 144 | 0.5 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E032 | Maxime Richard | Applications | QA Engineer | 200 | 24 | 8 | 168 | 167 | 167 | 2 | 99.4 | 99.4 | 78 | 21.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 0 | 0 | 160 | 158 | 158 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E032 | Maxime Richard | Applications | QA Engineer | 160 | 0 | 0 | 160 | 117 | 117 | 43 | 73.1 | 73.1 | 78 | -4.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E032 | Maxime Richard | Applications | QA Engineer | 200 | 16 | 8 | 176 | 119.5 | 119.5 | 56.5 | 67.9 | 67.9 | 78 | -10.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E032 | Maxime Richard | Applications | QA Engineer | 120 | 8 | 16 | 96 | 22 | 22 | 74 | 22.9 | 22.9 | 78 | -55.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E033 | Aya Bauer | Sales | Account Director | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 20 | -20 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E033 | Aya Bauer | Sales | Account Director | 160 | 0 | 0 | 160 | 15.5 | 15.5 | 140.5 | 9.7 | 9.7 | 20 | -10.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E033 | Aya Bauer | Sales | Account Director | 200 | 16 | 0 | 184 | 19.5 | 19.5 | 164.5 | 10.6 | 10.6 | 20 | -9.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E033 | Aya Bauer | Sales | Account Director | 160 | 0 | 8 | 152 | 16 | 16 | 128 | 10.5 | 10.5 | 20 | -9.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E033 | Aya Bauer | Sales | Account Director | 160 | 16 | 16 | 128 | 26.5 | 26.5 | 101.5 | 20.7 | 20.7 | 20 | 0.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E033 | Aya Bauer | Sales | Account Director | 200 | 16 | 8 | 176 | 35.5 | 35.5 | 140.5 | 20.2 | 20.2 | 20 | 0.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E033 | Aya Bauer | Sales | Account Director | 160 | 0 | 0 | 160 | 31 | 31 | 129 | 19.4 | 19.4 | 20 | -0.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E033 | Aya Bauer | Sales | Account Director | 200 | 0 | 8 | 192 | 38.5 | 38.5 | 153.5 | 20.1 | 20.1 | 20 | 0.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E033 | Aya Bauer | Sales | Account Director | 160 | 0 | 0 | 160 | 32 | 32 | 128 | 20 | 20 | 20 | 0 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E033 | Aya Bauer | Sales | Account Director | 160 | 16 | 0 | 144 | 28.5 | 28.5 | 115.5 | 19.8 | 19.8 | 20 | -0.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E033 | Aya Bauer | Sales | Account Director | 200 | 32 | 8 | 160 | 31.5 | 31.5 | 128.5 | 19.7 | 19.7 | 20 | -0.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E033 | Aya Bauer | Sales | Account Director | 120 | 24 | 16 | 80 | 11.5 | 11.5 | 68.5 | 14.4 | 14.4 | 20 | -5.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E034 | Victor Renard | Sales | Account Manager | 160 | 0 | 8 | 152 | 16.5 | 16.5 | 135.5 | 10.9 | 10.9 | 20 | -9.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E034 | Victor Renard | Sales | Account Manager | 160 | 40 | 0 | 120 | 12.5 | 12.5 | 107.5 | 10.4 | 10.4 | 20 | -9.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E034 | Victor Renard | Sales | Account Manager | 200 | 0 | 0 | 200 | 19 | 19 | 181 | 9.5 | 9.5 | 20 | -10.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E034 | Victor Renard | Sales | Account Manager | 160 | 0 | 8 | 152 | 29.5 | 29.5 | 122.5 | 19.4 | 19.4 | 20 | -0.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E034 | Victor Renard | Sales | Account Manager | 160 | 0 | 16 | 144 | 29.5 | 29.5 | 114.5 | 20.5 | 20.5 | 20 | 0.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E034 | Victor Renard | Sales | Account Manager | 200 | 24 | 8 | 168 | 34.5 | 34.5 | 133.5 | 20.5 | 20.5 | 20 | 0.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E034 | Victor Renard | Sales | Account Manager | 160 | 0 | 0 | 160 | 32 | 32 | 128 | 20 | 20 | 20 | 0 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E034 | Victor Renard | Sales | Account Manager | 200 | 16 | 8 | 176 | 35.5 | 35.5 | 140.5 | 20.2 | 20.2 | 20 | 0.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E034 | Victor Renard | Sales | Account Manager | 160 | 16 | 0 | 144 | 28 | 28 | 116 | 19.4 | 19.4 | 20 | -0.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E034 | Victor Renard | Sales | Account Manager | 160 | 0 | 0 | 160 | 33 | 33 | 127 | 20.6 | 20.6 | 20 | 0.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E034 | Victor Renard | Sales | Account Manager | 200 | 8 | 8 | 184 | 36.5 | 36.5 | 147.5 | 19.8 | 19.8 | 20 | -0.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E034 | Victor Renard | Sales | Account Manager | 120 | 16 | 16 | 88 | 13 | 13 | 75 | 14.8 | 14.8 | 20 | -5.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E035 | Alice Meier | HR | HR Business Partner | 160 | 24 | 8 | 128 | 0 | 0 | 128 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E035 | Alice Meier | HR | HR Business Partner | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E035 | Alice Meier | HR | HR Business Partner | 200 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E035 | Alice Meier | HR | HR Business Partner | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E035 | Alice Meier | HR | HR Business Partner | 160 | 0 | 16 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E035 | Alice Meier | HR | HR Business Partner | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E035 | Alice Meier | HR | HR Business Partner | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E035 | Alice Meier | HR | HR Business Partner | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E035 | Alice Meier | HR | HR Business Partner | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E035 | Alice Meier | HR | HR Business Partner | 160 | 32 | 0 | 128 | 0 | 0 | 128 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E035 | Alice Meier | HR | HR Business Partner | 200 | 32 | 8 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E035 | Alice Meier | HR | HR Business Partner | 120 | 16 | 16 | 88 | 0 | 0 | 88 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 24 | 0 | 136 | 0 | 0 | 136 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 200 | 16 | 0 | 184 | 0 | 0 | 184 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 0 | 16 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 200 | 40 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 0 | 0 | 160 | 0 | 0 | 156 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 24 | 0 | 136 | 0 | 0 | 136 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 200 | 0 | 8 | 192 | 0 | 0 | 192 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E036 | Nathan Cohen | HR | Talent Acquisition Specialist | 120 | 0 | 16 | 104 | 0 | 0 | 98 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E037 | Lina Gomes | Operations | Office & Operations Manager | 200 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 32 | 8 | 120 | 0 | 0 | 120 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 0 | 16 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E037 | Lina Gomes | Operations | Office & Operations Manager | 200 | 32 | 8 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E037 | Lina Gomes | Operations | Office & Operations Manager | 200 | 0 | 8 | 192 | 0 | 0 | 184 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 16 | 0 | 144 | 0 | 0 | 136 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E037 | Lina Gomes | Operations | Office & Operations Manager | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E037 | Lina Gomes | Operations | Office & Operations Manager | 200 | 24 | 8 | 168 | 0 | 0 | 168 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E037 | Lina Gomes | Operations | Office & Operations Manager | 120 | 0 | 16 | 104 | 0 | 0 | 104 | 0 | 0 | 10 | -10 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 16 | 8 | 136 | 79.5 | 79.5 | 56.5 | 58.5 | 58.5 | 78 | -19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 0 | 0 | 160 | 99 | 99 | 61 | 61.9 | 61.9 | 78 | -16.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 200 | 0 | 0 | 200 | 137 | 137 | 63 | 68.5 | 68.5 | 78 | -9.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 8 | 8 | 144 | 143.5 | 143.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 0 | 16 | 144 | 143.5 | 143.5 | 1 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 200 | 16 | 8 | 176 | 172 | 172 | 4 | 97.7 | 97.7 | 78 | 19.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 16 | 0 | 144 | 142.5 | 142.5 | 1.5 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 200 | 40 | 8 | 152 | 148.5 | 148.5 | 3.5 | 97.7 | 97.7 | 78 | 19.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 0 | 0 | 160 | 158 | 158 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 160 | 0 | 0 | 160 | 156.5 | 156.5 | 9.5 | 97.8 | 97.8 | 78 | 19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 200 | 24 | 8 | 168 | 163.5 | 163.5 | 6.5 | 97.3 | 97.3 | 78 | 19.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E038 | Paul Lemoine | Data & AI | Principal Data & AI Architect | 120 | 0 | 16 | 104 | 31.5 | 31.5 | 72.5 | 30.3 | 30.3 | 78 | -47.7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 8 | 152 | 106 | 106 | 46 | 69.7 | 69.7 | 78 | -8.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 118.5 | 118.5 | 41.5 | 74.1 | 74.1 | 78 | -3.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E039 | Jade Santos | Data & AI | Senior Data Architect | 200 | 8 | 0 | 192 | 136.5 | 136.5 | 55.5 | 71.1 | 71.1 | 78 | -6.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 16 | 8 | 136 | 134 | 134 | 2 | 98.5 | 98.5 | 78 | 20.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 16 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E039 | Jade Santos | Data & AI | Senior Data Architect | 200 | 64 | 8 | 128 | 128 | 128 | 6 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 159 | 159 | 1 | 99.4 | 99.4 | 78 | 21.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E039 | Jade Santos | Data & AI | Senior Data Architect | 200 | 0 | 8 | 192 | 189.5 | 189.5 | 2.5 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 155 | 155 | 5 | 96.9 | 96.9 | 78 | 18.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E039 | Jade Santos | Data & AI | Senior Data Architect | 160 | 0 | 0 | 160 | 155.5 | 155.5 | 4.5 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E039 | Jade Santos | Data & AI | Senior Data Architect | 200 | 16 | 8 | 176 | 172.5 | 172.5 | 3.5 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E039 | Jade Santos | Data & AI | Senior Data Architect | 120 | 16 | 16 | 88 | 19.5 | 19.5 | 68.5 | 22.2 | 22.2 | 78 | -55.8 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 16 | 0 | 144 | 0 | 0 | 144 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 200 | 24 | 0 | 176 | 0 | 0 | 178 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 24 | 8 | 128 | 62 | 62 | 58 | 48.4 | 48.4 | 78 | -29.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 0 | 16 | 144 | 144 | 144 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 200 | 16 | 8 | 176 | 176 | 176 | 2 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 16 | 0 | 144 | 144 | 144 | 0 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 200 | 8 | 8 | 184 | 177.5 | 177.5 | 6.5 | 96.5 | 96.5 | 78 | 18.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 0 | 0 | 160 | 156 | 156 | 4 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 160 | 16 | 0 | 144 | 140.5 | 140.5 | 7.5 | 97.6 | 97.6 | 78 | 19.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 200 | 0 | 8 | 192 | 187 | 187 | 9 | 97.4 | 97.4 | 78 | 19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E040 | Adam Klein | Data & AI | Senior AI Engineer | 120 | 0 | 16 | 104 | 80 | 80 | 24 | 76.9 | 76.9 | 78 | -1.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 0 | 8 | 152 | 72 | 72 | 80 | 47.4 | 47.4 | 78 | -30.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 32 | 0 | 128 | 64.5 | 64.5 | 63.5 | 50.4 | 50.4 | 78 | -27.6 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E041 | Zoé Marques | Data & AI | Data Engineer | 200 | 0 | 0 | 200 | 164 | 164 | 36 | 82 | 82 | 78 | 4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 24 | 8 | 128 | 125.5 | 125.5 | 2.5 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 16 | 16 | 128 | 125 | 125 | 3 | 97.7 | 97.7 | 78 | 19.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E041 | Zoé Marques | Data & AI | Data Engineer | 200 | 0 | 8 | 192 | 191.5 | 191.5 | 1 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 16 | 0 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E041 | Zoé Marques | Data & AI | Data Engineer | 200 | 0 | 8 | 192 | 189.5 | 189.5 | 2.5 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 0 | 0 | 160 | 154 | 154 | 6 | 96.2 | 96.2 | 78 | 18.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E041 | Zoé Marques | Data & AI | Data Engineer | 160 | 24 | 0 | 136 | 133.5 | 133.5 | 2.5 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E041 | Zoé Marques | Data & AI | Data Engineer | 200 | 0 | 8 | 192 | 186.5 | 186.5 | 5.5 | 97.1 | 97.1 | 78 | 19.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E041 | Zoé Marques | Data & AI | Data Engineer | 120 | 8 | 16 | 96 | 36.5 | 36.5 | 53.5 | 38 | 38 | 78 | -40 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E042 | Samuel Jung | Data & AI | ML Engineer | 200 | 16 | 0 | 184 | 93.5 | 93.5 | 90.5 | 50.8 | 50.8 | 78 | -27.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 0 | 8 | 152 | 73 | 73 | 79 | 48 | 48 | 78 | -30 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 24 | 16 | 120 | 117 | 117 | 3 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E042 | Samuel Jung | Data & AI | ML Engineer | 200 | 32 | 8 | 160 | 157.5 | 157.5 | 1.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 24 | 0 | 136 | 132.5 | 132.5 | 3.5 | 97.4 | 97.4 | 78 | 19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E042 | Samuel Jung | Data & AI | ML Engineer | 200 | 0 | 8 | 192 | 190 | 190 | 2 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 8 | 0 | 152 | 149.5 | 149.5 | 2.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E042 | Samuel Jung | Data & AI | ML Engineer | 160 | 0 | 0 | 160 | 156.5 | 156.5 | 3.5 | 97.8 | 97.8 | 78 | 19.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E042 | Samuel Jung | Data & AI | ML Engineer | 200 | 0 | 8 | 192 | 190 | 190 | 2 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E042 | Samuel Jung | Data & AI | ML Engineer | 120 | 16 | 16 | 88 | 64 | 64 | 24 | 72.7 | 72.7 | 78 | -5.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 0 | 8 | 152 | 0 | 0 | 152 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 0 | 0 | 160 | 0 | 0 | 158 | 0 | 0 | 78 | -78 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E043 | Manon Franco | Data & AI | Data Scientist | 200 | 0 | 0 | 200 | 119.5 | 119.5 | 80.5 | 59.8 | 59.8 | 78 | -18.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 0 | 8 | 152 | 120.5 | 120.5 | 31.5 | 79.3 | 79.3 | 78 | 1.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 0 | 16 | 144 | 141 | 141 | 3 | 97.9 | 97.9 | 78 | 19.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E043 | Manon Franco | Data & AI | Data Scientist | 200 | 48 | 8 | 144 | 144.5 | 144.5 | 0 | 100.3 | 100.3 | 78 | 22.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 16 | 0 | 144 | 143 | 143 | 1.5 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E043 | Manon Franco | Data & AI | Data Scientist | 200 | 0 | 8 | 192 | 189 | 189 | 4 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 40 | 0 | 120 | 120.5 | 120.5 | 0.5 | 100.4 | 100.4 | 78 | 22.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E043 | Manon Franco | Data & AI | Data Scientist | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E043 | Manon Franco | Data & AI | Data Scientist | 200 | 16 | 8 | 176 | 171 | 171 | 5 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E043 | Manon Franco | Data & AI | Data Scientist | 120 | 0 | 16 | 104 | 79.5 | 79.5 | 25 | 76.4 | 76.4 | 78 | -1.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 0 | 8 | 152 | 107.5 | 107.5 | 44.5 | 70.7 | 70.7 | 78 | -7.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 16 | 0 | 144 | 113.5 | 113.5 | 22.5 | 78.8 | 78.8 | 78 | 0.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 200 | 16 | 0 | 184 | 183.5 | 183.5 | 1 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 0 | 8 | 152 | 151 | 151 | 3 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 0 | 16 | 144 | 143.5 | 143.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 200 | 48 | 8 | 144 | 143 | 143 | 1 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 16 | 0 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 200 | 16 | 8 | 176 | 174 | 174 | 6.5 | 98.9 | 98.9 | 78 | 20.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 0 | 0 | 160 | 113.5 | 113.5 | 46.5 | 70.9 | 70.9 | 78 | -7.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 160 | 0 | 0 | 160 | 110.5 | 110.5 | 49.5 | 69.1 | 69.1 | 78 | -8.9 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 200 | 8 | 8 | 184 | 125.5 | 125.5 | 58.5 | 68.2 | 68.2 | 78 | -9.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E044 | Yanis Vidal | Cloud & Platform | Cloud Architect | 120 | 0 | 16 | 104 | 56.5 | 56.5 | 47.5 | 54.3 | 54.3 | 78 | -23.7 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 0 | 8 | 152 | 91.5 | 91.5 | 60.5 | 60.2 | 60.2 | 78 | -17.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 154.5 | 154.5 | 5.5 | 96.6 | 96.6 | 78 | 18.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 200 | 32 | 0 | 168 | 165 | 165 | 3 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 16 | 8 | 136 | 135 | 135 | 1 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 16 | 16 | 128 | 127.5 | 127.5 | 0.5 | 99.6 | 99.6 | 78 | 21.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 200 | 0 | 8 | 192 | 184.5 | 184.5 | 12 | 96.1 | 96.1 | 78 | 18.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 153 | 153 | 7 | 95.6 | 95.6 | 78 | 17.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 200 | 0 | 8 | 192 | 190 | 190 | 2 | 99 | 99 | 78 | 21 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 156 | 156 | 4 | 97.5 | 97.5 | 78 | 19.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 160 | 0 | 0 | 160 | 155.5 | 155.5 | 4.5 | 97.2 | 97.2 | 78 | 19.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 200 | 56 | 8 | 136 | 133.5 | 133.5 | 2.5 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E045 | Louise Carvalho | Cloud & Platform | DevOps Engineer | 120 | 0 | 16 | 104 | 79.5 | 79.5 | 24.5 | 76.4 | 76.4 | 78 | -1.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 0 | 8 | 152 | 135.5 | 135.5 | 16.5 | 89.1 | 89.1 | 78 | 11.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 0 | 0 | 160 | 157.5 | 157.5 | 2.5 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 200 | 32 | 0 | 168 | 166.5 | 166.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 0 | 8 | 152 | 151 | 151 | 1 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 16 | 16 | 128 | 126.5 | 126.5 | 0 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 200 | 0 | 8 | 192 | 185.5 | 185.5 | 5 | 96.6 | 96.6 | 78 | 18.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 200 | 40 | 8 | 152 | 150 | 150 | 2 | 98.7 | 98.7 | 78 | 20.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 0 | 0 | 160 | 128.5 | 128.5 | 23.5 | 80.3 | 80.3 | 78 | 2.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 160 | 16 | 0 | 144 | 71.5 | 71.5 | 74.5 | 49.7 | 49.7 | 78 | -28.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 200 | 16 | 8 | 176 | 87.5 | 87.5 | 88.5 | 49.7 | 49.7 | 78 | -28.3 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E046 | Alexandre Blanc | Cloud & Platform | Platform Engineer | 120 | 0 | 16 | 104 | 40.5 | 40.5 | 63.5 | 38.9 | 38.9 | 78 | -39.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 0 | 8 | 152 | 92.5 | 92.5 | 59.5 | 60.9 | 60.9 | 78 | -17.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 16 | 0 | 144 | 142 | 142 | 2 | 98.6 | 98.6 | 78 | 20.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E047 | Mia Nowak | Cybersecurity | Security Architect | 200 | 0 | 0 | 200 | 196.5 | 196.5 | 8.5 | 98.2 | 98.2 | 78 | 20.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 0 | 8 | 152 | 151.5 | 151.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 0 | 16 | 144 | 143.5 | 143.5 | 0.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E047 | Mia Nowak | Cybersecurity | Security Architect | 200 | 16 | 8 | 176 | 175 | 175 | 7 | 99.4 | 99.4 | 78 | 21.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 24 | 0 | 136 | 132 | 132 | 4 | 97.1 | 97.1 | 78 | 19.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E047 | Mia Nowak | Cybersecurity | Security Architect | 200 | 0 | 8 | 192 | 189 | 189 | 3 | 98.4 | 98.4 | 78 | 20.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 16 | 0 | 144 | 138 | 138 | 4 | 95.8 | 95.8 | 78 | 17.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E047 | Mia Nowak | Cybersecurity | Security Architect | 160 | 8 | 0 | 152 | 148 | 148 | 4 | 97.4 | 97.4 | 78 | 19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E047 | Mia Nowak | Cybersecurity | Security Architect | 200 | 40 | 8 | 152 | 105.5 | 105.5 | 42.5 | 69.4 | 69.4 | 78 | -8.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E047 | Mia Nowak | Cybersecurity | Security Architect | 120 | 0 | 16 | 104 | 39 | 39 | 65 | 37.5 | 37.5 | 78 | -40.5 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 0 | 8 | 152 | 57.5 | 57.5 | 94.5 | 37.8 | 37.8 | 78 | -40.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 0 | 0 | 160 | 160 | 160 | 4 | 100 | 100 | 78 | 22 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 200 | 0 | 0 | 200 | 197.5 | 197.5 | 2.5 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 64 | 8 | 88 | 86 | 86 | 2 | 97.7 | 97.7 | 78 | 19.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 16 | 16 | 128 | 123.5 | 123.5 | 4.5 | 96.5 | 96.5 | 78 | 18.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 200 | 0 | 8 | 192 | 191 | 191 | 1 | 99.5 | 99.5 | 78 | 21.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 16 | 0 | 144 | 138.5 | 138.5 | 5.5 | 96.2 | 96.2 | 78 | 18.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 200 | 8 | 8 | 184 | 180.5 | 180.5 | 3.5 | 98.1 | 98.1 | 78 | 20.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 16 | 0 | 144 | 143.5 | 143.5 | 7.5 | 99.7 | 99.7 | 78 | 21.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 160 | 0 | 0 | 160 | 158.5 | 158.5 | 2 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 200 | 0 | 8 | 192 | 133.5 | 133.5 | 58.5 | 69.5 | 69.5 | 78 | -8.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E048 | Raphaël Meyer | Cybersecurity | Security Engineer | 120 | 0 | 16 | 104 | 54 | 54 | 50 | 51.9 | 51.9 | 78 | -26.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 0 | 8 | 152 | 145 | 145 | 7 | 95.4 | 95.4 | 78 | 17.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 159 | 159 | 1 | 99.4 | 99.4 | 78 | 21.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 200 | 40 | 0 | 160 | 158.5 | 158.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 16 | 8 | 136 | 135 | 135 | 1 | 99.3 | 99.3 | 78 | 21.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 8 | 16 | 136 | 137 | 137 | 0 | 100.7 | 100.7 | 78 | 22.7 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 200 | 0 | 8 | 192 | 187 | 187 | 5 | 97.4 | 97.4 | 78 | 19.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 158 | 158 | 2 | 98.8 | 98.8 | 78 | 20.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 200 | 24 | 8 | 168 | 166.5 | 166.5 | 1.5 | 99.1 | 99.1 | 78 | 21.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 0 | 0 | 160 | 159 | 159 | 1 | 99.4 | 99.4 | 78 | 21.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 160 | 16 | 0 | 144 | 100.5 | 100.5 | 43.5 | 69.8 | 69.8 | 78 | -8.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 200 | 0 | 8 | 192 | 126.5 | 126.5 | 65.5 | 65.9 | 65.9 | 78 | -12.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E049 | Nora Aydin | Consulting | Senior Business Consultant | 120 | 16 | 16 | 88 | 13 | 13 | 75 | 14.8 | 14.8 | 78 | -63.2 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-01 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 0 | 8 | 152 | 105.5 | 105.5 | 46.5 | 69.4 | 69.4 | 78 | -8.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-02 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 0 | 0 | 160 | 113.5 | 113.5 | 46.5 | 70.9 | 70.9 | 78 | -7.1 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-03 | E050 | Mathis Girard | Consulting | Business Consultant | 200 | 16 | 0 | 184 | 131 | 131 | 53 | 71.2 | 71.2 | 78 | -6.8 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-04 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 16 | 8 | 136 | 134 | 134 | 2 | 98.5 | 98.5 | 78 | 20.5 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-05 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 24 | 16 | 120 | 118 | 118 | 2 | 98.3 | 98.3 | 78 | 20.3 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-06 | E050 | Mathis Girard | Consulting | Business Consultant | 200 | 0 | 8 | 192 | 185 | 185 | 7 | 96.4 | 96.4 | 78 | 18.4 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-07 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 8 | 0 | 152 | 149 | 149 | 3 | 98 | 98 | 78 | 20 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-08 | E050 | Mathis Girard | Consulting | Business Consultant | 200 | 0 | 8 | 192 | 190.5 | 190.5 | 1.5 | 99.2 | 99.2 | 78 | 21.2 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-09 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 16 | 0 | 144 | 119 | 119 | 25 | 82.6 | 82.6 | 78 | 4.6 | Balanced | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-10 | E050 | Mathis Girard | Consulting | Business Consultant | 160 | 0 | 0 | 160 | 49 | 49 | 111 | 30.6 | 30.6 | 78 | -47.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-11 | E050 | Mathis Girard | Consulting | Business Consultant | 200 | 40 | 8 | 152 | 45.5 | 45.5 | 106.5 | 29.9 | 29.9 | 78 | -48.1 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
2026-12 | E050 | Mathis Girard | Consulting | Business Consultant | 120 | 0 | 16 | 104 | 24.5 | 24.5 | 79.5 | 23.6 | 23.6 | 78 | -54.4 | Underutilized | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE

## RAID
raid_id | project_id | project_name | raid_type | title | description | impact_rating | probability_rating | overall_rating | owner_name | date_identified | target_resolution_date | status | mitigation_or_action | last_update | classification | synthetic_record
P001-R-01 | P001 | LuxHealth Data Platform | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Maya Fernandes | 2026-01-26 | 2026-05-05 | Open | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P001-R-02 | P001 | LuxHealth Data Platform | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Maya Fernandes | 2026-02-02 | 2026-06-04 | Monitoring | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P001-I-01 | P001 | LuxHealth Data Platform | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Maya Fernandes | 2026-02-09 | 2026-07-04 | Closed | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P001-A-01 | P001 | LuxHealth Data Platform | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Jean Schmit | 2026-02-16 | 2026-08-03 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P001-D-01 | P001 | LuxHealth Data Platform | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Maya Fernandes | 2026-02-23 | 2026-09-02 | Mitigating | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002-R-01 | P002 | Sovereign AI Factory | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Maya Fernandes | 2026-02-23 | 2026-06-02 | Open | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002-R-02 | P002 | Sovereign AI Factory | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Maya Fernandes | 2026-03-02 | 2026-07-02 | Mitigating | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002-I-01 | P002 | Sovereign AI Factory | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Maya Fernandes | 2026-03-09 | 2026-08-01 | Open | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002-A-01 | P002 | Sovereign AI Factory | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Luca Conti | 2026-03-16 | 2026-08-31 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P002-D-01 | P002 | Sovereign AI Factory | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Maya Fernandes | 2026-03-23 | 2026-09-30 | Open | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003-R-01 | P003 | Core Banking Modernisation | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Julien Bernard | 2026-01-26 | 2026-05-05 | Mitigating | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003-R-02 | P003 | Core Banking Modernisation | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Julien Bernard | 2026-02-02 | 2026-06-04 | Monitoring | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003-I-01 | P003 | Core Banking Modernisation | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Julien Bernard | 2026-02-09 | 2026-07-04 | Closed | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003-A-01 | P003 | Core Banking Modernisation | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Amélie Dubois | 2026-02-16 | 2026-08-03 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P003-D-01 | P003 | Core Banking Modernisation | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Julien Bernard | 2026-02-23 | 2026-09-02 | Open | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004-R-01 | P004 | Smart Mobility Analytics | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Julien Bernard | 2026-03-23 | 2026-06-30 | Monitoring | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004-R-02 | P004 | Smart Mobility Analytics | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Julien Bernard | 2026-03-30 | 2026-07-30 | Monitoring | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004-I-01 | P004 | Smart Mobility Analytics | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Julien Bernard | 2026-04-06 | 2026-08-29 | Monitoring | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004-A-01 | P004 | Smart Mobility Analytics | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Luca Conti | 2026-04-13 | 2026-09-28 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P004-D-01 | P004 | Smart Mobility Analytics | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Julien Bernard | 2026-04-20 | 2026-10-28 | Mitigating | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005-R-01 | P005 | Cloud Landing Zone | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Sara Khan | 2026-01-26 | 2026-05-05 | Mitigating | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005-R-02 | P005 | Cloud Landing Zone | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Sara Khan | 2026-02-02 | 2026-06-04 | Open | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005-I-01 | P005 | Cloud Landing Zone | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Sara Khan | 2026-02-09 | 2026-07-04 | Closed | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005-A-01 | P005 | Cloud Landing Zone | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Amélie Dubois | 2026-02-16 | 2026-08-03 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P005-D-01 | P005 | Cloud Landing Zone | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Sara Khan | 2026-02-23 | 2026-08-31 | Monitoring | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006-R-01 | P006 | AML Data Quality | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Sara Khan | 2026-02-23 | 2026-06-02 | Open | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006-R-02 | P006 | AML Data Quality | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Sara Khan | 2026-03-02 | 2026-07-02 | Monitoring | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006-I-01 | P006 | AML Data Quality | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Sara Khan | 2026-03-09 | 2026-08-01 | Closed | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006-A-01 | P006 | AML Data Quality | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Claire Muller | 2026-03-16 | 2026-08-31 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P006-D-01 | P006 | AML Data Quality | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Sara Khan | 2026-03-23 | 2026-09-30 | Open | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007-R-01 | P007 | Cyber Resilience Programme | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Nicolas Wagner | 2026-02-02 | 2026-05-12 | Monitoring | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007-R-02 | P007 | Cyber Resilience Programme | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Nicolas Wagner | 2026-02-09 | 2026-06-11 | Open | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007-I-01 | P007 | Cyber Resilience Programme | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Nicolas Wagner | 2026-02-16 | 2026-07-11 | Mitigating | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007-A-01 | P007 | Cyber Resilience Programme | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Jean Schmit | 2026-02-23 | 2026-08-10 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P007-D-01 | P007 | Cyber Resilience Programme | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Nicolas Wagner | 2026-03-02 | 2026-09-09 | Monitoring | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008-R-01 | P008 | Customer 360 Platform | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Nicolas Wagner | 2026-04-27 | 2026-08-04 | Open | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008-R-02 | P008 | Customer 360 Platform | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Nicolas Wagner | 2026-05-04 | 2026-09-03 | Mitigating | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008-I-01 | P008 | Customer 360 Platform | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Nicolas Wagner | 2026-05-11 | 2026-10-03 | Monitoring | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008-A-01 | P008 | Customer 360 Platform | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Amélie Dubois | 2026-05-18 | 2026-11-02 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P008-D-01 | P008 | Customer 360 Platform | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Nicolas Wagner | 2026-05-25 | 2026-12-02 | Mitigating | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009-R-01 | P009 | ERP Integration | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Maya Fernandes | 2026-01-26 | 2026-05-05 | Monitoring | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009-R-02 | P009 | ERP Integration | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Maya Fernandes | 2026-02-02 | 2026-06-04 | Open | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009-I-01 | P009 | ERP Integration | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Maya Fernandes | 2026-02-09 | 2026-07-04 | Closed | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009-A-01 | P009 | ERP Integration | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Amélie Dubois | 2026-02-16 | 2026-08-03 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P009-D-01 | P009 | ERP Integration | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Maya Fernandes | 2026-02-23 | 2026-09-02 | Mitigating | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010-R-01 | P010 | GenAI Knowledge Assistant | Risk | Specialist availability may constrain critical delivery activities | Specialist availability may constrain critical delivery activities. | High | Medium | High | Nicolas Wagner | 2026-05-25 | 2026-09-01 | Monitoring | Confirm named backup resources and protect critical allocation. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010-R-02 | P010 | GenAI Knowledge Assistant | Risk | Client approval cycles may delay acceptance milestones | Client approval cycles may delay acceptance milestones. | Medium | High | High | Nicolas Wagner | 2026-06-01 | 2026-10-01 | Mitigating | Agree approval SLA and escalate overdue decisions through governance. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010-I-01 | P010 | GenAI Knowledge Assistant | Issue | A dependency has delivered incomplete or unstable input | A dependency has delivered incomplete or unstable input. | High | High | Critical | Nicolas Wagner | 2026-06-08 | 2026-10-31 | Mitigating | Run daily triage, define workaround and assign recovery owner. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010-A-01 | P010 | GenAI Knowledge Assistant | Assumption | Required client environments and test data will remain available | Required client environments and test data will remain available. | Medium | Medium | Medium | Luca Conti | 2026-06-15 | 2026-11-30 | Validated | Validate assumption at each stage gate. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE
P010-D-01 | P010 | GenAI Knowledge Assistant | Dependency | Go-live depends on client security and infrastructure approval | Go-live depends on client security and infrastructure approval. | High | Medium | High | Nicolas Wagner | 2026-06-22 | 2026-12-18 | Open | Track evidence and decision dates in the integrated plan. | Action reviewed in the latest project status meeting. | PROJECT_MANAGEMENT_RESTRICTED | TRUE

## Change Requests
change_request_id | project_id | project_name | request_date | change_type | requested_by | description | business_reason | estimated_cost_impact_eur | estimated_schedule_impact_days | decision_status | decision_date | approved_cost_impact_eur | approved_schedule_impact_days | decision_owner | classification | synthetic_record
CR-001 | P001 | LuxHealth Data Platform | 2026-08-21 | Technical | Synthetic Client A S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 36000 | 5 | Pending |  | 0 | 0 | Jean Schmit | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-002 | P001 | LuxHealth Data Platform | 2026-03-05 | Schedule | Synthetic Client A S.A. | Client dependency moved the planned test window. | Protect delivery quality, compliance or business value. | 25000 | 3 | Approved | 2026-03-17 | 25000 | 3 | Jean Schmit | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-003 | P002 | Sovereign AI Factory | 2026-07-29 | Schedule | Synthetic Client B S.A. | Client dependency moved the planned test window. | Protect delivery quality, compliance or business value. | 65000 | 5 | Rejected | 2026-08-04 | 0 | 0 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-004 | P002 | Sovereign AI Factory | 2026-08-18 | Compliance | Synthetic Client B S.A. | Additional evidence and security validation requested. | Protect delivery quality, compliance or business value. | 36000 | 15 | Approved | 2026-08-23 | 36000 | 15 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-005 | P003 | Core Banking Modernisation | 2026-07-29 | Compliance | Synthetic Client C S.A. | Additional evidence and security validation requested. | Protect delivery quality, compliance or business value. | 12000 | 8 | Pending |  | 0 | 0 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-006 | P003 | Core Banking Modernisation | 2026-04-20 | Scope | Synthetic Client C S.A. | Additional reporting and controls requested by client. | Protect delivery quality, compliance or business value. | 36000 | 15 | Approved | 2026-05-03 | 36000 | 15 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-007 | P004 | Smart Mobility Analytics | 2026-10-16 | Scope | Synthetic Client D S.A. | Additional reporting and controls requested by client. | Protect delivery quality, compliance or business value. | 36000 | 8 | Approved | 2026-10-30 | 36000 | 8 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-008 | P004 | Smart Mobility Analytics | 2026-08-28 | Technical | Synthetic Client D S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 65000 | 8 | Pending |  | 0 | 0 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-009 | P005 | Cloud Landing Zone | 2026-03-18 | Technical | Synthetic Client E S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 65000 | 3 | Pending |  | 0 | 0 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-010 | P005 | Cloud Landing Zone | 2026-07-16 | Schedule | Synthetic Client E S.A. | Client dependency moved the planned test window. | Protect delivery quality, compliance or business value. | 36000 | 15 | Approved | 2026-07-27 | 36000 | 15 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-011 | P006 | AML Data Quality | 2026-04-08 | Schedule | Synthetic Client F S.A. | Client dependency moved the planned test window. | Protect delivery quality, compliance or business value. | 48000 | 0 | Approved | 2026-04-13 | 48000 | 0 | Claire Muller | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-012 | P006 | AML Data Quality | 2026-09-08 | Compliance | Synthetic Client F S.A. | Additional evidence and security validation requested. | Protect delivery quality, compliance or business value. | 25000 | 15 | Approved | 2026-09-21 | 25000 | 15 | Claire Muller | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-013 | P007 | Cyber Resilience Programme | 2026-03-11 | Compliance | Synthetic Client G S.A. | Additional evidence and security validation requested. | Protect delivery quality, compliance or business value. | 65000 | 0 | Approved | 2026-03-17 | 65000 | 0 | Jean Schmit | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-014 | P007 | Cyber Resilience Programme | 2026-09-03 | Scope | Synthetic Client G S.A. | Additional reporting and controls requested by client. | Protect delivery quality, compliance or business value. | 48000 | 0 | Approved | 2026-09-16 | 48000 | 0 | Jean Schmit | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-015 | P007 | Cyber Resilience Programme | 2026-05-29 | Technical | Synthetic Client G S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 12000 | 15 | Approved | 2026-06-10 | 12000 | 15 | Jean Schmit | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-016 | P008 | Customer 360 Platform | 2026-10-30 | Scope | Synthetic Client H S.A. | Additional reporting and controls requested by client. | Protect delivery quality, compliance or business value. | 18000 | 0 | Approved | 2026-11-04 | 18000 | 0 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-017 | P008 | Customer 360 Platform | 2026-09-16 | Technical | Synthetic Client H S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 25000 | 5 | Rejected | 2026-09-25 | 0 | 0 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-018 | P009 | ERP Integration | 2026-06-21 | Technical | Synthetic Client I S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 25000 | 3 | Rejected | 2026-06-28 | 0 | 0 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-019 | P009 | ERP Integration | 2026-07-07 | Schedule | Synthetic Client I S.A. | Client dependency moved the planned test window. | Protect delivery quality, compliance or business value. | 48000 | 5 | Approved | 2026-07-17 | 48000 | 5 | Amélie Dubois | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-020 | P010 | GenAI Knowledge Assistant | 2026-09-15 | Scope | Synthetic Client J S.A. | Additional reporting and controls requested by client. | Protect delivery quality, compliance or business value. | 25000 | 3 | Rejected | 2026-09-24 | 0 | 0 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE
CR-021 | P010 | GenAI Knowledge Assistant | 2026-09-05 | Technical | Synthetic Client J S.A. | Architecture adjustment required after integration discovery. | Protect delivery quality, compliance or business value. | 18000 | 0 | Pending |  | 0 | 0 | Luca Conti | PROJECT_MANAGEMENT_RESTRICTED | TRUE

## Exceptions
exception_id | month | employee_id | employee_name | department | exception_type | expected_hours | logged_hours | client_project_hours | approval_status | severity | recommended_action | classification | synthetic_record
EX-0001 | 2026-05 | E001 | Sophie Lambert | Finance | Timesheet status is Pending | 160 | 158 | 10.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0002 | 2026-06 | E001 | Sophie Lambert | Finance | Timesheet status is Pending | 200 | 200 | 25 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0003 | 2026-01 | E002 | Marc Hoffmann | Finance | Timesheet status is Pending | 160 | 160 | 16 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0004 | 2026-03 | E002 | Marc Hoffmann | Finance | Timesheet status is Pending | 200 | 200 | 38.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0005 | 2026-07 | E002 | Marc Hoffmann | Finance | Timesheet status is Rejected ¦ Under-logged by 12.0 hours | 160 | 148 | 24.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0006 | 2026-03 | E003 | Elena Rossi | Finance | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 200 | 192 | 39 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0007 | 2026-11 | E003 | Elena Rossi | Finance | Timesheet status is Pending | 200 | 200 | 39 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0008 | 2026-09 | E005 | Nadia Benali | Finance | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 160 | 154 | 33.5 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0009 | 2026-10 | E005 | Nadia Benali | Finance | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 27 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0010 | 2026-05 | E006 | Jean Schmit | Executive | Timesheet status is Pending | 160 | 160 | 12.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0011 | 2026-10 | E006 | Jean Schmit | Executive | Timesheet status is Pending | 160 | 158 | 14 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0012 | 2026-11 | E006 | Jean Schmit | Executive | Timesheet status is Pending | 200 | 200 | 17 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0013 | 2026-05 | E008 | Luca Conti | Executive | Timesheet status is Pending | 160 | 160 | 35 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0014 | 2026-11 | E009 | Amélie Dubois | Executive | Timesheet status is Pending | 200 | 200 | 14.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0015 | 2026-07 | E013 | Sara Khan | Project Management | Timesheet status is Pending | 160 | 160 | 157 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0016 | 2026-09 | E013 | Sara Khan | Project Management | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 160 | 154 | 82 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0017 | 2026-12 | E014 | Nicolas Wagner | Project Management | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 120 | 114 | 78.5 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0018 | 2026-08 | E017 | Amina Amar | Data & AI | Timesheet status is Rejected ¦ Under-logged by 5.5 hours | 200 | 194.5 | 172 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0019 | 2026-05 | E018 | Gabriel Simon | Data & AI | Timesheet status is Pending | 160 | 160 | 133 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0020 | 2026-06 | E019 | Eva Moreau | Data & AI | Timesheet status is Pending | 200 | 200 | 173.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0021 | 2026-08 | E019 | Eva Moreau | Data & AI | Timesheet status is Rejected | 200 | 200 | 189.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0022 | 2026-09 | E019 | Eva Moreau | Data & AI | Timesheet status is Pending | 160 | 160 | 160 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0023 | 2026-11 | E020 | Antoine Robert | Data & AI | Timesheet status is Pending | 200 | 204 | 126 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0024 | 2026-08 | E021 | Lea Nguyen | Data & AI | Timesheet status is Rejected | 200 | 199.5 | 149.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0025 | 2026-10 | E021 | Lea Nguyen | Data & AI | Timesheet status is Pending | 160 | 160 | 154.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0026 | 2026-05 | E022 | Hugo Laurent | Data & AI | Timesheet status is Pending | 160 | 160 | 117 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0027 | 2026-06 | E023 | Mila Costa | Cloud & Platform | Timesheet status is Pending | 200 | 200 | 190 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0028 | 2026-07 | E023 | Mila Costa | Cloud & Platform | Timesheet status is Pending | 160 | 160 | 153.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0029 | 2026-03 | E024 | Louis Fontaine | Cloud & Platform | Timesheet status is Pending | 200 | 200 | 197 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0030 | 2026-04 | E024 | Louis Fontaine | Cloud & Platform | Timesheet status is Pending | 160 | 158.5 | 130 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0031 | 2026-07 | E024 | Louis Fontaine | Cloud & Platform | Timesheet status is Pending | 160 | 160 | 115 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0032 | 2026-01 | E026 | Noah Durand | Cybersecurity | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 160 | 154 | 138.5 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0033 | 2026-11 | E026 | Noah Durand | Cybersecurity | Timesheet status is Pending | 200 | 200.5 | 188.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0034 | 2026-02 | E027 | Emma Lopez | Cybersecurity | Timesheet status is Rejected | 160 | 158.5 | 158 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0035 | 2026-05 | E027 | Emma Lopez | Cybersecurity | Timesheet status is Pending | 160 | 160.5 | 144 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0036 | 2026-06 | E027 | Emma Lopez | Cybersecurity | Timesheet status is Rejected | 200 | 201 | 191 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0037 | 2026-10 | E027 | Emma Lopez | Cybersecurity | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 160 | 154 | 94.5 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0038 | 2026-02 | E028 | Arthur Mercier | Consulting | Timesheet status is Rejected | 160 | 160 | 159.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0039 | 2026-08 | E029 | Chloé Diallo | Consulting | Timesheet status is Pending | 200 | 200 | 174 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0040 | 2026-03 | E030 | Rayan Fischer | Applications | Timesheet status is Pending | 200 | 200.5 | 168.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0041 | 2026-07 | E030 | Rayan Fischer | Applications | Timesheet status is Rejected | 160 | 159.5 | 157 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0042 | 2026-06 | E031 | Lucie Pereira | Applications | Timesheet status is Rejected | 200 | 200.5 | 174.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0043 | 2026-07 | E031 | Lucie Pereira | Applications | Timesheet status is Rejected | 160 | 160 | 131.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0044 | 2026-08 | E031 | Lucie Pereira | Applications | Timesheet status is Pending | 200 | 200 | 181.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0045 | 2026-12 | E031 | Lucie Pereira | Applications | Timesheet status is Rejected ¦ Under-logged by 14.0 hours | 120 | 106 | 55 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0046 | 2026-01 | E032 | Maxime Richard | Applications | Timesheet status is Pending | 160 | 162 | 104.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0047 | 2026-06 | E032 | Maxime Richard | Applications | Timesheet status is Pending | 200 | 200.5 | 165.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0048 | 2026-09 | E032 | Maxime Richard | Applications | Timesheet status is Rejected | 160 | 160 | 158 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0049 | 2026-10 | E032 | Maxime Richard | Applications | Timesheet status is Pending | 160 | 160 | 117 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0050 | 2026-12 | E032 | Maxime Richard | Applications | Timesheet status is Pending | 120 | 120 | 22 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0051 | 2026-02 | E033 | Aya Bauer | Sales | Timesheet status is Pending | 160 | 156 | 15.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0052 | 2026-03 | E033 | Aya Bauer | Sales | Timesheet status is Pending | 200 | 200 | 19.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0053 | 2026-04 | E033 | Aya Bauer | Sales | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 16 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0054 | 2026-03 | E034 | Victor Renard | Sales | Timesheet status is Pending | 200 | 200 | 19 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0055 | 2026-11 | E035 | Alice Meier | HR | Timesheet status is Pending | 200 | 200 | 0 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0056 | 2026-08 | E036 | Nathan Cohen | HR | Timesheet status is Pending | 200 | 200 | 0 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0057 | 2026-12 | E036 | Nathan Cohen | HR | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 120 | 114 | 0 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0058 | 2026-08 | E037 | Lina Gomes | Operations | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 200 | 192 | 0 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0059 | 2026-09 | E037 | Lina Gomes | Operations | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 0 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0060 | 2026-07 | E038 | Paul Lemoine | Data & AI | Timesheet status is Pending | 160 | 160 | 142.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0061 | 2026-08 | E039 | Jade Santos | Data & AI | Timesheet status is Pending | 200 | 200 | 189.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0062 | 2026-04 | E040 | Adam Klein | Data & AI | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 62 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0063 | 2026-12 | E040 | Adam Klein | Data & AI | Timesheet status is Pending | 120 | 120 | 80 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0064 | 2026-12 | E041 | Zoé Marques | Data & AI | Timesheet status is Rejected ¦ Under-logged by 6.0 hours | 120 | 114 | 36.5 | Rejected | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0065 | 2026-06 | E042 | Samuel Jung | Data & AI | Timesheet status is Rejected | 200 | 199 | 157.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0066 | 2026-11 | E042 | Samuel Jung | Data & AI | Timesheet status is Pending | 200 | 200 | 190 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0067 | 2026-12 | E042 | Samuel Jung | Data & AI | Timesheet status is Pending | 120 | 120 | 64 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0068 | 2026-03 | E043 | Manon Franco | Data & AI | Timesheet status is Pending | 200 | 200 | 119.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0069 | 2026-04 | E043 | Manon Franco | Data & AI | Timesheet status is Pending | 160 | 160 | 120.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0070 | 2026-12 | E043 | Manon Franco | Data & AI | Timesheet status is Pending | 120 | 120.5 | 79.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0071 | 2026-02 | E044 | Yanis Vidal | Cloud & Platform | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 113.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0072 | 2026-10 | E044 | Yanis Vidal | Cloud & Platform | Timesheet status is Pending | 160 | 160 | 110.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0073 | 2026-11 | E044 | Yanis Vidal | Cloud & Platform | Timesheet status is Pending | 200 | 200 | 125.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0074 | 2026-06 | E045 | Louise Carvalho | Cloud & Platform | Timesheet status is Rejected | 200 | 204.5 | 184.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0075 | 2026-08 | E045 | Louise Carvalho | Cloud & Platform | Timesheet status is Pending | 200 | 200 | 190 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0076 | 2026-05 | E046 | Alexandre Blanc | Cloud & Platform | Timesheet status is Rejected | 160 | 158.5 | 126.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0077 | 2026-06 | E046 | Alexandre Blanc | Cloud & Platform | Timesheet status is Rejected | 200 | 198.5 | 185.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0078 | 2026-09 | E046 | Alexandre Blanc | Cloud & Platform | Timesheet status is Rejected ¦ Under-logged by 8.0 hours | 160 | 152 | 128.5 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0079 | 2026-09 | E047 | Mia Nowak | Cybersecurity | Timesheet status is Rejected | 160 | 158 | 138 | Rejected | High | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0080 | 2026-11 | E049 | Nora Aydin | Consulting | Timesheet status is Pending | 200 | 200 | 126.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0081 | 2026-05 | E050 | Mathis Girard | Consulting | Timesheet status is Pending | 160 | 160 | 118 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0082 | 2026-08 | E050 | Mathis Girard | Consulting | Timesheet status is Pending | 200 | 200 | 190.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE
EX-0083 | 2026-12 | E050 | Mathis Girard | Consulting | Timesheet status is Pending | 120 | 120 | 24.5 | Pending | Medium | PM or line manager to review, correct and re-approve the timesheet. | PROJECT_MANAGEMENT_RESTRICTED_PERSONAL | TRUE

## Dashboard
Synthetic Project Portfolio Dashboard — FY2026
Portfolio KPI | Value
Projects | 10
Named employees | 50
Timesheet lines | 10288
Client-project hours | 56322
Actual project cost | 5730841.69
Adjusted cost budget | 6778439.92
Estimate at completion | 6359707.53
Forecast variance | 418732.39
Project | Completion % | Actual Cost | EAC | Variance | RAG
LuxHealth Data Platform | 84.3 | 849179.75 | 941874.26 | 21325.43 | Amber
Sovereign AI Factory | 93.5 | 704621.73 | 771839.95 | 32724.78 | Green
Core Banking Modernisation | 88.3 | 920227.06 | 1021061.58 | 36126.87 | Red
Smart Mobility Analytics | 79.8 | 521882.49 | 593067.48 | 33772.24 | Amber
Cloud Landing Zone | 93.7 | 510911.81 | 563077.79 | 37067.79 | Amber
AML Data Quality | 88.2 | 372779.17 | 409231.12 | 71530.33 | Red
Cyber Resilience Programme | 90.6 | 811798.86 | 890286.54 | 125498.43 | Green
Customer 360 Platform | 76.3 | 347800.85 | 397165.29 | 16143.5 | Amber
ERP Integration | 89 | 363999.45 | 405740.3 | 46950.59 | Red
GenAI Knowledge Assistant | 79.6 | 327640.52 | 366363.22 | -2407.57 | Red